## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (Tender No.70/SE/PMU of 2022-23) |  |  | VCH/001026/2022-2023 | BP-2022-23-337 | 29/09/2022 |  | J.S. CONSTRUCTION | 28.62 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-K) of Purulia District under Purulia Division, PHE Dte. (Tender No.60/EE/PD of 2022-23) |  |  | VCH/001074/2022-2023 | BP-2022-23-436 | 28/11/2022 |  | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 12.93 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Tender No.61/EE/PD of 2022-23) |  |  | VCH/001075/2022-2023 | BP-2022-23-435 | 28/11/2022 |  | HARI NARAYAN YADAV CONSTRUCTION CO | 8.89 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (SL - 4) (Tender No.69/EE/PD of 2022-23) |  |  | VCH/001167/2022-2023 | BP-2022-23-331 | 29/09/2022 |  | M/S. BIMALENDU BOSE | 38.12 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Supply of Fuel & lubricant bill for AWC Bandwan Block. |  |  | BILL/00348/2022-2023 | BP-2022-23-850 | 31/03/2023 |  | M/S SHANKAR AUTO SERVICE | 8.26 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000139/2022-2023 | 752/PD | 02/05/2022 | 16/06/2022 | HARI NARAYAN YADAV CONSTRUCTION CO | 23.72 | 9.65 | 40.69 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000138/2022-2023 | 751/PD | 02/05/2022 | 16/06/2022 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 23.73 | 7.19 | 30.32 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000134/2022-2023 | 748/PD | 02/05/2022 | 16/06/2022 | JYOTY SOLAR POWER | 47.51 | 44.21 | 93.06 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000137/2022-2023 | 750/PD | 02/05/2022 | 16/06/2022 | MEGA SOLAR ENERGY | 47.47 | 46.13 | 97.18 | 0
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-M) & 2 nos AWC within Bandwan Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer |  | ORD/000816/2022-2023 | 1709/PD | 22/11/2022 | 06/01/2023 | GOUTAM CHAKRABORTY | 66.41 | 54.22 | 81.64 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Bandwan Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | Assistant Engineer |  | ORD/000821/2022-2023 | 1710/PD | 22/11/2022 | 06/01/2023 | PRINCE INDUSTRIES ( INDIA) | 91.77 | 86.73 | 94.51 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply tap connection arrangement for 09 nos. AWC within Bandwan block (Part-F) of Purulia District under Purulia Division, PHE Dte. [Tender No 213/2022-2023 of EE/PD] |  |  | VCH/001649/2022-2023 | BP-2022-23-533 | 11/01/2023 |  | BOSE CONSTRUCTION | 25.99 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply tap connection arrangement for 11 nos. AWC within Bandwan block (Part-C) of Purulia District under Purulia division, PHE Dte. (Phase-III) [Tender No 837/2022-2023 of EE/PD] |  |  | VCH/001648/2022-2023 | BP-2022-23-532 | 11/01/2023 |  | BOSE CONSTRUCTION | 34.13 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Supply and delivery of 200 mm dia UPVC pipe for Purulia-I Block and other Blocks at Drilling Store/Site under Purulia Mechanical Division, P.H.E Dte. (Tender No.262/EE/PMD of 2022-23) |  |  | VCH/001670/2022-2023 | BP-2022-23-512 | 22/12/2022 |  | COMBINE ENTERPRISES | 16.67 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 26 nos AWC within Bandwan Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000955/2022-2023 | 33/PD | 09/01/2023 | 23/02/2023 | ROY CONSTRUCTION | 14.05 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Bandwan Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000132/2022-2023 | 745/PD | 02/05/2022 | 16/06/2022 | BOSE CONSTRUCTION | 70.87 | 40.82 | 57.6 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Bandwan Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2022-2023 | 746/PD | 02/05/2022 | 16/06/2022 | SOUHARDYA BUSINESS LINE | 71.09 | 54.34 | 76.43 | 75
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (SL - 4) | Assistant Engineer | Junior Engineer | ORD/000627/2022-2023 | 1158/PD | 01/08/2022 | 15/09/2022 | M/S. BIMALENDU BOSE | 158.35 | 86.73 | 54.77 | 100
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 1250/PD | 30/08/2022 | 14/10/2022 | PREMNATH MITRA | 197.98 | 70.71 | 35.72 | 82
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000628/2022-2023 | 1157/PD | 01/08/2022 | 15/09/2022 | J.S. CONSTRUCTION | 158.35 | 104.56 | 66.03 | 100
21 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2022-2023 | 749/PD | 02/05/2022 | 16/06/2022 | SOUMITRA CHAKRABORTY | 47.47 | 37.38 | 78.76 | 100
22 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000822/2022-2023 | 1711/PD | 22/11/2022 | 06/01/2023 | BOSE CONSTRUCTION | 91 | 43.75 | 48.08 | 100
Total | [13 empty] | 1283.37 | 686.43 | 53.49