## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Water supply Tap Connection Arrangement for 12 nos AWC within Bagmundi Block (Part-B), 08 nos AWC within Bagmundi Block (Part-E-1) & 04 nos AWC within Bagmundi Block (Part-F-1) of Purulia District under Purulia Division, PHE Dte. (Phase-I) (Without Tubewell) (SL-13) | Assistant Engineer |  | ORD/001039/2022-2023 | 212/PD | 13/02/2023 | 30/03/2023 | MANASH GHOSH | 113.58 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Baghmundi Block (Part-C) of Purulia District under Purulia Division, PHE Dte. (Without Tubewell) (SL-2) | Assistant Engineer | JUNIOR ENGINEER | ORD/001065/2022-2023 | 300/PD | 28/02/2023 | 14/04/2023 | MIDNAPUR PIPE CONCERN | 117.72 | 65.91 | 55.99 | 65
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Bagmundi Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000487/2021-2022 | 498/PD | 29/03/2022 | 13/05/2022 | KANTILAL SAO | 15.78 | 14.29 | 90.57 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Baghmundi Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000875/2022-2023 | 1853/PD | 13/12/2022 | 27/01/2023 | KM ENTERPRISES | 49.52 | 47.1 | 95.11 | 75
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Jhalda-II Block & Baghmundi Block (Part-A)of Purulia District under Purulia Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000572/2022-2023 | 1127/PD | 25/07/2022 | 08/09/2022 | SINGHA ENTERPRISE | 94.88 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos. AWC within Jhalda-I, Arsha & Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001329/2022-2023 | 1050_PD | 08/07/2022 | 22/08/2022 | PRASENJIT BASAK | 157.97 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Bagmundi Block (Part-A), 08 nos AWC within Bagmundi Block (Part-E-2) & 04 nos AWC within Bagmundi Block (Part-F-2) of Purulia District under Purulia Division, PHE Dte. (Phase-II) (Without Tubewell) (SL. No. 12) | Assistant Engineer | Junior Engineer | ORD/001193/2022-2023 | 462/PD | 27/03/2023 | 04/06/2025 | ZEOLITE FRESH INDIA | 113.57 | 0 | 0 | 60
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 18 nos AWC within Bagmundi Block (Part-D), 02 nos AWC within Bagmundi Block (Part-E-3) & 04 nos AWC within Bagmundi Block (Part-F-3) of Purulia District under Purulia Division, PHE Dte. (Phase-III) (Without Tubewell) (SL. No. 14) | Assistant Engineer | JUNIOR ENGINEER | ORD/001066/2022-2023 | 301/PD | 28/02/2023 | 17/02/2025 | ARINDAM MAJUMDAR | 113.55 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | SM/10284 | Anganwadi | Installation of 02 (Two) nos. 1.00 H.P. capacity Solar Photovoltaic Submersible Pump set in pre-existing / new bore Tube well along with 1200 Watt peak capacity Solar photovoltaic array panels on steel structure including Supply & Delivery of approved quality materials & Geophysical investigation by electrologging with all allied works at Majhidi and sahebbon Village within Ajodhya WSS in Purulia District of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000657/2024-2025 | 1876/PD | 01/10/2024 | 15/11/2024 | ROY CONSTRUCTION | 22.83 | 0 | 0 | 0
Total | [13 empty] | 799.4 | 127.31 | 15.93