## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Supply and delivery of 200 mm dia UPVC pipe for Purulia-I Block and other Blocks at Drilling Store/Site under Purulia Mechanical Division, P.H.E Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000183/2022-2023 | 754/PMD | 07/11/2022 | 07/12/2022 | COMBINE ENTERPRISES | 16.67 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Providing skilled labor for operation of big dia & small dia DTH drilling with departmental rig unit 26D/AR under Purulia Mechanical Division PHE Dte. (Tender No.19/EE/PMD of 2022-23) |  |  | VCH/000457/2022-2023 | BP-2022-23-256 | 15/09/2022 | 15/09/2022 | NUPUR CHANDRA HALDER | 0.81 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rig bore tube well at different AWC under JJM Programme (Fuel & Lubricant bill) |  |  | VCH/001048/2022-2023 | BP-2022-23-392 | 19/10/2022 | 19/10/2022 | M/S SHANKAR AUTO SERVICE | 14.86 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Durku GP is Purulia-I block under Purulia Mechanical Division PHE Dte. (T/N 136/EE/PMD of 2022-23) |  |  | VCH/000416/2022-2023 |  | 13/08/2022 | 13/08/2022 | ANUP KUMAR SAHA | 43.17 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Submission of 01(One) Hand Receipt for fuel bill in respect of construction of Rig Board Tube Well at different AWC Programme. |  |  | VCH/000663/2022-2023 |  | 25/09/2022 | 25/09/2022 | M/S SHANKAR AUTO SERVICE | 14.86 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Providing hire boar skilled & experienced drivers for driving Departmental Rig Mounted tracks & supporting vehicle of Rig mounted tracks & operating vehicle rig unit 26D/AR & 13D/AR & other vehicle under Purulia Mechanical Division PHE Dte. (Tender No.118/EE/PMD of 2019-20) |  |  | VCH/000455/2022-2023 | BP-2022-23-264 | 16/09/2022 | 16/09/2022 | SANTU MITRA | 0.88 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Execution of electrical restor query for ground water availability by experience qualified geologist..... Nadiha Udaypur GP in Para Block & other Area for RBTW source erection in AWC with in Purulia Mechanical Division PHE Dte. (Tender No.169/EE/PMD of 2022-23) |  |  | VCH/000456/2022-2023 | BP-2022-23-255 | 15/09/2022 | 15/09/2022 | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Durku GP, Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2022-2023 | 454/PMD | 04/07/2022 | 19/07/2022 | ANUP KR. SAHA | 34.97 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm X 165mm) by DTH method in different source less AWC at Ajodhya GP, Baghmundi Block under Purulia Mechanical Division,P.H.E Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000211/2022-2023 | 784/PMD | 24/11/2022 | 09/12/2022 | M DHARA & BROTHERS | 37.83 | 25.48 | 67.35 | 0
10 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Execution of the yield test at Dubra, Anara GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. |  |  | ORD/000321/2022-2023 | 32/PMSD(Drilling) | 03/02/2023 | 18/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
11 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Para Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000281/2022-2023 | 73/PMD | 31/01/2023 | 02/03/2023 | SUMIT KR. CHAKRABORTY | 75.71 | 24.4 | 32.22 | 0
12 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mmx165mm) by DTH method in different sourceless AWC at Lagda GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000241/2022-2023 | 28/PMD | 17/01/2023 | 27/01/2023 | KHITISH CH. PATHAK | 15.86 | 15.81 | 99.73 | 0
13 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Execution of the yield test at Anara GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. |  |  | ORD/000331/2022-2023 | 27/PMSD(Drilling) | 02/02/2023 | 17/02/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0.98 | 100 | 0
14 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Purulia-l Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia |  |  | ORD/000278/2022-2023 | 71/PMD | 31/01/2023 | 20/02/2023 | RABINDRA NATH KHAN | 37.84 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 7 nos AWC within Purulia-I Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000973/2022-2023 | 40/PD | 09/01/2023 | 23/02/2023 | S. S. ENTERPRISE | 3.89 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Name of Work: Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Manara GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000001/2023-2024 | 383/PMD | 06/04/2023 | 16/04/2023 | GOUTAM CHAKRABORTY | 12.69 | 11.66 | 91.85 | 0
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2022-2023 | 756/PD | 02/05/2022 | 16/06/2022 | SK ABBAS | 26.93 | 14.45 | 53.66 | 100
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Purulia-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2022-2023 | 760/PD | 02/05/2022 | 16/06/2022 | M/S CHAKRABORTY CONSTRUCTION | 13.54 | 9.01 | 66.51 | 0
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Purulia-I Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2022-2023 | 761/PD | 02/05/2022 | 16/06/2022 | ASHOKE ADHIKARY | 13.52 | 8.51 | 62.92 | 100
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 10 nos AWC within PURULIA-I Block (Part-K,L,M,N,N,O,P,Q,R) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000907/2022-2023 | 1868/PD | 13/12/2022 | 27/01/2023 | MAHARSHI BANERJEE | 47.3 | 37.18 | 78.6 | 80
21 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200x165mm) by DTH method in different sourceless AWC at Bhandarpuara GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000240/2022-2023 | 27/PMD | 17/01/2023 | 06/02/2023 | M/S D. PALIT & CO. | 44.35 | 34.13 | 76.97 | 0
22 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Durku GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000002/2023-2024 | 384/PMD | 06/04/2023 | 16/04/2023 | SEN BROTHERS | 12.68 | 12.67 | 99.92 | 100
23 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Sonaijuri GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000003/2023-2024 | 385/PMD | 06/04/2023 | 16/04/2023 | S. PATHAK & CO. | 6.34 | 6.26 | 98.7 | 100
24 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Washing and developing of tube well for AWC programme at Purulia-I ,Purulia-II and other block under PMD, PHE, Dte.(2nd call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000026/2023-2024 | 413/PMD | 12/04/2023 | 27/04/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 3.58 | 3.41 | 95 | 100
25 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Providing skilled labour for operation of big dia & small dia DTH drilling with departmental rig unit 26D/AR under Purulia Mechanical Division PHE Dte. (Tender No.19/EE/PMD of 2022-23) |  |  | VCH/001090/2022-2023 | BP-2022-23-215 | 24/08/2022 | 24/08/2022 | NUPUR CHANDRA HALDER | 0.13 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Durku GP in Purulia-I block under Purulia Mechanical Division PHE Dte. (Tender No 136/EE/PMD of 2022-23) |  |  | VCH/001093/2022-2023 | BP-2022-23-212 | 24/08/2022 | 24/08/2022 | ANUP KUMAR SAHA | 34.96 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Supply and delivery of Cummins filter & some other items at store under PMD, PHE Dte. (Tender No- 08/2022-23 of EE/PMD) |  |  | VCH/001100/2022-2023 | BP-2022-23-221 | 24/08/2022 | 24/08/2022 | MAHIPAL MAJHI | 1.29 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Repairing and regular maintenance of 2 nos water tanker (WB89-2339 & WB89-2305) and all other allied works under Purulia Mechanical Division, PHE Dte. (Tender No- 40/2022-23 of EE/PMD) |  |  | VCH/001091/2022-2023 | BP-2022-23-216 | 24/08/2022 | 24/08/2022 | PINTU DEY | 0.59 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Yield test of Purulia-I, Purulia-II, Joypur, Jhalda-I, Jhalda-II and other blocks in the District of Purulia under PMD, PHE Dte. (Tender No- 25/2022-23 of EE/PMD) |  |  | VCH/001092/2022-2023 | BP-2022-23-217 | 24/08/2022 | 24/08/2022 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 2.18 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Maintenance and minor repairing of vehicle No WAW-1992 (Swaraj Mazda) VWS-849 and minor modification work of ATR-711 under Purulia Mechanical Division, PHE Dte. (Tender No- 129/2022-23 of EE/PMD) |  |  | VCH/001089/2022-2023 | BP-2022-23-214 | 24/08/2022 | 24/08/2022 | NUPUR CHANDRA HALDER | 0.78 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Supply and delivery of drilling adaptor, Rod lifter, Rod guide bush at store under PMD, PHE Dte. (Tender No- 22/2022-23 of EE/PMD) |  |  | VCH/001101/2022-2023 | BP-2022-23-213 | 24/08/2022 | 24/08/2022 | UJJAL DIESEL SERVICE | 3.25 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Purulia-I Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-D, G & K) | Assistant Engineer | Junior Engineer | ORD/000284/2022-2023 | 825/PD | 17/05/2022 | 01/07/2022 | MEGA SOLAR ENERGY | 90.64 | 41.14 | 45.39 | 100
33 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Purulia-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2022-2023 | 755/PD | 02/05/2022 | 16/06/2022 | FIDERE MARINE SERVICES PVT LTD | 40.81 | 26.04 | 63.8 | 100
34 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2022-2023 | 757/PD | 02/05/2022 | 16/06/2022 | SUBODH PRAMANIK | 26.88 | 26.32 | 97.92 | 100
35 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000147/2022-2023 | 759/PD | 02/05/2022 | 16/06/2022 | THE BUSINESS ENGINEERS INDIA | 27.18 | 24.08 | 88.59 | 100
36 | PURULIA |  | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200x165mm) by DTH method in different sourceless AWC at Dimdiha GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia |  |  | ORD/000242/2022-2023 | 29/PMD | 17/01/2023 | 06/02/2023 | SOUMITRA CHAKRABOTY | 25.35 | 21.89 | 86.36 | 100
37 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewell ssinked at various Schools & AWCs of . Kashipur & Para Blocks under Purulia Division ,PHE,Dte. | Assistant Engineer | Junior Engineer | ORD/001381/2023-2024 | 1737/PD | 04/12/2023 | 03/01/2024 | SANJAY KUMAR NARSARIA | 14.03 | 8.88 | 63.33 | 65
38 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 1250/PD | 30/08/2022 | 01/04/2025 | PREMNATH MITRA | 197.98 | 86.98 | 43.93 | 100
Total | [13 empty] | 951.25 | 440.25 | 46.28