## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Digha G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000157/2022-2023 | 1047/BMD | 23/08/2022 | 22/09/2022 | SUMIT KUMAR CHAKRABORTY | 48.32 | 0 | 0 | 0
2 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depths. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Sarbori G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000163/2022-2023 | 1053/BMD | 23/08/2022 | 02/10/2022 | SINGHA ENTERPRISE | 61.13 | 0 | 0 | 0
3 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different sourceless AWC at Guniara G.P in Neturia Block in the Distric of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000158/2022-2023 | 1048/BMD | 23/08/2022 | 17/09/2022 | SUMIT KUMAR CHAKRABORTY | 35.44 | 0 | 0 | 0
4 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Janardandih G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000159/2022-2023 | 1049/BMD | 23/08/2022 | 12/09/2022 | ANUP KUMAR SAHA | 32.44 | 0 | 0 | 0
5 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Bhamunia, Saltora, Rayesba G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000160/2022-2023 | 1050/BMD | 23/08/2022 | 22/09/2022 | ANUP KUMAR SAHA | 48.66 | 0 | 0 | 0
6 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Rayesbandh G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000161/2022-2023 | 1051/BMD | 23/08/2022 | 02/10/2022 | CHAKRABORTY MAINING & ENGINEERING. | 72.84 | 0 | 0 | 0
7 | PURULIA |  | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Saltore G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | Assistant Engineer |  | ORD/000162/2022-2023 | 1052/BMD | 23/08/2022 | 02/10/2022 | PRINCE INDUSTRIES (INDIA) | 67.13 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 28/2022-23 of EE/PD) |  |  | VCH/001055/2022-2023 | BP-2022-23-400 | 20/10/2022 | 20/10/2022 | NATIONAL CONSTRUCTION | 12.09 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 20 nos AWC within HUra Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-II)" | Assistant Engineer | Junior Engineer | ORD/000826/2022-2023 | 1706/PD | 22/11/2022 | 06/01/2023 | SHWET BARANI | 95.6 | 0 | 0 | 35
10 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-I Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000962/2022-2023 | 42/PD | 09/01/2023 | 23/02/2023 | DEBANJAN SEAL | 1.66 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 58 nos AWC within Nituria Block ) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000958/2022-2023 | 36/PD | 09/01/2023 | 23/02/2023 | ASHOK KUMAR CHATTERJEE | 32.2 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000477/2021-2022 | 473/PD | 24/03/2022 | 08/05/2022 | NATIONAL CONSTRUCTION | 47.04 | 0 | 0 | 100
13 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000476/2021-2022 | 462/PD | 24/03/2022 | 08/05/2022 | WRISHI ENTERPRISE | 47.04 | 0 | 0 | 100
14 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Acceptance cum Work Order For "Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte." | Assistant Engineer |  | ORD/000800/2022-2023 | 1727/PD | 22/11/2022 | 06/01/2023 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 24.79 | 0 | 0 | 100
15 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within JHALDA-1 Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000880/2022-2023 | 1858/PD | 13/12/2022 | 27/01/2023 | PRINCE INDUSTRIES ( INDIA) | 99.23 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within JHALDA-1 Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000881/2022-2023 | 1859/PD | 13/12/2022 | 27/01/2023 | M/S. BIMALENDU BOSE | 99.22 | 0 | 0 | 100
17 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Jhalda-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (SL-4) | Assistant Engineer | JUNIOR ENGINEER | ORD/001040/2022-2023 | 269/PD | 24/02/2023 | 10/04/2023 | SINGHA ENTERPRISE | 165.14 | 0 | 0 | 100
18 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Jhalda-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000550/2022-2023 | 1050/PD | 08/07/2022 | 22/08/2022 | PRASENJIT BASAK | 157.97 | 0 | 0 | 100
19 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within JHALDA -I BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000220/2022-2023 | 799/PD | 05/05/2022 | 01/09/2025 | S AND P ENTERPRISE | 219.6 | 0 | 0 | 100
20 | PURULIA |  | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Jhalda-I Block (Part-E) & 9 nos AWC within Jhalda-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Phase-I) (Sl. No. 11) | Assistant Engineer | JUNIOR ENGINEER | ORD/001041/2022-2023 | 268/PD | 24/02/2023 | 11/06/2025 | MOTI RAHAMAN | 147.74 | 0 | 0 | 100
Total | [13 empty] | 1515.28 | 0 | 0