## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 185/2022-23 of EE/PD) |  |  | VCH/001040/2022-2023 | BP-2022-23-372 | 19/10/2022 | 19/10/2022 | SUDHANSHU OJHA | 6.8 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) (Tender No- 404/2022-23 of EE/PD) |  |  | VCH/001056/2022-2023 | BP-2022-23-403 | 20/10/2022 | 20/10/2022 | SUPRIYA MAHANTI MISHRA | 8.44 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bongabari(Zone-III) Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000386/2022-2023 | 217/PMD | 28/02/2023 | 30/03/2023 | COMBINE ENTERPRISES | 21.61 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply, Delivery and installation 75kva voltage stabilizer for Augmentation of Bongabari w/s scheme(Zone-II) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000429/2022-2023 | 239/PMD | 03/03/2023 | 02/05/2023 | MOUSUMI BENERJEE | 8.01 | 0 | 0 | 15
5 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Repairing, renovation & restoration of Pump House with Panel room including roof treatment at Namo Pindra River site of Bongabari W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000045/2023-2024 | 660/PD | 17/05/2023 | 16/07/2023 | SABYASACHI MISHRA | 4.19 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Laying of HDPE pipe as distribution main (loop line) from Surulia Road Side Hari Mandir to Surulia Shiv Mandir in Surulia village for drinking water supply through FHTC to met up the water crisis at Uppar Surulia Village from existing Bongabari W/S scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2021-2022 | 94/PSD | 14/03/2022 | 29/03/2022 | SOUVIK MANDAL | 4.6 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer |  | ORD/000109/2022-2023 | 645/PD | 22/04/2022 | 06/06/2022 | SUPRIYA MAHANTI MISHRA | 10.98 | 0 | 0 | 80
8 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2022-2023 | 648/PD | 22/04/2022 | 06/06/2022 | KABERI DUTTA | 9.84 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000623/2022-2023 | 1390/PD | 01/09/2022 | 16/10/2022 | SOUVIK MANDAL | 23.21 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Temporary Car Shed near guest house under JJM / Jalswanpa under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000829/2022-2023 | 1723/PD | 22/11/2022 | 06/01/2023 | BOSE CONSTRUCTION | 4.99 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Repairing and Restoration of damaged 125 mm dia pipe line at bongabari near Club to Bangabari more & Rest shed to Jack pushing point and 75 mm dia from Hatuara Firm main gate to DIET-II Campus and 100mm dia GI pipe road Crossing near Surulia more for Surulia Bauri Para of Purulia-II Block area to drinking water supply under Bongabari Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000835/2022-2023 | 1737/PD | 22/11/2022 | 06/01/2023 | SADHAN GORAIN | 5.7 | 0 | 0 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001217/2022-2023 | 505/PD | 31/03/2023 | 15/05/2023 | KABERI DUTTA | 2.92 | 0 | 0 | 100
13 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 611/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.03 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Hatuara Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000621/2022-2023 | 1392/PD | 01/09/2022 | 01/01/2026 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 45 | 0 | 0 | 90
15 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Palashkola and Gopalpur Mouza of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000832/2022-2023 | 1724/PD | 22/11/2022 | 01/01/2026 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 54.03 | 0 | 0 | 90
16 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village including extention of distribution pipe line (Gap Portion) of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/001052/2022-2023 | 284/PD | 27/02/2023 | 13/04/2023 | SIDDHARTHA SANKAR SARKAR | 23 | 0 | 0 | 100
17 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bongabari w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000410/2022-2023 | 238/PMD | 03/03/2023 | 02/05/2023 | COMBINE ENTERPRISES | 77.44 | 0 | 0 | 15
18 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation at Bongabari w/s scheme(Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000469/2022-2023 | 309/PMD | 16/03/2023 | 15/04/2023 | TAPAN KUMAR DEY | 21.6 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply delivery and installation of Internal lighting and external lighting at Proposed Pump House for Augmentation of Bongabari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000129/2023-2024 | 867/PMD | 21/07/2023 | 19/09/2023 | KANTILAL SAO | 2.84 | 0 | 0 | 0
20 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Proposed pump house Bongabari w/s(Zone-II) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000055/2023-2024 | 524/PMD | 05/05/2023 | 04/07/2023 | DEY ENTERPRISE, HOWRAH | 37.81 | 0 | 0 | 20
21 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Naudiha habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000145/2024-2025 | 916/PD | 07/05/2024 | 01/04/2025 | KM ENTERPRISES | 40.61 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Laying of 250 mm DI rising main from Mahara CWR to Hatuara OHR for augmentation of Bongabari W/S scheme at Purulia-II block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000147/2024-2025 | 918/PD | 07/05/2024 | 06/07/2024 | TAPAN CHANDRA | 84.23 | 0 | 0 | 75
23 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Emergency piling work along with sand filling at collecting line trenches for protection work against flash flood at Sirkabad W/S Scheme under Purulia Division,PHE Dte.(Under Bongabari W/S Scheme) |  |  | ORD/003545/2023-2024 | 324/PD | 01/03/2024 | 15/04/2024 | SUBRATA MAHAPATRA | 34.58 | 0 | 0 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at Proposed pump house (Zone-II) site with other allied works under Bongabari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000543/2023-2024 | 374/PMD | 04/03/2024 | 03/05/2024 | TAPAN KUMAR DEY | 5.82 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pathardih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000247/2024-2025 | 1140/PD | 18/06/2024 | 02/08/2024 | ASHOKE ADHIKARY | 31.61 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000622/2022-2023 | 1391/PD | 01/09/2022 | 16/10/2022 | GOUTAM CHAKRABORTY | 39.1 | 0 | 0 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Office Room Cum Godown Room within Purulia Sadar Sub-division campus under JJM/Jal Swapna Programme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000842/2022-2023 | 1744/PD | 22/11/2022 | 21/05/2023 | BOSE CONSTRUCTION | 38.36 | 0 | 0 | 100
28 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing additional Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000921/2022-2023 | 1929/PD | 22/12/2022 | 05/02/2023 | GOUTAM CHAKRABORTY | 38.42 | 0 | 0 | 100
29 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply & installation of submersible pumping machinery at River Bed Tubewell for Augmentation of Bongabari w/s(River site) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000431/2022-2023 | 250/PMD | 06/03/2023 | 05/05/2023 | SEN BROTHERS | 8.99 | 0 | 0 | 90
30 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Over Head Reservoir (OHR) of 500 Cum Capacity, Staging Height 25 mtr. at Birgiri Mouza of Bangabari W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E Dte. (SL - 2) | Assistant Engineer | Junior Engineer-1 | ORD/001106/2022-2023 | 354/PD | 14/03/2023 | 09/12/2023 | MS CHANDI CHARAN ROY | 138.29 | 0 | 0 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Namo Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001218/2022-2023 | 506/PD | 31/03/2023 | 15/05/2023 | SUDHANSHU OJHA | 5.3 | 0 | 0 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river near Samsan Ghat at Puncha under Bongabari W/S Scheme of Purulia Sadar Sub- Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000871/2023-2024 | 1521/PD | 16/10/2023 | 15/12/2023 | SOUVIK MANDAL | 43.94 | 0 | 0 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Boundary wall & Sinking of T/well at Mahara Tolapathardih(Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003483/2023-2024 | 361/PD | 04/03/2024 | 03/05/2024 | GANGULY ENTERPRISES | 20.05 | 0 | 0 | 100
34 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Laying of DI pipeline and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Sirkabad W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.(Under Bongabari W/S Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003546/2023-2024 | 329/PD | 01/03/2024 | 30/04/2024 | HIRAK KUMAR SAO | 8.04 | 0 | 0 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Left out HDPE Distribution main Pipe line from Hatuara OHR site to existing distribution main of Bongabari W/S scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000141/2024-2025 | 924/PD | 07/05/2024 | 06/07/2024 | GOUTAM CHAKRABORTY | 64.54 | 0 | 0 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 1103/PD | 11/06/2024 | 11/06/2024 | Resource Division | 289.91 | 0 | 0 | 0
37 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Payment of WBSEDCL quotation for new power connection at Bongabari W/S Scheme (Zone-II), Mahara, under PMD, PHE Dte. |  |  | BILL/00342/2024-2025 | BP-24-25-112 | 23/08/2024 | 23/08/2024 | WBSEDCL PURULIA | 8.05 | 0 | 0 | 0
38 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river at Namopindra village of Bongabari W/S scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000874/2023-2024 | 1524/PD | 16/10/2023 | 01/03/2025 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.43 | 0 | 0 | 85
39 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage and Construction of 200 cum capacity CWR & Pump house including panel room & chlorination room, Boundary Wall at Mahara of Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000191/2024-2025 | 922/PD | 07/05/2024 | 01/02/2025 | SUBRATA MAHAPATRA | 72 | 0 | 0 | 50
40 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery with other allied work for direct pumping at Mahara (Zone - III) of Augmentation of Bongabari water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2024-2025 | 1017/PMD | 25/06/2024 | 01/10/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 49.03 | 0 | 0 | 25
41 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Continuation work order for the work of Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division, P.H.E Dte. (500 cubic meter capacity Over Head Reservoir of Bongabari W/S Scheme within Purulia Sadar Sub-Division under Purulia Division P.H.E Dte.) | Assistant Engineer | Junior Engineer-1 | ORD/001324/2022-2023 | 313/PD | 02/03/2023 | 01/07/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
42 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahara Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000120/2024-2025 | 913/PD | 07/05/2024 | 01/01/2026 | SANTANU BANERJEE | 29.87 | 0 | 0 | 0
43 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jitdih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/000143/2024-2025 | 914/PD | 07/05/2024 | 01/01/2026 | MAHARSHI BANERJEE | 32.57 | 0 | 0 | 0
44 | PURULIA |  | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Supply, Delivery and Installation of Openwell submersible pumping machinery with other allied works at Bongabari w/s scheme (Pindra) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000622/2024-2025 | 1544/PMD | 11/11/2024 | 01/10/2025 | M/S A.D. CONCERN | 3.09 | 0 | 0 | 30
45 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Guard room with Toilet at Bongabari OHR campus for Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. |  |  | ORD/001314/2024-2025 | 457/PD | 24/03/2025 | 22/07/2025 | MAHATO CONSTRUCTION | 7.22 | 0 | 0 | 0
46 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer-1 | ORD/000108/2022-2023 | 644/PD | 22/04/2022 | 01/01/2025 | SIDDHARTHA SANKAR SARKAR | 10.99 | 0 | 0 | 100
47 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Laying of 225 mm dia.(OD) HDPE Pipe as Rising main at Upar Pindra Village of Pindra G.P. of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000841/2022-2023 | 1743PD | 22/11/2022 | 01/01/2026 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 43.16 | 0 | 0 | 100
48 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Laying of Pipe for distribution pipe line (Gap Portion) to providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/001204/2022-2023 | 491/PD | 31/03/2023 | 01/01/2025 | SIDDHARTHA SANKAR SARKAR | 20.25 | 0 | 0 | 100
49 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000110/2022-2023 | 646/PD | 22/04/2022 | 06/06/2022 | INDRAJIT SARKAR | 10.99 | 0 | 0 | 100
50 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Repairing of DI Pipeline and Repairing & Construction of boundary wall at Puncha Riversite Pump house Site under Puncha W/S Scheme under,Manbazar-II Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000870/2023-2024 | 1523/PD | 16/10/2023 | 25/05/2025 | KANAILAL PAL | 24.14 | 0 | 0 | 100
51 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Construction of Boundary wall & Sinking of T/well at Bongabari (Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003485/2023-2024 | 360/PD | 04/03/2024 | 01/10/2024 | M/S CONTRACTORS SYNDICATE | 29.93 | 0 | 0 | 100
52 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | New Sinking of 3 (Three) Nos 200 mm dia river bed vertical tubewell along with necessary 100 mm dia GI collecting line from River bed Tubewell to CWR at river bank (Kansabati River) at Pindra under Bangabari W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000210/2024-2025 | 1078/PD | 07/06/2024 | 22/07/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.94 | 0 | 0 | 100
53 | PURULIA |  | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dubkidi Habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000144/2024-2025 | 915/PD | 07/05/2024 | 03/11/2024 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 48.75 | 0 | 0 | 100
Total | [13 empty] | 1716.06 | 0 | 0