## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Supply and Delivery of DI Fittings And Valve For Arsha and its Adjoing Mouza W/S Scheme of Purulia Sadar Sub-Division Under Purulia Division Phe Dte. | Assistant Engineer |  | ORD/000852/2022-2023 | 1756/PD | 22/11/2022 | 07/12/2022 | AMAL KUMAR MUKHERJEE | 2.65 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Painting, fixing of water level indicator, brickwork at ground floor and other allied works related to Over Head Reservoir of 100 Cum Capacity at fasko mouza under Arsha water supply scheme(Zone-II) of Purulia Division, P.H.E. Dte. |  |  | ORD/000277/2024-2025 | 1233/PD | 03/07/2024 | 01/09/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.42 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain etc. complete at Arsha Zone-III for Augmentation of Arsha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. |  |  | ORD/001083/2024-2025 | 2178/PD | 13/12/2024 | 13/03/2025 | SADHAN GORAIN | 5.27 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under Zone-1 command area of Arsha & its Adjoing Mouza Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Zone-1, GP-Arsha,Village-Rangamati, Habitation-Rangamati- 624 nos,Pattarn-136Nos, Santaldih-25 nos, Asharamdih-68 nos) | Assistant Engineer | Junior Engineer-3 | ORD/000843/2022-2023 | 1745/PD | 22/11/2022 | 06/01/2023 | TUMPA GORAIN | 62.69 | 31.11 | 49.62 | 100
5 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Extension of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-3, GP-Arsha,Village-Tumba) Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000995/2022-2023 | 108/PD | 20/01/2023 | 19/02/2023 | MOONLIGHT HOUSE | 24.38 | 19.33 | 79.26 | 100
6 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Supplying & laying of Parallel line and Branch line of HDPE pipe for Distribution System of Arsha W/S Scheme(Zone-1) under Purulia Division PHE Dte. (Mouza Name-Rangamati)(Village Name-Asaramdih) | Assistant Engineer | Junior Engineer-3 | ORD/000659/2023-2024 | 1350/PD | 13/09/2023 | 13/10/2023 | TUMPA GORAIN | 12.98 | 9.77 | 75.27 | 100
7 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Construction of RCC elevated reservoir of capacity 100 cum & staging height 20 mtr. for Arsha W/S Scheme at (Zone-II) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001295/2022-2023 | 802/PD | 05/05/2022 | 31/12/2022 | ANUP KUMAR SAHA | 30.47 | 29.83 | 97.89 | 75
8 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Construction of Boundary wall at Arsha Zone-2 OHR Site and Making Bypass Arrangement at OHR Site under Arsha W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001870/2023-2024 | 95/PD | 15/01/2024 | 15/03/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 25.58 | 22.63 | 88.46 | 100
9 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Laying Gap portion DI Rising Main & Distribution for zone-II and Laying in new alignment of Distribution Pipeline due to Construction village Road at Zone III with Construction protection wall for Rising Main pipeline of Arsha & Its Adjoining Mouza W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000849/2023-2024 | 1488/PD | 12/10/2023 | 11/11/2023 | SADHAN GORAIN | 20.19 | 10.21 | 50.54 | 80
10 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Supplying & Laying of Distribution pipeline and Providing FHTC at Arsha W/S Scheme (Zone-3) under Purulia Division PHE Dte. (Mouza Covered-Arsha,Khedadih,Tumba) | Assistant Engineer | Junior Engineer-3 | ORD/000345/2024-2025 | 1370/PD | 25/07/2024 | 15/10/2025 | SADHAN GORAIN | 39.24 | 0 | 0 | 45
11 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Laying of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-2, GP-Arsha,Village-Fasko) Water Supply Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/000993/2022-2023 | 106/PD | 20/01/2023 | 30/01/2025 | KANTILAL SAO | 33.89 | 4.77 | 14.07 | 100
12 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Laying of Distribution pipeline of Arsha W/S Scheme (Zone-1) under Purulia Division PHE Dte.(Mouza Covered Rangamati,Pattanr,Asaramdih) | Assistant Engineer | Junior Engineer-3 | ORD/000344/2024-2025 | 1369/PD | 25/07/2024 | 21/04/2025 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 24.74 | 0 | 0 | 100
13 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Construction of Staff Toilet at Arsha riversite pump house under Arsha Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000122/2024-2025 | 889/PD | 07/05/2024 | 04/09/2024 | MRINAL KANTI GORAI | 4.07 | 0 | 0 | 100
14 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Laying of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-3, GP-Arsha,Village-Arsha) Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000992/2022-2023 | 105/PD | 20/01/2023 | 20/04/2023 | MS GORAIN CONCERN | 82.04 | 34.81 | 42.43 | 72
15 | PURULIA |  | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | SM/10544 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of distribution Pipeline of Arsha (Zone-III) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tumba Village] | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/000248/2024-2025 | 1141/PD | 18/06/2024 | 01/04/2026 | MOONLIGHT HOUSE | 6.65 | 0 | 0 | 0
Total | [13 empty] | 384.29 | 162.45 | 42.27