## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) |  |  | VCH/000327/2022-2023 |  | 03/08/2022 | 03/08/2022 | NANIGOPAL DEY | 4.08 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II (Tender No.48/22-23/SE/PMU/WBPWSP(P) |  |  | VCH/001023/2022-2023 | BP-2022-23-320 | 29/09/2022 | 29/09/2022 | NIBHAS SINHA | 120.95 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I. (Tender No- 79/2022-23 of SE/PMU/WBPWSP(P) ) |  |  | VCH/001067/2022-2023 | BP-2022-23-411 | 28/10/2022 | 28/10/2022 | MIDNAPUR PIPE CONCERN | 16.62 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Installation of 3000 mm dia X 1800 mm 2 Nos. Pressure Shell and Pressure Type Iron Elimination Plant for WTP at Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 792/PD | 05/05/2022 | 19/06/2022 | ANUP KUMAR SAHA | 66.12 | 66.11 | 99.99 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Blower Room at Para Water supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2022-2023 | 328/RNP | 01/06/2022 | 30/08/2022 | DEBDAT GANGULY | 4.04 | 2.83 | 70.09 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Repairing of Pump House Cum Chlorine Room With Sanitary and Water Supply Arrangement at Tube Well Headwork Site under Para W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000366/2022-2023 | 329/RNP | 01/06/2022 | 22/06/2022 | SABYASACHI MISHRA | 1.15 | 0 | 0 | 85
7 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Para W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000387/2022-2023 | 339/RNP | 01/06/2022 | 01/07/2022 | MOYTEC | 1.4 | 1.4 | 100 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 180 cum / 200 Cum with other allied works at Para Pump House site under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Divisioin, PHE Dte. | Assistant Engineer |  | ORD/000335/2022-2023 | 866/PD | 23/05/2022 | 31/08/2022 | ADITYA HAZRA | 25.24 | 23.12 | 91.58 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | Assistant Engineer |  | ORD/000501/2022-2023 | 1010/PD | 29/06/2022 | 13/08/2022 | NIBHAS SINHA | 444.92 | 322.9 | 72.58 | 95
10 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of 2 Nos. 3 mtr dia Intake well at Harai river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Para W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000917/2022-2023 | 1926/PD | 22/12/2022 | 22/03/2023 | M/S KARUNAMOYEE CONSTRUCTION | 14.83 | 11.22 | 75.7 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Work for Parrllel Distribution system with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. Part-II | Assistant Engineer | Junior Engineer | ORD/000181/2023-2024 | 997/PD | 26/07/2023 | 24/09/2023 | NIBHAS SINHA | 95.82 | 91.19 | 95.17 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 959/PD | 20/06/2022 | 20/06/2022 | Resource Division | 19.57 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 981/PD | 22/06/2022 | 22/06/2022 | Resource Division | 176.36 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) |  |  | VCH/000326/2022-2023 | BP-2022-23-171 | 11/08/2022 | 11/08/2022 | NANIGOPAL DEY | 1.28 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Para W/S Scheme, Block- Para) ) to be augmentated/ retrofitting under Purulia Division, PHE Dte. (Tender No- 537/2021-22 of EE/PD) |  |  | VCH/000917/2022-2023 | BP-2022-23-117 | 16/07/2022 | 16/07/2022 | RADIANT | 6.26 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Refreshment bill paid for office meeting to Circuit House. |  |  | BILL/00575/2023-2024 | BP-2023-24-352 | 07/08/2023 | 07/08/2023 | SHREEMA SWEETS | 0.22 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | New Connection for Augmentation of para W/S |  |  | BILL/00247/2023-2024 | BP-23-24-151 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.233/EE/PD of 2022-23) |  |  | VCH/001097/2022-2023 | BP-2022-23-171 | 11/08/2022 | 11/08/2022 | NANIGOPAL DEY | 4.08 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Repairing of pump house cum chlorine room with sanitary and water supply arrangement at T/W head work site under Para W/s Scheme of Raghunathpur Sub- Division, PHE Dte. [Tender No 215/2022-23 of EE/PD] |  |  | VCH/001539/2022-2023 | BP-2022-23-685 | 01/03/2023 | 01/03/2023 | SABYASACHI MISHRA | 0.82 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Car bill for office purpose against vehicle reg. no.WB-55A/4524 & paid for the month of June to Aug,2022. |  |  | VCH/001903/2022-2023 | BP-2023-24-57 | 04/05/2023 | 04/05/2023 | ANUP KUMAR SAHA | 1.17 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Bill of the IEC programes done in 10 blocks during ARANYA SAPTAHA. |  |  | BILL/00676/2023-2024 | BP-2023-24-414 | 25/08/2023 | 25/08/2023 | M/S SAYAK BHATTACHARYA | 0.97 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Car bill paid for office purpose against Reg. No.WB-55A/7171 paid for the month of Nov & Dec,23. |  |  | VCH/001900/2022-2023 | BP-2023-24-53 | 28/04/2023 | 28/04/2023 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply, delivery fitting & fixing of 2 Nos. Scheme Description Sign boards (6' X 3') under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location :- (Hariharpur) & Head Work site (Hariharpur Basti) | Assistant Engineer | Junior Engineer | ORD/001930/2023-2024 | 23/RNP | 15/01/2024 | 22/01/2024 | M/S SAYAK BHATTACHARYA | 0.34 | 0 | 0 | 0
24 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at para water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000686/2024-2025 | 1698/PMD | 06/12/2024 | 06/03/2025 | KAMAKHYA ENTERPRISE | 15.46 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | Assistant Engineer | Junior Engineer | ORD/000735/2022-2023 | 1253/PD | 30/08/2022 | 14/10/2022 | MIDNAPUR PIPE CONCERN | 109.03 | 21.28 | 19.52 | 92
26 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 650 cum, Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000914/2022-2023 | 1888/PD | 15/12/2022 | 11/09/2023 | NIBHAS SINHA | 151.46 | 56.79 | 37.5 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Laying of Clear Water Rising Main at Hariharpur area from intake to OHR under Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000979/2022-2023 | 84/PD | 17/01/2023 | 17/04/2023 | TAPAN CHANDRA | 38.38 | 9.77 | 25.47 | 25
28 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Para water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000375/2022-2023 | 205/PMD | 28/02/2023 | 29/04/2023 | M/S D. PALIT & CO. | 15.06 | 0 | 0 | 100
29 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Para (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000038/2023-2024 | 444/PMD | 20/04/2023 | 20/05/2023 | MS SAJAHAN CHOWDHURY | 21.63 | 0 | 0 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of Pump House (8 mtr X 7.5 mtr) at Head Work Site under Para W/S Scheme of Raghunathpur Construction Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 832/PD | 26/06/2023 | 24/09/2023 | GANGULY ENTERPRISES | 23.07 | 13 | 56.37 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Sinking of 4 (Four) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Para W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001813/2023-2024 | 43/PD | 09/01/2024 | 23/02/2024 | MANATOSH SINGH | 16.73 | 0 | 0 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Laying distribution System with FHTC work (540Nos.), restoration of concrete road and with allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II. | Assistant Engineer | Junior Engineer | ORD/001689/2023-2024 | 1865/PD | 21/12/2023 | 19/02/2024 | NIBHAS SINHA | 43.26 | 0 | 0 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Bypass arrangement of Old rising main pipe line (Old OHR site ) to new rising main pipe line and new rising main pipe line to new OHR Inlet and distribution pipe line connection with all allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000461/2024-2025 | 1520/PD | 27/08/2024 | 11/10/2024 | TAPAN CHANDRA | 6.63 | 0 | 0 | 100
34 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Restoration of concrete check dam with Ancillary structure as and when needed at Harirampur Intake Site of Para W/S Scheme under Raghunathpur Sub-Division, Under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003457/2023-2024 | 331/PD | 01/03/2024 | 15/04/2024 | SAMAN KUMAR MAHATO | 39.52 | 0 | 0 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Connecting line with manifold at two nos Intake to Iron Elevation Plant of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000137/2024-2025 | 908/PD | 07/05/2024 | 06/07/2024 | M/S KARUNAMOYEE CONSTRUCTION | 8.8 | 0 | 0 | 100
36 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply, Delivery and laying of 185 sq mm XLPE cable at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000592/2024-2025 | 1450/PMD | 01/10/2024 | 31/10/2024 | SUMIT KUMAR CHAKRABORTY | 4.24 | 0 | 0 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Repairing of DI Rising Main & Sinking of 4(Four ) Nos. 200 mm dia DTH rigboredtubewell with 1 H.P. Submersible Pumping Machinary with allied works at Anara Girls' High School, Para S.N. High School, Dubra High School & Anara S.E. Railway Colony High School for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 1098/PD | 07/06/2024 | 06/08/2024 | M/S SAYAK BHATTACHARYA | 22.57 | 0 | 0 | 100
38 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply and Delivery and installation intake well cover & allied work at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000679/2024-2025 | 1691/PMD | 06/12/2024 | 05/01/2025 | PINTU DEY | 2.04 | 0 | 0 | 100
39 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of Blower room and Other Allied Works at Para Head work Site of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001207/2024-2025 | 2331/PD | 31/12/2024 | 02/05/2025 | RANI SATI CONSTRUCTION | 4.99 | 0 | 0 | 0
40 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Construction of sump at Pump House of Para head work site under Aug. of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000350/2025-2026 | 428/RNP | 12/08/2025 | 19/08/2025 | GANGULY ENTERPRISES | 0.49 | 0 | 0 | 0
41 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, backwash pumping machineries, MCC panel, H.O.T., Flowmwter and other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000373/2022-2023 | 203/PMD | 28/02/2023 | 29/04/2023 | RABINDRA NATH KHAN | 76.22 | 13.88 | 18.21 | 100
42 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Para w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000374/2022-2023 | 204/PMD | 28/02/2023 | 29/04/2023 | PINTU DEY | 10.13 | 4.41 | 43.51 | 100
43 | PURULIA |  | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Internal and external illumination with other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000017/2023-2024 | 388/PMD | 06/04/2023 | 16/06/2025 | M/S KARUNAMOYEE CONSTRUCTION | 5.33 | 0 | 0 | 40
44 | PURULIA |  | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | SM/10718 | Augmentation | Supply, delivery fitting & fixing of 52 Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Hura & Para Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001152/2024-2025 | 2303/PD | 31/12/2024 | 01/03/2025 | AMIT PATHAK | 4.75 | 0 | 0 | 100
Total | [13 empty] | 1634.18 | 637.91 | 39.04