## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No- 577/2022-23 of EE/PD) |  |  | VCH/001069/2022-2023 | BP-2022-23-422 | 11/11/2022 | 11/11/2022 | RAKSHIT ENTERPRISE | 4.34 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | New sinking of 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000541/2022-2023 | 1060/PD | 08/07/2022 | 07/08/2022 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 28.64 | 14.75 | 51.5 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 600 cum (Intze Type), Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000924/2022-2023 | 1897/PD | 15/12/2022 | 11/09/2023 | DEBAKI RANJAN SARKAR | 148.87 | 105.73 | 71.02 | 72
4 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Reconditioning of filter Bed by Changing of Filter Media of WTP and Inside & Outside Painting Of WTP Structures & Intake Bridge at Mouza Ghat of Manbazar II Block (part) W/S Scheme of Purulia Sadar Sub-Division under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000109/2023-2024 | 871/PD | 30/06/2023 | 30/07/2023 | ANUP KUMAR SAHA | 25.51 | 9.26 | 36.3 | 80
5 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000326/2022-2023 | 858/PD | 23/05/2022 | 31/08/2022 | ROY CONSTRUCTION | 13.86 | 12.93 | 93.33 | 98
6 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-I, Zone-II & Zone-V of Habitation- Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-I),(1. GP-Kumari, Habitation-Toparbad,Tilaboni,Susunia,Rangametya, Manikdi, Kumari, Kuchlifela, Dhanda, Boch ,Khariduara Alis Balarampur, 2) Dighi GP-Tamakhun, Jhariadi.) | Assistant Engineer | Junior Engineer-3 | ORD/000620/2022-2023 | 1393/PD | 01/09/2022 | 16/10/2022 | ANUP KUMAR SAHA | 11.23 | 10.03 | 89.27 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000502/2022-2023 | 438/PSD | 24/06/2022 | 04/07/2022 | RAKSHIT ENTERPRISE | 4.39 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Laying of distribution pipeline at different School & ICDS center for providing 21 nos Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of Manbazar W/S Scheme of Manbazar-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000007/2023-2024 | 535/PD | 12/04/2023 | 11/06/2023 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 4.4 | 3.99 | 90.53 | 91
9 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1016/PD | 05/07/2022 | 05/07/2022 | Resource Division | 132.89 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 968/PD | 21/06/2022 | 21/06/2022 | Resource Division | 120.16 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 241/PD | 20/02/2023 | 20/02/2023 | Resource Division | 217.33 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 988/PD | 23/06/2022 | 23/06/2022 | Resource Division | 0.47 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 612/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 3.1 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Manbazar W/S Scheme, Block- Manbazar-I) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 539/2021-22 of EE/PD) |  |  | VCH/000916/2022-2023 | BP-2022-23-118 | 16/07/2022 | 16/07/2022 | RADIANT | 6.62 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Regarding laying of water supply pipe line along PWD Land on (i) Manbazar_Bansa Road at ch.0.00 Kmp to 0.765 Km & Damda-Chakoltore-Dradi-Kenda-Manbazar Road at ch. 45.526 to 46.00 Kmp (ii) Indkuri-Manbazar Road at ch.0.00 Km to 0.850 Km, (iii) Sindri-Manbazar Road at ch. 17.00 Kmp to 17.80 Km, (iV) Manbazar-Bandwan-Kuilapal Road at ch. 0.00 kmp to 0.636 Km in respect of Augumentation of Manbazar Water suplly Scheme under JJM. |  |  | BILL/00028/2022-2023 | BP-2022-23-464 | 09/12/2022 | 09/12/2022 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 146.74 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : CHARKI, RAMNAGAR, KHALPARA, KENBEDYA, KASATORA (Part), MANBAZAR (Part) VILLAGE] (2nd Call) | Assistant Engineer | Junior Engineer-3 | ORD/000533/2022-2023 | 1049/PD | 08/07/2022 | 22/08/2022 | EQUIPMENTS AND SPARES AGENCIES | 128.82 | 71.83 | 55.76 | 90
17 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000432/2022-2023 | 251PMD | 06/03/2023 | 05/05/2023 | MOON LIGHT HOUSE | 12.08 | 11.18 | 92.56 | 80
18 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell at Manbazar w/s(zone-1) scheme under PMD, PHE Dte. in the District of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000433/2022-2023 | 252/PMD | 06/03/2023 | 05/05/2023 | SANTANU BANERJEE | 48.12 | 40.92 | 85.04 | 57
19 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Shifting and laying of DI rising main and HDPE distribution main pipeline from manbazar Bus stand to warehouse along manbazar- Bandwan road due to widening of PWD road at Manbazar-1 block under Manbazar-I Water Supply Scheme Under Purulia Division ,PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000039/2023-2024 | 667/PD | 17/05/2023 | 16/07/2023 | ROY CONSTRUCTION | 15.28 | 3.42 | 22.36 | 75
20 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 19/08/2024 | M/S D. PALIT & CO. | 11.74 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | Assistant Engineer | Junior Engineer-3 | ORD/000303/2022-2023 | 836/PD | 19/05/2022 | 03/07/2022 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 30.37 | 69.64 | 100
22 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Balaance Work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area Zone-III, & Zone-IV of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | Assistant Engineer | Junior Engineer-1 | ORD/000738/2022-2023 | 1478/PD | 20/09/2022 | 04/11/2022 | SADHAN GORAIN | 21.29 | 19.32 | 90.76 | 100
23 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Repairing and Renovation of Pump house cum switch room including other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001128/2022-2023 | 377/PD | 15/03/2023 | 29/04/2023 | ROY CONSTRUCTION | 2.19 | 1.07 | 48.66 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Inter connection of 200 mm dia DI pipe with newly constructed CWR including Repairing and Renovation of Guard Room cum Store Room, Boundary wall with sanitary, plumbing & electrification work with other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001129/2022-2023 | 376/PD | 15/03/2023 | 29/04/2023 | ROY CONSTRUCTION | 6.54 | 3.55 | 54.31 | 100
25 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Quotation for new connection |  |  | BILL/00453/2023-2024 | BP-23-24-220 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : KASATORA (Part), MANBAZAR (Part) VILLAGE] | Assistant Engineer | Junior Engineer-3 | ORD/000302/2022-2023 | 835/PD | 19/05/2022 | 17/01/2023 | NANIGOPAL DEY | 43.62 | 18.63 | 42.7 | 90
27 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : MADHUPUR, BOLUDI & JHARBAGDA (Part) VILLAGE] | Assistant Engineer | Junior Engineer-3 | ORD/000793/2022-2023 | 1444/PD | 14/09/2022 | 29/10/2022 | MACHINO TECHNO | 122.46 | 54.97 | 44.89 | 65
28 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : MANBAZAR (Part), PATHARMOHORA VILLAGE] | Assistant Engineer | Junior Engineer-3 | ORD/000794/2022-2023 | 1445/PD | 14/09/2022 | 29/10/2022 | MACHINO TECHNO | 123.8 | 61.16 | 49.4 | 64
29 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supply, Delivery and installation 175kva voltage stabilizer for Augmentation of Manbazar w/s(Zone-1) scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000434/2022-2023 | 253/PMD | 06/03/2023 | 06/02/2025 | SANTU MITRA | 18.25 | 16.64 | 91.18 | 59
30 | PURULIA |  | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000428/2022-2023 | 246/PMD | 03/03/2023 | 29/04/2025 | NUPUR CHANDRA HALDER | 69.09 | 49.26 | 71.3 | 65
31 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Manbazar (Harekristapur) river site for Augmentation of Manbazar W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000023/2023-2024 | 542/PD | 12/04/2023 | 21/07/2023 | BASANTA PARAMANIK | 14.05 | 2.86 | 20.38 | 70
32 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-II) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000319/2022-2023 | 869/PD | 23/05/2022 | 31/01/2024 | ZAKIR HOSSIN MONDAL | 86.39 | 63.88 | 73.95 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | SM/10719 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-II) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000324/2022-2023 | 857/PD | 23/05/2022 | 01/10/2023 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 14.06 | 10.62 | 75.5 | 100
Total | [13 empty] | 1657.42 | 616.36 | 37.19