## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Damodar river site under Saltora-Hijli W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000334/2022-2023 | 865/PD | 23/05/2022 | 31/08/2022 | BALAJI UDDYOG | 13.87 | 12.42 | 89.52 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | New Sinking of 200 mm dia 8 (Eight) Nos river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) under Saltora-Hijli W/S Scheme under Raghunathpur Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2022-2023 | 855/PD | 23/05/2022 | 22/06/2022 | ASHOK KUMAR CHATTERJEE | 41.13 | 22.13 | 53.81 | 35
3 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Repairing & renovation of of CWR, Office Bldg., Pump Houses and Boundary Wall at Saltora -Hijli W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000336/2022-2023 | 867/PD | 23/05/2022 | 22/07/2022 | M/S ADITYA KUMAR | 6.94 | 2.97 | 42.77 | 50
4 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Distribution System with FHTC work (285 Nos.) of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | Assistant Engineer | Junior Engineer | ORD/000504/2022-2023 | 1009/PD | 29/06/2022 | 13/08/2022 | PARTHA PRATIM CHHATAIT | 110.11 | 56.34 | 51.17 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Distribution System with FHTC work and construction of Boundary wall at OHR Site of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | Assistant Engineer | Junior Engineer | ORD/000913/2022-2023 | 1891/PD | 15/12/2022 | 13/06/2026 | BALAJI UDDYOG | 204.07 | 83.16 | 40.75 | 35
6 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Laying of Clear Water Rising Main under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 856/PD | 23/05/2022 | 22/07/2022 | BASANTA KUMAR SINGHADEO | 51.02 | 12.58 | 24.65 | 25
7 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Additional work for Restoration work by construction of RCC Retaining wall for protection work of dedicated transformer at Saltore-Hijuli CWR site of Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Handed over to PRI Bodies ) | Assistant Engineer | Junior Engineer | ORD/001291/2022-2023 | 273/6/RNP | 19/05/2022 | 03/06/2022 | BASANTA KUMAR SINGHADEO | 0.88 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of Pump House (10 X 7 mtr) at Head Work site under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000333/2022-2023 | 864/PD | 23/05/2022 | 31/08/2022 | M/S SAYAK BHATTACHARYA | 15.23 | 15.13 | 99.3 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000404/2022-2023 | 343/RNP | 01/06/2022 | 01/07/2022 | G.TECH INDIA | 1.4 | 0.97 | 69.22 | 75
10 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 200 cum and staging height 20 mtr. with including supply of all labour & materials for Saltora -Hijli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000176/2022-2023 | 793/PD | 05/05/2022 | 30/01/2023 | ASHOK KUMAR CHATTERJEE | 64.5 | 53.5 | 82.94 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at River Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000367/2022-2023 | 330/RNP | 01/06/2022 | 30/08/2022 | SUBRATA SINGHADEO | 4.48 | 4.04 | 90.24 | 95
12 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Saltore-Hijuli OHR Campus under Saltore-Hijuli W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 40.00 mtr.) | Assistant Engineer |  | ORD/000368/2022-2023 | 332/RNP | 01/06/2022 | 22/06/2022 | AMIT PATHAK | 3.65 | 3.64 | 99.58 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Distribution System with FHTC work and construction of approach road at Pump House of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-III | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000929/2022-2023 | 1892/PD | 15/12/2022 | 28/04/2025 | PRAVAT SARKAR | 99.55 | 80.18 | 80.55 | 88
14 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at OHR Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000370/2022-2023 | 331/RNP | 01/06/2022 | 30/08/2022 | DEBANJAN SEAL | 4.46 | 4.44 | 99.58 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 958/PD | 20/06/2022 | 20/06/2022 | Resource Division | 158.64 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 979/PD | 22/06/2022 | 22/06/2022 | Resource Division | 118.82 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 973/2021-22 of EE/PD) |  |  | VCH/000969/2022-2023 | BP-2022-23-137 | 19/07/2022 | 19/07/2022 | M/S TECH VISION | 0.41 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 543/2021-22 of EE/PD) |  |  | VCH/000970/2022-2023 | BP-2022-23-138 | 19/07/2022 | 19/07/2022 | M/S TECH VISION | 4.08 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply, Delivery and installation of CWR Submersible pumping machineries, MCC Panels, flow meter with others allied works for Augmentation at SALTORE HIJULI ( ZONE-3) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000347/2022-2023 | 132/PMD | 20/02/2023 | 21/04/2023 | M/S D. PALIT & CO. | 27.01 | 11.92 | 44.13 | 35
20 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Saltore Hijuli Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000040/2023-2024 | 446/PMD | 20/04/2023 | 20/05/2023 | T.N.BANERJEE | 21.56 | 16.62 | 77.11 | 50
21 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works at SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000350/2022-2023 | 135/PMD | 20/02/2023 | 21/04/2023 | BISHWANATH NANDI | 7.64 | 7.63 | 99.85 | 0
22 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels, flow meter, HOT crane with others allied works for Augmentation at SALTORE HIJULI (ZONE-1 and 2) w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000349/2022-2023 | 134/PMD | 20/02/2023 | 21/04/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 70.46 | 68.82 | 97.68 | 100
23 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply, Delivery and installation of 8 nos. River bed submersible pumps motor sets with other allied works for SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000058/2023-2024 | 527/PMD | 05/05/2023 | 04/07/2023 | INDRAJIT MITRA | 23.5 | 21.09 | 89.76 | 8
24 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Additional work for Construction of Switch Room Cum Chlorin Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part - II) | Assistant Engineer | Junior Engineer | ORD/000530/2023-2024 | 397/RNP | 05/09/2023 | 20/09/2023 | DEBANJAN SEAL | 0.97 | 0.97 | 99.7 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Additional work for Construction of Switch Room Cum Chlorine Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part -I) | Assistant Engineer | Junior Engineer | ORD/000527/2023-2024 | 399/RNP | 05/09/2023 | 20/09/2023 | DEBANJAN SEAL | 0.94 | 0.94 | 99.88 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 426/PD | 21/03/2023 | 21/03/2023 | Resource Division | 37.42 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Quotation for removal of one 63 KVA DTR along with one span HT & one span LT line at the premises of Saltore Hijuli PHE |  |  | BILL/00435/2023-2024 | BP-23-24-222 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 0.09 | 0 | 0 | 0
28 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FOR AUGMENTATION OF SALTORE HIJULI WATER SUPPLY SCHEME |  |  | VCH/000425/2022-2023 | BP-22-23-85 | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 4.68 | 0 | 0 | 0
29 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply, delivery and Installation of Submersible pumping machineries for newly constructed tube wells and other allied works for Augmentation of Saltore hijuli W/S scheme under PMD Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000058/2024-2025 | 976/PMD | 20/06/2024 | 19/08/2024 | BISHWANATH NANDI | 8.76 | 7.34 | 83.77 | 70
30 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply, delivery and fitting fixing of Mainswitch and cable for Pumphouse and internal and external illumination of OHR site for Augmentation at Saltore Hijuli(Zone-1 & 2) w/s supply scheme under PMD,PHE Dte .in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000391/2023-2024 | 376/PMD | 04/03/2024 | 03/05/2024 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 10.49 | 5.36 | 51.09 | 100
31 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply and delivery of Free chlorine test kit at different Pumping water supply scheme under Purulia Mechanical Division, PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000321/2023-2024 | 46/PMSD(W/S) | 08/02/2024 | 23/02/2024 | M/S R.K. ENTERPRISE | 0.94 | 0.94 | 100 | 100
32 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System for zone-III & Miscellaneous works at Pump House under Saltore-Hijuli W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000642/2024-2025 | 1574/PMD | 14/11/2024 | 01/03/2025 | BISHWANATH NANDI | 4.42 | 0 | 0 | 100
33 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | Testing commissioning of Gaseous chlorination system and extension of solution line upto OLD CWR for Augmentation at Saltore Hijuli (Zone-1 & 2) under PMD, PHE Dte in the district of Purulia. (2ND Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000566/2024-2025 | 353/PMSD(W/S) | 04/09/2024 | 01/10/2025 | BISHWANATH NANDI | 0.81 | 0 | 0 | 100
34 | PURULIA |  | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme | SM/10721 | Augmentation | New service connection at Saltore Hijuli OHR site |  |  | BILL/00111/2024-2025 | BP-24-25-15 | 24/05/2024 | 24/05/2024 | WBSEDCL SALTORE CCC | 0.11 | 0 | 0 | 0
Total | [13 empty] | 1123.05 | 493.12 | 43.91