## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Nutandi (J.L. No.- 61) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000337/2022-2023 | 871/PD | 23/05/2022 | 07/07/2022 | AJAY MONDAL | 35.11 | 16.01 | 45.59 | 50
2 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-II) | Assistant Engineer |  | ORD/000313/2022-2023 | 846/PD | 23/05/2022 | 22/06/2022 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of Capacity 100 Cum with other allied works at Deolghata Pump House campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000317/2022-2023 | 850/PD | 23/05/2022 | 31/08/2022 | SK ABBAS | 10.71 | 9.64 | 90.01 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Barbenda (J.L. No.- 63) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000548/2022-2023 | 1039/A/PD | 07/07/2022 | 05/09/2022 | PREMNATH MITRA | 80.51 | 25.67 | 31.89 | 32
5 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Bhaddi (J.L. No.- 65) & Mouza- Litiadih (J.L. No.-99) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000527/2022-2023 | 1040/PD | 06/07/2022 | 05/08/2022 | AMAL KUMAR MUKHERJEE | 13.51 | 3.41 | 25.27 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/001148/2022-2023 | 423/PD | 21/03/2023 | 05/05/2023 | BOSE CONSTRUCTION | 43.97 | 4.81 | 10.95 | 60
7 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Withdrawing of 150 mm dia. DI Pipe (distribution main) & newly laying in new trench and through culvert under Railway track near Ranibandh Rail Crossing of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/001222/2022-2023 | 247/PSD | 31/03/2023 | 10/04/2023 | APEX TRADERS | 0.71 | 0.68 | 96.86 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-I) | Assistant Engineer |  | ORD/000311/2022-2023 | 845/PD | 23/05/2022 | 22/06/2022 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 1000 M3 capacity Over Head Reservoir of Joypur W/S Scheme under Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/001003/2022-2023 | 112/A/PD | 20/01/2023 | 19/02/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.86 | 66.67 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 300mt. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000083/2023-2024 | 816/PD | 26/06/2023 | 10/08/2023 | SADHAN GORAIN | 5.01 | 4.53 | 90.39 | 95
11 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply & delivery DI Specials for Newly Laying of Distribution Main (DI-K7) Pipe line from OHR Site to Joypur Ranibandh Rail Crossing & Towards Raghbore More under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000085/2023-2024 | 817/PD | 26/06/2023 | 10/08/2023 | PRIYATOSH MUKHERJEE | 4.11 | 4.02 | 97.78 | 98
12 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 250mtr. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000658/2023-2024 | 1352/PD | 13/09/2023 | 28/10/2023 | SADHAN GORAIN | 4.18 | 3.34 | 79.97 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 970/PD | 21/06/2022 | 21/06/2022 | Resource Division | 372.24 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 613/PMD | 01/06/2023 | 01/06/2023 | Resource Division | 1.55 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Joypur W/S Scheme, Block- Joypur) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 535/2021-22 of EE/PD) |  |  | VCH/000915/2022-2023 | BP-2022-23-119 | 16/07/2022 | 16/07/2022 | RADIANT | 8.59 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00092/2022-2023 | BP-2022-23-5179 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 45.74 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00089/2022-2023 | BP-2022-23-5176 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.34 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00088/2022-2023 | BP-2022-23-5175 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.27 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000312/2022-2023 | 842/PD | 23/05/2022 | 07/07/2022 | PRIYATOSH MUKHERJEE | 71.27 | 48.07 | 67.45 | 70
20 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Joypur OHR for Augmentation of Joypur Water supply scheme block Joypur under PMD PHE Dte. district Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000381/2022-2023 | 212/PMD | 28/02/2023 | 30/03/2023 | ANUP KR. SAHA | 21.6 | 20.03 | 92.71 | 93
21 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Arrangement of internal lighting with other allied works for augmentation of Joypur (River side & OHR side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000424/2022-2023 | 242/PMD | 03/03/2023 | 02/05/2023 | MD. ASLAM | 1.21 | 0.85 | 70.16 | 60
22 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Over Head Reservoir (OHR) of 1000 Cum Capacity, Staging Height 20 mtr. at existing OHR Campus (Rahardaga Mouza ) of Joypur W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001027/2022-2023 | 148/PD | 03/02/2023 | 31/10/2023 | SADHAN GORAIN | 229.29 | 176.17 | 76.83 | 92
23 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/001150/2022-2023 | 424/PD | 21/03/2023 | 05/05/2023 | BOSE CONSTRUCTION | 88.75 | 19.71 | 22.21 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river near Deulghata of Joypur W/S scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000872/2023-2024 | 1522/PD | 16/10/2023 | 15/12/2023 | ANUP KUMAR SAHA | 43.6 | 0 | 0 | 0
25 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Yard lighting arrangement with others allied work at Joypur water Supply Scheme (River Site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000203/2023-2024 | 1193/PMD | 03/11/2023 | 02/01/2024 | S. PATHAK & CO. | 10.83 | 6.09 | 56.24 | 56
26 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extension of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001864/2023-2024 | 90/PD | 15/01/2024 | 15/03/2024 | PRIYATOSH MUKHERJEE | 61.3 | 31.85 | 51.96 | 75
27 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER |  | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 10/05/2024 | ASHOKE ADHIKARY | 8.07 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Staff Toilet at Riversite Pump house under Joypur PWSS Scheme under Purulia Division, PHE Dte. |  |  | ORD/000156/2024-2025 | 886/PD | 07/05/2024 | 06/07/2024 | PURNA CHANDRA TEWARI | 4.1 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room at Joypur OHR site of Joypur W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000314/2022-2023 | 847/PD | 23/05/2022 | 21/08/2022 | KM ENTERPRISES | 16.44 | 16.37 | 99.56 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Repairing, renovation & restoration of Pump house & store cum Guard room at Deolghata Pump house campus of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000316/2022-2023 | 848/PD | 23/05/2022 | 22/07/2022 | SEKH IRFAN | 5.38 | 4.11 | 76.43 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (Jl-105) & Mouza-Ghaghri (Jl-106) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000315/2022-2023 | 843/PD | 23/05/2022 | 07/07/2022 | MOONLIGHT HOUSE | 14.06 | 13.37 | 95.12 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Tunta (Jl-104) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000850/2022-2023 | 1754/PD | 22/11/2022 | 06/01/2023 | M/S KHAN ENTERPRISE | 23.24 | 18.58 | 79.95 | 100
33 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Repairing, renovation of Boundary Wall at Joypur OHR site of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000899/2022-2023 | 1838/PD | 12/12/2022 | 11/01/2023 | TRINITY CONSTRUCTION | 18.79 | 18.75 | 99.79 | 100
34 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 350 cubic meter capacity Over Head Reservoir of Bandwan W/S Scheme under Purulia Division P.H.E Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001028/2022-2023 | 231/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0.8 | 28.79 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 200 cubic meter capacity Over Head Reservour of Darda W/S Scheme under Purulia Division P.H.E dte. | Assistant Engineer | Junior Engineer-3 | ORD/001029/2022-2023 | 232/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0.94 | 33.54 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 600 cubic meter capacity Over Head Reservour of ManbazaR -I W/S Scheme under Purulia Division P.H.E dte. | Assistant Engineer | Junior Engineer-3 | ORD/001030/2022-2023 | 233/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0.91 | 32.64 | 100
37 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 100 cubic meter capacity Over Head Reservour of Arsha W/S Scheme under Purulia Division P.H.E dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/001033/2022-2023 | 236/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.04 | 37.29 | 100
38 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001047/2022-2023 | 279/PD | 27/02/2023 | 29/03/2023 | S. R. ENTERPRISE | 10.39 | 0 | 0 | 60
39 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 250 cubic meter capacity Over Head Reservour of Puncha W/S Scheme under Purulia Division P.H.E dte. | Assistant Engineer | Junior Engineer-3 | ORD/001031/2022-2023 | 234/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 1.26 | 45.28 | 100
40 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Emergent Dismantling of R.C.C. Elevated Reservoir, Capcaity 350 Cum (Intze Type), Staging height 20 metre at Joypur OHR Site of Joypur W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000024/2023-2024 | 553/PD | 13/04/2023 | 12/07/2023 | TAPAN CHANDRA | 10.38 | 10.35 | 99.79 | 100
41 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain, Land development etc. complete at Joypur OHR Site, of Joypur W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000043/2023-2024 | 659/PD | 17/05/2023 | 25/08/2023 | KM ENTERPRISES | 10.91 | 10.85 | 99.47 | 100
42 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Undercut Pump house including panel room & chlorination room at Deulghata Pump House of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001496/2023-2024 | 1796/PD | 08/12/2023 | 07/03/2024 | M/S CONTRACTORS SYNDICATE | 23.01 | 12.64 | 54.92 | 100
43 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 750 cubic meter capacity Over Head Reservour of Kotshila W/S Scheme under Purulia Division P.H.E dte. | Assistant Engineer | Junior Engineer-3 | ORD/001032/2022-2023 | 235/PD | 17/02/2023 | 19/03/2023 | M.K.KAYAL & ASSOCIATES | 2.79 | 0.98 | 35.23 | 100
44 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Laying DI Rising Main in new alignment from Pump house to OHR and making Inter Connection Arrangement with Distribution System for Joypur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000228/2024-2025 | 1062/PD | 07/06/2024 | 06/08/2024 | BHAGABAN DAS KUMAR | 2.55 | 2.54 | 99.61 | 100
45 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Joypur Block to supply drinking water of command area of Joypur Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 1394/PD | 01/09/2022 | 16/10/2022 | AMAL KUMAR MUKHERJEE | 6.32 | 6.03 | 95.47 | 100
46 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Laying of Pipeline from Banahata Mouza to Kachahatu Mouza for Providing FHTC at Joypur Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/003983/2023-2024 | 529/PD | 16/03/2024 | 15/05/2024 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 84.88 | 22.46 | 26.46 | 100
47 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and) at Gurrabera habitation of Mouza-Ritudih (JL-62) under command area of Joypur Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000123/2024-2025 | 890/PD | 07/05/2024 | 21/06/2024 | BHAGABAN DAS KUMAR | 3.24 | 3.24 | 99.99 | 100
48 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of Staff Toilet at Sirkabad OHR Site under Joypur PWSS Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000155/2024-2025 | 885/PD | 07/05/2024 | 01/10/2024 | INDRAJIT SARKAR | 4.09 | 0 | 0 | 100
49 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Left Out & Parallal distribution pipe line including Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (JL-105) & Mouza- Ghaghri (JL-106) under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000219/2024-2025 | 1093/PD | 07/06/2024 | 06/08/2024 | MOONLIGHT HOUSE | 4.13 | 3.68 | 88.94 | 100
50 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | New sinking of 2(Two ) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000440/2024-2025 | 1503/PD | 27/08/2024 | 26/09/2024 | BOSE CONSTRUCTION | 18.14 | 9.67 | 53.3 | 100
51 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | New Connection for Augmentation of Joypur (River Side) W/S Scheme |  |  | BILL/00245/2023-2024 | BP-2023-24-150 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
52 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | New Connection For Augmentation of Joypur |  |  | BILL/00246/2023-2024 | BP-2023-24-149 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 4.45 | 0 | 0 | 0
53 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000409/2022-2023 | 936/PD | 16/06/2022 | 01/01/2025 | M/S. S. CHOUDHURY | 201.33 | 74.27 | 36.89 | 100
54 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Joypur(Riverside) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000426/2022-2023 | 244/PMD | 03/03/2023 | 01/05/2025 | COMBINE ENTERPRISES | 58.94 | 38.28 | 64.96 | 35
55 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing (Left Out) Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Bhaddi (J.L. No.- 65) & Mouza- Litiadih (J.L. No.-99) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001107/2022-2023 | 378/PD | 16/03/2023 | 01/01/2026 | AMAL KUMAR MUKHERJEE | 8.93 | 0 | 0 | 50
56 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Joypur(riverside) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000425/2022-2023 | 243/PMD | 03/03/2023 | 04/03/2024 | ANUP KR. SAHA | 70.91 | 47.39 | 66.84 | 66
57 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Joypur (OHR side) water supply scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000031/2023-2024 | 421/PMD | 13/04/2023 | 12/06/2023 | MERCURY ENGINEERING COMPANY | 36.21 | 24.69 | 68.18 | 30
58 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Joypur(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000120/2023-2024 | 801/PMD | 12/07/2023 | 06/05/2025 | M/S P.P.ELECTRICALS | 15.63 | 0 | 0 | 96
59 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Left Out & Parallal distribution pipe line including Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Tunta (JL-104) under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000207/2024-2025 | 1067/PD | 07/06/2024 | 22/07/2024 | M/S KHAN ENTERPRISE | 12.2 | 0 | 0 | 0
60 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Laying of Collecting line from Riverbed Manifold to Pump house and Laying of Distribution pipeline from Existing OHR to Main Road and other allied works complete under Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. (Under Joypur W/S Scheme) | Assistant Engineer | Junior Engineer-3 | ORD/003948/2023-2024 | 293/PD | 28/02/2024 | 26/06/2025 | ASHOKE ADHIKARY | 12.9 | 0 | 0 | 80
61 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extention of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/004250/2023-2024 | 491/PD | 16/03/2024 | 11/03/2025 | UMA CONSTRUCTION | 74.86 | 0 | 0 | 100
62 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000339/2022-2023 | 873/PD | 23/05/2022 | 01/01/2025 | M/S. S. CHOUDHURY | 72.66 | 38.29 | 52.69 | 55
63 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Shyampur (Jl-101) & Mouza-Dhabani (Jl-103) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000309/2022-2023 | 841/PD | 23/05/2022 | 26/10/2024 | SUNNY ELECTRIC CO | 56.74 | 51.99 | 91.63 | 100
64 | PURULIA |  | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of Capacity 200 Cum with other allied work at OHR campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000870/2022-2023 | 1837/PD | 12/12/2022 | 08/12/2023 | KM ENTERPRISES | 33.08 | 26.17 | 79.13 | 100
65 | PURULIA |  | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | SM/10722 | Augmentation | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Joypur(OHR Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000427/2022-2023 | 245/PMD | 03/03/2023 | 02/05/2023 | ANUP KR. SAHA | 10.76 | 10.51 | 97.67 | 96
Total | [13 empty] | 2156.4 | 846.92 | 39.27