## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 971/2021-22 of EE/PD) |  |  | VCH/000971/2022-2023 | BP-2022-23-139 | 19/07/2022 | 19/07/2022 | HORIZEN | 1.99 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) (Tender No.506/2022-23 of EE/PD) |  |  | VCH/001021/2022-2023 | BP-2022-23-312 | 26/09/2022 | 26/09/2022 | NANIGOPAL DEY | 8.78 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | New Sinking of 02 (Two) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line other allied works of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 126/2022-23 of EE/PD) |  |  | VCH/000960/2022-2023 | BP-2022-23-128 | 19/07/2022 | 19/07/2022 | KOUSHIK CHATTERJEE | 5.39 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) (Tender No- 282/2022-23 of EE/PD) |  |  | VCH/001032/2022-2023 | BP-2022-23-377 | 19/10/2022 | 19/10/2022 | ANUP KUMAR SAHA | 32.08 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) (Tender No- 281/2022-23 of EE/PD) |  |  | VCH/001041/2022-2023 | BP-2022-23-376 | 19/10/2022 | 19/10/2022 | ANUP KUMAR SAHA | 50.47 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | New Sinking of 03 (Three) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with construction of 01 nos common manifold chamber at kotshila river site of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 124/2022-23 of EE/PD) |  |  | VCH/000961/2022-2023 | BP-2022-23-129 | 19/07/2022 | 19/07/2022 | BOSE CONSTRUCTION | 8.56 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 544/2021-22 of EE/PD) |  |  | VCH/000972/2022-2023 | BP-2022-23-140 | 19/07/2022 | 19/07/2022 | HORIZEN | 7.98 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chayadih) | Assistant Engineer |  | ORD/000338/2022-2023 | 872/PD | 23/05/2022 | 22/07/2022 | APURBA PATRA | 46.84 | 29.95 | 63.93 | 70
9 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of 250 mm and 150 mm dia DI (K9) pipe as rising main from riverside pump house site to OHR site under Kotshila Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000318/2022-2023 | 849/PD | 23/05/2022 | 22/07/2022 | GLOBAL CONSTRUCTION | 75.85 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Kachahatu) Zone-II | Assistant Engineer |  | ORD/000549/2022-2023 | 1079/PD | 12/07/2022 | 26/08/2022 | PRAVAT SARKAR | 111.73 | 63.2 | 56.57 | 65
11 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Panroma) Zone-ii | Assistant Engineer | Junior Engineer-3 | ORD/000539/2022-2023 | 1054/PD | 08/07/2022 | 22/08/2022 | M/S. MSS RISING ENTERPRISE | 36.04 | 23.35 | 64.81 | 65
12 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Jiudaru) | Assistant Engineer | Junior Engineer-3 | ORD/000532/2022-2023 | 1043/A/PD | 07/07/2022 | 05/09/2022 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 64.02 | 24.07 | 37.6 | 35
13 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hetbatari) | Assistant Engineer |  | ORD/000601/2022-2023 | 1226/PD | 22/08/2022 | 21/09/2022 | SARKAR ENTERPRISE | 15.98 | 2.79 | 17.47 | 25
14 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Nowahatu) | Assistant Engineer |  | ORD/000531/2022-2023 | 1056/PD | 08/07/2022 | 22/08/2022 | MOLLA ENTERPRISE | 23.78 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Ghatketia) | Assistant Engineer | Junior Engineer-3 | ORD/000530/2022-2023 | 1057/PD | 08/07/2022 | 07/08/2022 | ROY CONSTRUCTION | 9.1 | 3.24 | 35.63 | 0
16 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of Transformer base for Installing Transformer and Cable Trench for HT & LT Line at Kotshila Pump House Campus under Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE DTE . | Assistant Engineer |  | ORD/000856/2022-2023 | 1807/PD | 06/12/2022 | 20/01/2023 | SAIBAL SARKAR | 15.18 | 5.65 | 37.24 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supply, delivery and installation 12kg/cm2 chlorine machine with others works for Augmentation of Kotshila w/s scheme under Purulia Mechanical Division, PHE, Dte. in purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000296/2022-2023 | 77/PMD | 01/02/2023 | 03/03/2023 | R K ENTERPRISES | 3.6 | 2.6 | 72.2 | 91
18 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division underPurulia Division, PHE Dte (Goaladih Mouza) | Assistant Engineer |  | ORD/001012/2022-2023 | 179/PD | 07/02/2023 | 09/03/2023 | SB CONSTRUCTION | 6.47 | 5.3 | 81.95 | 90
19 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with Construction of 1 nos Common Manifold Chamber at Kotshila river site of Kotshila W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000331/2022-2023 | 862/PD | 23/05/2022 | 22/06/2022 | BOSE CONSTRUCTION | 23.05 | 6.48 | 28.13 | 100
20 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Kotshila W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000330/2022-2023 | 861/PD | 23/05/2022 | 22/06/2022 | KOUSHIK CHATTERJEE | 11.39 | 2.8 | 24.57 | 100
21 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of 300mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001063/2022-2023 | 294/PD | 27/02/2023 | 13/04/2023 | KM ENTERPRISES | 52.23 | 40.78 | 78.08 | 100
22 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of 280mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001061/2022-2023 | 293/PD | 27/02/2023 | 13/04/2023 | GOUTAM CHAKRABORTY | 81.35 | 63.02 | 77.46 | 100
23 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Pipeline from Kachahatu Riversite Pump House to Banahata Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001010/2022-2023 | 177/PD | 07/02/2023 | 24/03/2023 | SUBODH PRAMANIK | 88.16 | 85.31 | 96.77 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Collecting line from Kanshabati Riverbed to Manifold Chamber for implementaion of JJM project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001092/2022-2023 | 359/PD | 14/03/2023 | 13/04/2023 | BOSE CONSTRUCTION | 7.65 | 7.16 | 93.57 | 100
25 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Collecting line from Kanshabati Riverbed to Kachahatu Pump house for implementation of JJM Project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001090/2022-2023 | 358/PD | 14/03/2023 | 13/04/2023 | KOUSHIK CHATTERJEE | 3.1 | 0.46 | 14.94 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 969/PD | 21/06/2022 | 21/06/2022 | Resource Division | 369.8 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 968/PD | 21/06/2022 | 21/06/2022 | Resource Division | 177.02 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Car bill paid for office purpose for the month of Jan & Feb,23 against Vehicle Reg. No. WB/55A/7171. |  |  | VCH/001819/2022-2023 |  | 30/11/2022 | 30/11/2022 | NIRUPAMA DEY | 0.63 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00085/2022-2023 | BP-2022-23-5172 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 37.72 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Indian Railways Miscellaneous collection. |  |  | BILL/00086/2022-2023 | BP-2022-23-5173 | 02/01/2023 | 02/01/2023 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 8.79 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Bill paid for Way leave Facility Charge of Rail Bhumi Crossing Seva (IR-RBCS) under South Eastern Railway, Ranchi Divison against Application ID:SER-RNC-2022-WL-8, 9, 10 dt.22/11/2022. |  |  | BILL/00009/2022-2023 | BP-2022-23-459 | 05/12/2022 | 05/12/2022 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 33.83 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Restoration of only Hard Shoulder of Purulia Ranchi Road under PWD Purulia Division from Rakbore more to Adardih Bridge after laying of Drinking water pipeline of Kotshila W/S Scheme under Jal-Jeban Mission of PHE Dte, Purulia in the District of Purulia during the year 2022-2023. |  |  | BILL/00182/2023-2024 | BP-2023-24-209 | 08/06/2023 | 08/06/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 23.61 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Car bill for office purpose against vehicle reg. no.WB-55A/7171 & paid for the month of Jan,23 & Feb,23. |  |  | VCH/001904/2022-2023 | BP-2023-24-58 | 04/05/2023 | 04/05/2023 | NIRUPAMA DEY | 0.63 | 0 | 0 | 0
34 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | DEPOSITION OF THE EARNEST MONEY FOR THE PORPOSED ENHANCEMENT OF THE LOAD AT KOTHSILA WATER SUPPLY SCHEME |  |  | VCH/000326/2022-2023 | 780/PMD | 23/11/2022 | 23/11/2022 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
35 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. |  |  | BILL/00539/2023-2024 | BP-2023-24-334 | 02/08/2023 | 02/08/2023 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
36 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 125 KVA AT 0.4 KV TO 281/281/281/281/281 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o EX ENGG PMD PHE DTE. (CONSUMER ID : 942406300) TO THEIR PREMISES AT KOTSHILA WATER SUPPLY SCHEME (AUGMENTATION) |  |  | BILL/00044/2022-2023 |  | 28/02/2023 | 28/02/2023 | WBSEDCL PURULIA | 10.37 | 0 | 0 | 0
37 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 150 Cum with other allied works at Kotshila pumphouse under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000329/2022-2023 | 860/PD | 23/05/2022 | 21/08/2022 | BOSE CONSTRUCTION | 17.45 | 0 | 0 | 65
38 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chaitandih) | Assistant Engineer | Junior Engineer-3 | ORD/000340/2022-2023 | 874/PD | 23/05/2022 | 22/06/2022 | PRATIK SAHA | 23.33 | 16.44 | 70.48 | 75
39 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chiruhatu) | Assistant Engineer | Junior Engineer-3 | ORD/000342/2022-2023 | 876/PD | 23/05/2022 | 07/07/2022 | GOUTAM CHAKRABORTY | 46.54 | 28.11 | 60.41 | 85
40 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) | Assistant Engineer | Junior Engineer-3 | ORD/000522/2022-2023 | 1041/PD | 07/07/2022 | 03/03/2025 | ANUP KUMAR SAHA | 82.11 | 10.56 | 12.86 | 85
41 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Timangda) | Assistant Engineer | Junior Engineer-3 | ORD/000523/2022-2023 | 1039/PD | 07/07/2022 | 21/08/2022 | MANATOSH SINGH | 44.34 | 33.64 | 75.87 | 80
42 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) | Assistant Engineer | Junior Engineer-3 | ORD/000526/2022-2023 | 1044/PD | 07/07/2022 | 03/03/2025 | ANUP KUMAR SAHA | 74.83 | 7.67 | 10.25 | 85
43 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Uparbatri) | Assistant Engineer | Junior Engineer-3 | ORD/000407/2022-2023 | 938/PD | 16/06/2022 | 30/06/2025 | SWAPAN MANDAL | 116.02 | 84.7 | 73.01 | 80
44 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KOTSHILA w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000253/2022-2023 | 43/PMD | 19/01/2023 | 20/03/2023 | TAPAN KUMAR DEY | 78.43 | 42.69 | 54.44 | 65
45 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supply, delivery and installation of 400KVA 11/.433 KV substation with 11 KV 800A VCB Panel with others allied works for Augmentation of Kotshila w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000269/2022-2023 | 42/PMD | 19/01/2023 | 20/03/2023 | CHAKRABORTY ENTERPRISE | 48.1 | 6.12 | 12.73 | 60
46 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supply delivery and installation submersible pumping machineries & 3 core 10 Sq. mm Al Ar. cable line , with others allied works for Augmentation of Kotshila W/S scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000490/2022-2023 | 154/PMD | 24/02/2023 | 25/04/2023 | M/S S.G.ENTERPRISE | 31.8 | 22.72 | 71.45 | 75
47 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Banahatu) Zone-ii | Assistant Engineer | Junior Engineer-3 | ORD/000538/2022-2023 | 1055/PD | 08/07/2022 | 31/03/2026 | SUBODH PRAMANIK | 58.54 | 53.17 | 90.82 | 90
48 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Murulahar ) | Assistant Engineer | Junior Engineer-3 | ORD/000525/2022-2023 | 1043/PD | 07/07/2022 | 05/09/2022 | PARTHA PRATIM CHHATAIT | 91.56 | 44.61 | 48.73 | 70
49 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Tiraldih or Goaladih) | Assistant Engineer | Junior Engineer-3 | ORD/000528/2022-2023 | 1058/PD | 08/07/2022 | 06/09/2022 | SOUMITRA CHAKRABORTY | 56.18 | 49.32 | 87.78 | 100
50 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) | Assistant Engineer | Junior Engineer-3 | ORD/000529/2022-2023 | 1059/PD | 08/07/2022 | 06/09/2022 | NANIGOPAL DEY | 33.35 | 17.48 | 52.4 | 90
51 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hanslata) Zone-ii | Assistant Engineer | Junior Engineer-3 | ORD/000540/2022-2023 | 1053/PD | 08/07/2022 | 22/08/2022 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 21.95 | 21.89 | 99.75 | 100
52 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of Over Head Reservoir (OHR) of 750 Cum Capacity, Staging Height 20 mtr. at BDO office Campus at Kotshila under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000912/2022-2023 | 1887/PD | 15/12/2022 | 11/09/2023 | ANUP KUMAR SAHA | 161.06 | 97.61 | 60.6 | 100
53 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chitarpur Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001014/2022-2023 | 181/PD | 07/02/2023 | 09/03/2023 | NANIGOPAL DEY | 2.71 | 1.87 | 69.02 | 90
54 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of Boundary wall at Kachahatu Pump House Site under Kotshila W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000997/2022-2023 | 110/PD | 20/01/2023 | 19/02/2023 | KANAILAL PAL | 14.97 | 14.91 | 99.59 | 100
55 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Parallel Distribution Pipeline at Banahatu Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001060/2022-2023 | 292/PD | 27/02/2023 | 13/04/2023 | M/S SAWDESH ENTERPRISE | 28.73 | 27.57 | 95.95 | 100
56 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001047/2022-2023 | 279/PD | 27/02/2023 | 29/03/2023 | S. R. ENTERPRISE | 10.39 | 7.98 | 76.74 | 60
57 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Kotshila OHR Site for Augmentation of Kotshila W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001089/2022-2023 | 369/PD | 14/03/2023 | 22/06/2023 | SABYASACHI MISHRA | 8.18 | 8.15 | 99.63 | 70
58 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Main Line & Parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jiudaru Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001085/2022-2023 | 345/pd | 13/03/2023 | 11/06/2023 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 79.96 | 79.78 | 99.78 | 100
59 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | 13 Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chiruhatu Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/001094/2022-2023 | 361/PD | 14/03/2023 | 28/04/2023 | M/S CHAKRABORTY CONSTRUCTION | 9.62 | 7.17 | 74.54 | 100
60 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Pipeline from Jiudaru Mouza to Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000068/2023-2024 | 699/PD | 22/05/2023 | 20/08/2023 | RAJAT KARMAKAR | 30.33 | 29.07 | 95.84 | 10
61 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Adardih Mouza) | Assistant Engineer | Junior Engineer-3 | ORD/000087/2023-2024 | 818/PD | 26/06/2023 | 10/08/2023 | SUSANTA KR DUTTA | 10.03 | 8.14 | 81.12 | 100
62 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Pipeline from Kachahatu Mouza to Jiudaru Mouza & Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000069/2023-2024 | 700/PD | 22/05/2023 | 20/08/2023 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 84.69 | 84.37 | 99.62 | 100
63 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supply and delivery of essential Electromechanical items for Augmentation of Kotshila w/s Scheme in PMD store under Purulia Mechanical Division PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000188/2023-2024 | 1178/PMD | 03/11/2023 | 02/01/2024 | SAIBAL SARKAR | 5.15 | 5.15 | 100 | 100
64 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Bill for earnest money for the proposed Enhancement of the load at your premises at Kotshila W/S Scheme. |  |  | BILL/00434/2023-2024 | BP-23-24-219 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
65 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Enhancement of the contract demand from 125KVA at 0.4 KV to 281/281//281//281//281 KVA respectively at 11 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kotshila Water Supply, (Consumer ID -942406300) |  |  | BILL/00860/2023-2024 | BP-24-25-1 | 19/04/2024 | 19/04/2024 | WBSEDCL PURULIA | 10.24 | 0 | 0 | 0
66 | PURULIA |  | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER ROOM AT KOTHSILA WS SCHEME |  |  | BILL/00508/2023-2024 | BP-23-24-269 | 22/01/2024 | 22/01/2024 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
67 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Office stationary bill supply & bill paid for the Bill No.765,770,785,848,850,839,840,841,842,849,845,847,837,838 & 836. |  |  | BILL/01797/2023-2024 | BP-2024-25-261 | 24/07/2024 | 24/07/2024 | KETIKA CONSUMERS CO-OP STORES LTD | 4.31 | 0 | 0 | 0
68 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Adardih) | Assistant Engineer | Junior Engineer-3 | ORD/000341/2022-2023 | 875/PD | 23/05/2022 | 17/02/2025 | SUSANTA KR DUTTA | 40.45 | 23.36 | 57.76 | 90
69 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Shyampur) | Assistant Engineer | Junior Engineer-3 | ORD/000524/2022-2023 | 1042/PD | 07/07/2022 | 06/02/2025 | S. R. ENTERPRISE | 64.93 | 53.7 | 82.7 | 92
70 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Repairing of DI Rising main (K-9) including laying of Parallel line at Jiudaru Mouza under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/000166/2023-2024 | 937/PD | 19/07/2023 | 18/08/2023 | ANUP KUMAR SAHA | 95.31 | 87.13 | 91.43 | 80
71 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Withdrawing & Relaying of DI(K-9) rising main pipeline including cleaning of chokage & laying of parallel pipeline at Kotshila water supply scheme under Purulia Division ,PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000168/2023-2024 | 939/PD | 19/07/2023 | 18/08/2023 | ANUP KUMAR SAHA | 87.21 | 62.91 | 72.14 | 70
72 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room from Kotshila Pump House to distribution area through distribution main of Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000327/2022-2023 | 859/PD | 23/05/2022 | 31/08/2022 | CHOUDHURY STONE CRUSHING | 16.65 | 0 | 0 | 50
73 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Repairing of DI Pipeline Rising main (K-9) including laying of Parallel line at Barudi Mouza for Providing FHTC under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/000167/2023-2024 | 938/PD | 19/07/2023 | 18/08/2023 | ANUP KUMAR SAHA | 78.98 | 0 | 0 | 100
74 | PURULIA |  | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | SM/10723 | Augmentation | Laying of Parallel line at Jiudaru Mouza and Branch Line and Gap portion of Hanslata Mouza under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/000101/2023-2024 | 868/PD | 30/06/2023 | 30/07/2023 | RAJAT KARMAKAR | 11.46 | 8.99 | 78.46 | 100
Total | [13 empty] | 3135.76 | 1413.18 | 45.07