## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Preparation of DPR (Consultancy Work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathol W/s Scheme, Block Kashipur) to be Augmented/Retrofitting. (Tender No.835/EE/PD of 2021-22) |  |  | VCH/000330/2022-2023 | BP-2022-23-232 | 05/09/2022 | 05/09/2022 | STEELCONC AND ASSOCIATES | 2.32 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.68/SE/PMU of 2022-23) |  |  | VCH/001053/2022-2023 | BP-2022-23-397 | 20/10/2022 | 20/10/2022 | MADHU SUDAN RAKSHIT | 44.2 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Keliathole-Palashkola W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 338/RNP | 01/06/2022 | 16/07/2022 | CHANCHAL MISHRA | 4.23 | 3.93 | 93.02 | 0
4 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply & installation of submersible pumping machinery at River Bed Tubewell at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000448/2022-2023 | 267/PMD | 06/03/2023 | 05/05/2023 | SAIBAL SARKAR | 47.89 | 39.49 | 82.47 | 50
5 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Providing Functional Household Tap Connection (FHTC) and other allied works of Keliathole Palashkola Water Supply Scheme(Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 142/RNP | 06/04/2023 | 13/04/2023 | AMIT PATHAK | 0.93 | 0.93 | 99.69 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Continuation work order for the work of Guarding arrangement through Registered firm organized by Ex-Military person for Guarding of all Govt. properties laying at Keliyathol Elevated Reservoir site under Palaskola-Kelyathol W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (w.e.f. 01.09.2022 to 30.10.2022) | Assistant Engineer |  | ORD/001221/2022-2023 | 1360/PD | 31/08/2022 | 30/10/2022 | MANBHUM SECURITY SERVICE | 1.46 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathole W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000439/2020-2021 | 357/D/PD | 25/02/2021 | 27/03/2021 | STEELCONC AND ASSOCIATES | 7.72 | 7.72 | 100 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Keliathole -Palashkola Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000390/2022-2023 | 348/RNP | 01/06/2022 | 21/06/2022 | SUBHAS CHANDRA MAHATO | 1.48 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/II) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | Assistant Engineer |  | ORD/000384/2022-2023 | 336/RNP | 01/06/2022 | 16/07/2022 | AMIT PATHAK | 4.55 | 4.53 | 99.7 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/I) (Mouza- Keliathole, Hab- Keliathole) | Assistant Engineer |  | ORD/000381/2022-2023 | 333/RNP | 01/06/2022 | 16/07/2022 | NANIGOPAL DEY | 4.58 | 4.57 | 99.79 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/II) (Mouza- Keliathole, Hab.- Keliathole) | Assistant Engineer |  | ORD/000382/2022-2023 | 334/RNP | 01/06/2022 | 16/07/2022 | NANIGOPAL DEY | 4.46 | 4.29 | 96.26 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/I) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | Assistant Engineer |  | ORD/000383/2022-2023 | 335/RNP | 01/06/2022 | 16/07/2022 | SUBHAS CHANDRA MAHATO | 4.55 | 4.52 | 99.45 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | Assistant Engineer |  | ORD/000547/2022-2023 | 465/RNP | 14/07/2022 | 13/08/2022 | M.K.KAYAL & ASSOCIATES | 2.79 | 2.79 | 100 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Repairing and Renovation of Elevated Reservoir at Keliathole Zone and Palashkola Zone including Head work site and other allied works under Keliathole Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000916/2022-2023 | 1925/PD | 22/12/2022 | 22/03/2023 | SUBHAS CHANDRA MAHATO | 13.16 | 12.07 | 91.66 | 100
15 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Palashkhola Keliyathol Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000385/2022-2023 | 216/PMD | 28/02/2023 | 30/03/2023 | COMBINE ENTERPRISES | 21.61 | 21.61 | 100 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 314/PD | 03/03/2023 | 03/03/2023 | Resource Division | 528.8 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Enhancement of contractual demand from 90 KVA at 0.4 KV to their premises at PALASHKHOLA WATER SUPPLY, Dist- Purulia under Regional Office Purulia. |  |  | BILL/00113/2023-2024 |  | 20/07/2023 | 20/07/2023 | WBSEDCL PURULIA | 6.55 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Keliathole-Palashkola W/S Scheme on Hura Kashipur Adra Raghunathpur Road (From Ch.22.163 Km to Ch.22.825 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. |  |  | BILL/00454/2023-2024 | BP-2023-24-313 | 26/07/2023 | 26/07/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 41.92 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-L) | Assistant Engineer | Junior Engineer-1 | ORD/000752/2022-2023 | 1421/PD | 08/09/2022 | 23/10/2022 | M/S NANDY ENTERPRISE | 108.08 | 78.66 | 72.78 | 90
20 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of RCC elevated reservoir of capacity 150 cum under Keliathole Palaskola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000633/2022-2023 | 1401/PD | 01/09/2022 | 29/05/2023 | SANTANU BANERJEE | 67.83 | 65.38 | 96.38 | 90
21 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of RCC elevated reservoir of capacity 250 cum under Keliathole Palaskola W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000634/2022-2023 | 1402/PD | 01/09/2022 | 29/05/2023 | RABIN CHANDRA CHAIL | 78.62 | 72.63 | 92.38 | 100
22 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Providing functional Household Tap Connection (FHTC) including Other allied works under Keliathole Palaskola W/S Scheme (Zone-I & III) under Raghunathpur Sub-Division, P.H.E. | Assistant Engineer | Junior Engineer | ORD/000901/2022-2023 | 1893/PD | 15/12/2022 | 13/02/2023 | BASANTA KUMAR SINGHADEO | 129.67 | 129.4 | 99.8 | 90
23 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Rectification of Internal lighting and external lighting for Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000049/2023-2024 | 518/PMD | 05/05/2023 | 04/07/2023 | RAKSHIT ENTERPRISE | 9.24 | 8.8 | 95.16 | 100
24 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rudra Mouza, JL No.-10, Plot No.68 at OHR site under Keliyathole-Palashkola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 701/PD | 22/05/2023 | 21/07/2023 | MAHARSHI BANERJEE | 14.33 | 12.86 | 89.76 | 70
25 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Dolang Kocha Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2023-2024 | 1358/PD | 13/09/2023 | 28/10/2023 | CHANDAN CHATTERJEE | 16.26 | 16.25 | 99.98 | 100
26 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of Office Cum Godown at PHE Campus Under Keliathole Palashkola w/s Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001869/2023-2024 | 93/PD | 15/01/2024 | 14/04/2024 | KM ENTERPRISES | 25.62 | 25.44 | 99.28 | 100
27 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Chatanigoramore to Kharhbon & Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000443/2024-2025 | 1505/PD | 27/08/2024 | 11/10/2024 | CHAIL CONSTRUCTION | 29.59 | 20.96 | 70.83 | 100
28 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 4 & 5) along with necessary 100 mm dia GI collecting line from Riverbed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakurighat of Parbeliya W/S Scheme under Keliyathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division , PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000211/2024-2025 | 1244/PD | 04/07/2024 | 18/08/2024 | M/S KARUNAMOYEE CONSTRUCTION | 4.38 | 3.68 | 84.09 | 100
29 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-III OHR site & supplying laying fitting fixing Parallel pipe line at Rangadihi Village & Kharpara village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(Zone -III) | Assistant Engineer | Junior Engineer-4 | ORD/000329/2024-2025 | 1354/PD | 25/07/2024 | 23/10/2024 | SUBRATA SINGHADEO | 22.28 | 5.88 | 26.37 | 100
30 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Chatanigora , & Pinrrah Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000444/2024-2025 | 1506/PD | 27/08/2024 | 11/10/2024 | CHAIL CONSTRUCTION | 45.72 | 0 | 0 | 100
31 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Repering & Renovation of connecting line at Kasai River of Maguria Lalpur & including providing House Hold Tap Connection (FHTC) of two no school (Amliatora Pry School -1no, Daldali Girls High School-2nos) and other allied works under Maguria Lalpur W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000378/2024-2025 | 1359/PD | 25/07/2024 | 23/09/2024 | ALOK KUMAR CHAKRABORTY | 2.54 | 2.53 | 99.46 | 100
32 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | Assistant Engineer | Junior Engineer | ORD/004362/2023-2024 | 56/PD | 09/01/2024 | 29/01/2024 | SSPR VALVE MANUFACTURING PVT LTD | 8.58 | 8.55 | 99.64 | 95
33 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Sinking of 1(One) nostubewell, laying DI pipe , filling and surface dressing at OHR Site of Zone - I of Kashipur Block under Keliathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000330/2024-2025 | 1355/PD | 25/07/2024 | 24/08/2024 | MAHARSHI BANERJEE | 6.26 | 6.17 | 98.56 | 80
34 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supplying laying fitting fixing of different dia pipe line & FHTC connection repairing (Damage of Old different dia pipe line & FHTC connection due to widening of road & Drain of PWD Roads from Doldoli more to Mourandih more &Karandih village ) in connection with Jal Jeevan Mission (JJM) under Maguria Lalpur Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division uneder Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000460/2024-2025 | 1519/PD | 27/08/2024 | 11/10/2024 | ALOK KUMAR CHAKRABORTY | 16.16 | 16.02 | 99.15 | 100
35 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying of Distribution System of pipe line at Kakdiha village is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Kalyathol & Palaskhola Piped Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000132/2024-2025 | 898/PD | 07/05/2024 | 21/06/2024 | SABYASACHI MISHRA | 14.23 | 14.18 | 99.66 | 100
36 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying of Distribution line and Road Crossing and Construction of Sluice valve Chamber and other allied works for Kashipur under Kalyathol & Palaskhola W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000492/2024-2025 | 1707/PD | 05/09/2024 | 20/10/2024 | MAHARSHI BANERJEE | 33.25 | 33.2 | 99.85 | 80
37 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | Assistant Engineer | Junior Engineer | ORD/004361/2023-2024 | 55/PD | 09/01/2024 | 29/01/2024 | SSPR VALVE MANUFACTURING PVT LTD | 8.13 | 8.1 | 99.67 | 95
38 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Enhancement of the contract demand from 90 KVA at 0.4 KV to 180/180/180/180/180 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Palashkhola Water Supply, (Consumer ID -942406300) |  |  | BILL/00862/2023-2024 | BP-23-24-340 | 21/03/2024 | 21/03/2024 | WBSEDCL PURULIA | 16.57 | 0 | 0 | 0
39 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Sl ii) Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur WS Scheme along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division PWD in the district of Purulia in Year 2023-2024. Estimate Amount: Rs.1,21,59,280/- |  |  | BILL/00736/2024-2025 | BP-2024-25-408 | 22/09/2024 | 22/09/2024 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 57.29 | 0 | 0 | 0
40 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Additional estimate for laying of distribution system, mending good damage of road and other allied works under Keliathole Palashkola w/s Scheme (Zone-III) within Raghunathpur Sub Division Under Purulia Division ,PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003976/2023-2024 | 521/PD | 16/03/2024 | 01/08/2025 | PREMNATH MITRA | 87.58 | 0 | 0 | 0
41 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying Distribution system ,Functional House hold tap Connection including other allied work under Keliathole Palashkola W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division PHE Dte |  |  | ORD/001082/2024-2025 | 2177/PD | 13/12/2024 | 11/02/2025 | SUBRATA SINGHADEO | 1.69 | 0 | 0 | 0
42 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying Distribution pipe line including providing functional Household Tap Connection (FHTC), Laying Clear water Rising main ,Sinking of 6 (Six) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line , and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000641/2022-2023 | 1252/PD | 30/08/2022 | 01/04/2025 | PRINCE INDUSTRIES ( INDIA) | 188.52 | 124.53 | 66.06 | 70
43 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000640/2022-2023 | 1162/PD | 01/08/2022 | 01/04/2025 | MADHU SUDAN RAKSHIT | 121.14 | 70.07 | 57.84 | 90
44 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | Assistant Engineer | Junior Engineer | ORD/000734/2022-2023 | 1443/PD | 14/09/2022 | 01/08/2025 | PREMNATH MITRA | 265.46 | 244.3 | 92.03 | 95
45 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply, Delivery and installation 200 kva voltage stabilizer for Augmentation of Palashkhola Keliyathol w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000050/2023-2024 | 519/PMD | 05/05/2023 | 04/07/2023 | ALPHA ENTERPRISES | 26.97 | 0 | 0 | 100
46 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Laying distribution pipe line and other allied work under Keliathole Palashkola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 673/PD | 17/05/2023 | 01/08/2025 | PREMNATH MITRA | 70.11 | 68 | 96.99 | 100
47 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply & installation of Horizontal Multistage Centrifugal pumping machinery with other allied works for Augmentation at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000118/2023-2024 | 646/PMD | 08/06/2023 | 31/03/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 77.49 | 71.85 | 92.73 | 100
48 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply, delivery fitting & fixing of 33Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Kashipur Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001156/2024-2025 | 2308/PD | 31/12/2024 | 01/03/2025 | BISWAJIT MAJI | 3.01 | 0 | 0 | 100
49 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply delivery and installation of valve, cable, de -watering pump etc. and other allied work at Palashkhola water supply scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000591/2024-2025 | 1449/PMD | 01/10/2024 | 03/03/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.6 | 0 | 0 | 100
50 | PURULIA |  | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Supply and installation of PLC panel, Level transmitter,Solar light(OHR Site) with other allied work at Palashkhola Kaliathol water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000685/2024-2025 | 1697/PMD | 06/12/2024 | 06/03/2025 | BISHWANATH NANDI | 16.61 | 0 | 0 | 100
51 | PURULIA |  | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | SM/11453 | Augmentation | Construction of Toilet and Repairing and Renovation of Guard room , Pump house, CWR and Boundary wall at Palaskhola-keliyatol under Palaskhola-keliyatol W/S scheme of Raghunathpur Sub-Division under Purulia Division , PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000331/2024-2025 | 1356/PD | 25/07/2024 | 01/05/2025 | NANIGOPAL DEY | 5.68 | 0 | 0 | 100
Total | [13 empty] | 2325.69 | 1213.9 | 52.2