## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 27/03/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 24.94 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 529/PD | 11/04/2023 | 10/06/2023 | AQUEDUCT PLASTICS PVT LTD | 447.81 | 32.76 | 7.31 | 8
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 11/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 24.92 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 03/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.88 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 24/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.96 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 21/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 24.96 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 18/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 25 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 28/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.9 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/06/2023 to 31/10/2023) | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 220/RNP | 30/05/2023 | 30/10/2023 | CHANDRA SHEKHAR KUNDU | 0.74 | 1.95 | 265.41 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 79/PD | 17/01/2023 | 17/01/2023 | Resource Division | 0.15 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuous work order for the work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/11/2023 to 31/03/2024) | Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 466/RNP | 10/10/2023 | 10/03/2024 | CHANDRA SHEKHAR KUNDU | 0.74 | 1.99 | 270.24 | 60
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Continuation Work Order for the Work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/04/2024 to 31/08/2024) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/003683/2023-2024 | 139/RNP | 12/03/2024 | 12/08/2024 | CHANDRA SHEKHAR KUNDU | 0.74 | 1.97 | 267.37 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | SM/14022 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 331 cum and other allied works under Raghunathpur W/S Scheme (Zone-VII-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001171/2024-2025 | 2325/PD | 31/12/2024 | 16/01/2026 | NANIGOPAL DEY | 13.17 | 0 | 0 | 0
Total | [13 empty] | 532.59 | 55.93 | 10.5