## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 27/03/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 10.65 | 24.94 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Repairing of DI rising main and repairing, renovation of Boundary wall (Total lenght =148 mtr) at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 545/PD | 12/04/2023 | 12/05/2023 | M/S SAYAK BHATTACHARYA | 10.93 | 10.91 | 99.83 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 11/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 1.25 | 24.92 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 03/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.88 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 24/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.96 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 21/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0.54 | 24.96 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 18/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 25 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 28/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 1.21 | 24.9 | 100
9 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Raghunathpur Pipe Water Supply scheme for Zone-VIII under Purulia Mechanical Division PHE. Dte. District Purulia |  |  | ORD/000387/2022-2023 | 218/PMD | 28/02/2023 | 30/03/2023 | JAL PRAVAHIKA PVT. LTD | 21.57 | 21.57 | 100 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Repairing of DI Rising Main and new Construction of Boundary wall, RCC Pillar, Barbed wire at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 867/PD | 30/06/2023 | 30/07/2023 | M/S SAYAK BHATTACHARYA | 4.25 | 4.24 | 99.8 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 72/PD | 17/01/2023 | 17/01/2023 | Resource Division | 1.38 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Seleta Mouza, JL No.-41, Plot No.237 at Boosting Pump Station site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 543/PD | 12/04/2023 | 11/06/2023 | SUBRATA SINGHADEO | 33.43 | 23.32 | 69.76 | 42
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Repairing of DI Rising Main, construction of RCC Clear water reservoir (CWR) of capacity 150 Cum, New Boundary wall (Lenth=62 mtr) and 01 No. Sinking of RBT Tubewell (200X165 mm dia) and other allied works at Zone-VIII OHR campus of Raghunathpur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000131/2024-2025 | 897/PD | 07/05/2024 | 25/04/2026 | SANDIP KUMAR DUBEY | 36.14 | 25.34 | 70.12 | 60
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Construction of 4 Nos. Sluice Valve Chamber at Setpalash & Cheliyama Bagdipara under Raghunathpur W/S Scheme (German Assisted) Zone-VIII of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/004766/2023-2024 | 174/RNP | 27/03/2024 | 03/04/2024 | JOY GURU ENTERPRISE | 0.92 | 0.84 | 91.19 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIII) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 10) | Assistant Engineer | Junior Engineer | ORD/001157/2022-2023 | 432/PD | 22/03/2023 | 01/01/2026 | PREMNATH MITRA | 414.3 | 158.07 | 38.15 | 45
16 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Laying of different dia HDPE pipe in distribution pipe line , replacing existing CI Pipes and allied works of Raghunathpur Water Supply Scheme( Zone -VIII) at Raghunathpur-II Block of Raghunathpur Sub division under Purulia Division,PHE DTE. | Assistant Engineer | Junior Engineer-1 | ORD/000554/2024-2025 | 1596/PD | 30/08/2024 | 01/04/2026 | PREMNATH MITRA | 94.69 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Continuation work order for the work of "Day to day hiring and operation charges of 1 (one) number 10/15 KVA Generator set Engaging one number expert operator for the office of the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. under Raghunathpur W/S Scheme (German Project) (w.e.f. 04.04.2025 to 03.06.2025)" | Assistant Engineer | Junior Engineer-1 | ORD/000575/2025-2026 | 166/RNP | 02/04/2025 | 02/06/2025 | MANATOSH SINGH | 0.87 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | SM/14023 | Augmentation | Repairing and Renovation of 300cum R.C.C. Elevated Reservoir & Repairing of Boundary Wall, Repairing of Guard Room & Construction of Toilet at Cheliyama OHR Site under Raghunathpur W/S Scheme (German Assisted) Zone-VIII of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000138/2024-2025 | 909/PD | 07/05/2024 | 31/03/2025 | KHITISH CHANDRA PATHAK | 8.29 | 0 | 0 | 100
Total | [13 empty] | 696.02 | 261.57 | 37.58