## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 27/03/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Repairing and renovation of Panel Room at office of the Assistant Engineer, Raghunathpur Sub-Division, PHE Dte. at S.D. Hospital Campus under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001102/2022-2023 | 94/RNP | 10/03/2023 | 25/03/2023 | BISWAJIT MAJI | 0.91 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone IV B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000125/2023-2024 | 861/PMD | 20/07/2023 | 19/08/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 0 | 75
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 11/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 03/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 24/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 21/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 18/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 28/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supplying & laying of different dia HDPE pipe line with other allied works from Tilabani OHR Campus to Bathandih village through Rabon More at Tilabani villlage under Kalabani G.P. under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2023-2024 | 665/PD | 17/05/2023 | 16/06/2023 | SADHAN GORAIN | 12.88 | 0 | 0 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 78/PD | 17/01/2023 | 17/01/2023 | Resource Division | 0.55 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Construction of Pump House (10 X 7 mtr) at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001044/2022-2023 | 276/PD | 27/02/2023 | 01/04/2025 | BASANTA KUMAR SINGHADEO | 18.56 | 0 | 0 | 40
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Laying of Distribution System including pipe carrying structure all complete including cost of materials including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-IV A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 584/PD | 20/04/2023 | 19/06/2023 | M/S RAJ KUMAR KHAN | 267.81 | 0 | 0 | 80
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Construction of Guard Room with toilet block at Zone-IV A under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001042/2024-2025 | 2103/PD | 05/12/2024 | 05/03/2025 | PRAKASH DESHMUKH | 6.41 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Construction of RCC Over Head Reservoir (Torch types with solid raft) capacity 150 Cum and other allied works of Raghunathpur Water Supply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000980/2022-2023 | 92/PD | 20/01/2023 | 17/10/2023 | BOSE CONSTRUCTION | 72.84 | 0 | 0 | 85
16 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Construction of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC) and other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IV B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 6) | Assistant Engineer | Junior Engineer | ORD/001104/2022-2023 | 270/PD | 24/02/2023 | 30/11/2024 | MITHU BUILDERS | 211.47 | 0 | 0 | 75
17 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Repairing and renovation of Gar Panchakot Inspection Bunglow (Ground Floor) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000967/2022-2023 | 46/PD | 09/01/2023 | 10/03/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 4.39 | 0 | 0 | 100
18 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Repairing works at 8 Nos Bridge of Rising Pipe line works under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001173/2024-2025 | 2327/PD | 31/12/2024 | 01/03/2025 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.81 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000648/2024-2025 | 1108/PMD | 11/07/2024 | 01/10/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 90
20 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site -Salata (I-B) (Tube Well -IV) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000651/2024-2025 | 1257/PMD | 22/08/2024 | 01/10/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
21 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Salata of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000611/2024-2025 | 864/PMD | 04/06/2024 | 01/10/2024 | ANUP KUMAR SAHA | 0.94 | 0 | 0 | 95
22 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, hi-lifting boundary wall and other allied works under Raghunathpur W/S Scheme (Zone-IV-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001097/2024-2025 | 2186/PD | 13/12/2024 | 13/03/2025 | SUBRATA SINGHADEO | 12.67 | 0 | 0 | 0
23 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Earthing arrangement and other works, at OHR site Salata of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000607/2024-2025 | 898/PMD | 10/06/2024 | 01/10/2024 | ANUP KUMAR SAHA | 0.7 | 0 | 0 | 90
24 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Construction of Guard Room with toilet block at Zone-IV B under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001043/2024-2025 | 2104/PD | 05/12/2024 | 05/03/2025 | SAANVI CONSTRUCTION | 6.41 | 0 | 0 | 0
25 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-III), under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000002/2025-2026 | 563/PMD | 07/04/2025 | 27/04/2025 | SANTU MITRA | 0.94 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Addition of column pipe including supply along with other works at OHR site-IA/II , Gobag (T/W no- 1,2,3 & 4 ) under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000015/2025-2026 | 633/PMD | 24/04/2025 | 09/05/2025 | ANUP KUMAR SAHA | 0.75 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-IV), under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000010/2025-2026 | 621/PMD | 22/04/2025 | 12/05/2025 | ANUP KUMAR SAHA | 0.94 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Withdrawing of existing CI Distribution pipe line (Damage portion) and relaying of GI pipe (80 mm dia) and distribution parallel HDPE pipe line including other allied works from Adra More to Nilu Kali Mandir at Raghunathpur Water Supply Scheme (Zone-III) under Zone-IV of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001355/2024-2025 | 505/PD | 25/03/2025 | 23/07/2025 | M/S SAYAK BHATTACHARYA | 80.88 | 0 | 0 | 100
29 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-II), under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000003/2025-2026 | 562/PMD | 07/04/2025 | 27/04/2025 | S. PATHAK & CO. | 0.96 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | SM/14024 | Augmentation | Supply, delivery & installation of earthing arrangement and other works at OHR site- Babugram (Zone-VI) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000004/2025-2026 | 561/PMD | 07/04/2025 | 27/04/2025 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
Total | [13 empty] | 808.25 | 0 | 0