## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2020-2021 | 357/E/PD | 25/02/2021 | 27/03/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Repairing and renovation of Gar Panchakot Inspection Bunglow (1st Floor & outside) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001046/2022-2023 | 278/PD | 27/02/2023 | 29/03/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 3.09 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000905/2022-2023 | 1025/PD | 06/01/2023 | 11/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000909/2022-2023 | 1008/PD | 29/12/2022 | 03/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000910/2022-2023 | 942/PD | 19/12/2022 | 24/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000906/2022-2023 | 1087/A/PD | 16/01/2023 | 21/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2022-2023 | 931/A/PD | 13/12/2022 | 18/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000908/2022-2023 | 1002/PD | 23/12/2022 | 28/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Nanduka Mouza, JL No.-63, Plot No.-476 under Raghunathpur-II Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000067/2023-2024 | 698/PD | 22/05/2023 | 21/07/2023 | AMIT PATHAK | 14.25 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Simra ,Pabra , Nabagram, Muchkunda , Muldi , pratappur , Dhanuktor , Manipur) |  |  | ORD/001112/2024-2025 | 2204/PD | 13/12/2024 | 11/02/2025 | SANTANU BANERJEE | 96.18 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Khajura Mouza, JL No.-164, Plot No.-565 under Raghunathpur-I Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2023-2024 | 766/PD | 08/06/2023 | 07/08/2023 | MAA TARA CONSTRUCTION | 11.42 | 0 | 0 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-V-B (Nanduka) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-4 | ORD/001359/2023-2024 | 1728/PD | 04/12/2023 | 13/03/2024 | MANIK MAHATO | 4.86 | 0 | 0 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 1104/PD | 11/06/2024 | 11/06/2024 | Resource Division | 25.08 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | SM/14025 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VA) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 7) | Assistant Engineer | Junior Engineer | ORD/001192/2022-2023 | 461/PD | 27/03/2023 | 29/03/2025 | SANTANU BANERJEE | 341.55 | 0 | 0 | 75
Total | [13 empty] | 565.67 | 0 | 0