## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for District Agragami Mohila O-Sisu Mangal Samiti NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000428/2021-2022 | 94/PR | 11/03/2022 | 09/06/2022 | DAS AND SON | 4.77 | 4.77 | 100 | 0
2 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) SL NO.02 | Assistant Engineer |  | ORD/000513/2022-2023 | 309/PR | 29/06/2022 | 29/06/2023 | COMPUTER MEDIA | 2.97 | 1.26 | 42.49 | 100
3 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus,Ranchi Road under Purulia Division, PHE Dte (w.e.f.01.07.2022 to 31.12.2022). SL NO.05 | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 312/PR | 29/06/2022 | 29/12/2022 | ARUNALOY SCIENTIFIC HOUSE | 3.86 | 3.82 | 99.19 | 0
4 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) SL NO.01 | Assistant Engineer |  | ORD/000512/2022-2023 | 308/PR | 29/06/2022 | 29/06/2023 | COMPUTER MEDIA | 2.73 | 1.34 | 48.83 | 0
5 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation and Maintenance and water testing in Jhalda Aug WTP Sub-Disrict Laboratory under Purulia Division, PHE Dte. (For 01 ( One) Year) (w.e.f. 01.07.2021 to 30.06.2022) | Assistant Engineer | Junior Engineer-1 | ORD/000013/2021-2022 | 723/PD | 30/06/2021 | 30/06/2022 | ANUP KUMAR SAHA | 5.24 | 2.7 | 51.57 | 0
6 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Day to establishment works of RWS Purulia Sub-Division Office & maintaning of files, letters issued & despatched register, service book of officials & all others ancilliary works by deployment of 02 (Two) nos. of personnel having proficiency with computer & office assistant having experience in Government works on monthly basis for the office of the Assistant Engineer, RWS Purulia Sub-Division, P.H.E. Dte. (1st Year) (Period from 01.01.2022 to 31.12.2022) (For 12 Months) | Assistant Engineer |  | ORD/000364/2021-2022 | 613/PD | 27/12/2021 | 27/12/2022 | COMPUTER MEDIA | 4.48 | 2.28 | 50.89 | 0
7 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Jhalda-I Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.05.2022 to 31.08.2022). SL NO.02 | Assistant Engineer |  | ORD/000361/2022-2023 | 244/PR | 29/04/2022 | 03/05/2022 | KOUSHIK CHATTERJEE | 2.09 | 2.01 | 96.41 | 0
8 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.05 | Assistant Engineer |  | ORD/000442/2022-2023 | 300/PR | 23/06/2022 | 23/06/2023 | TUSHAR KANTI GORAI | 3.66 | 3.53 | 96.37 | 100
9 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Baghmundi Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.01 | Assistant Engineer |  | ORD/000437/2022-2023 | 296/PR | 23/06/2022 | 05/07/2022 | BOSE CONSTRUCTION | 3.66 | 2.3 | 63 | 100
10 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory Of Raghunathpur Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.06 | Assistant Engineer |  | ORD/000443/2022-2023 | 301/PR | 23/06/2022 | 23/06/2023 | MANATOSH SINGH | 4.76 | 2.2 | 46.25 | 100
11 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 31.12.2022). SL NO.04 | Assistant Engineer | Junior Engineer-3 | ORD/000515/2022-2023 | 311/PR | 29/06/2022 | 29/12/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.77 | 2.6 | 93.56 | 0
12 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | Assistant Engineer | Junior Engineer | ORD/000760/2022-2023 | 1356/PD | 31/08/2022 | 30/06/2023 | ANUDIP SAHA | 4.72 | 1.79 | 37.93 | 100
13 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Continuation order for the work of "Supply of Laboratory reagent/media/consumables required for routi ne water testing of different laboratories under Purulia Division, PHE Dte. ( For 3 months)" | Assistant Engineer | Junior Engineer | ORD/000895/2022-2023 | 1895/PD | 15/12/2022 | 30/12/2022 | ARUNALOY SCIENTIFIC HOUSE | 33.8 | 33.8 | 100 | 100
14 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Continuation work for Day to establishment works of RWS Purulia Sub-Division Office & maintaning of files, letters issued & despatched register, service book of officials & all others ancilliary works by deployment of 02 (Two) nos. of personnel having proficiency with computer & office assistant having experience in Government works on monthly basis for the office of the Assistant Engineer, RWS Purulia Sub-Division, P.H.E. Dte. (1st Year) (Period from 01.01.2023 to 31.03.2023) | Assistant Engineer | Junior Engineer | ORD/001004/2022-2023 | 650/PR | 30/12/2022 | 30/03/2023 | COMPUTER MEDIA | 1.1 | 1.1 | 100 | 100
15 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 11 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-A) SL NO.05 | Assistant Engineer | Junior Engineer | ORD/001074/2022-2023 | 95/PR | 28/02/2023 | 30/03/2023 | SIKHA ENTERPRISES | 0.71 | 0.7 | 99.26 | 100
16 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Sirkabad SDL, Bagmundi SDL,Santuri SDL,Dubra SDL ,Joypur SDL) Sl NO.02 | Assistant Engineer | Junior Engineer | ORD/001064/2022-2023 | 92/PR | 28/02/2023 | 30/03/2023 | DEBANJAN SEAL | 0.83 | 0.82 | 99.75 | 100
17 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Bandwan WTP SDL, Balarampur WTP SDL,Jhalda WTP SDL ,Raghunathpur WTPSDL,Chemliyama SDL.) (SL NO.01) | Assistant Engineer | Junior Engineer-3 | ORD/001042/2022-2023 | 91/PR | 28/02/2023 | 30/03/2023 | ANUDIP SAHA | 0.83 | 0.82 | 99.75 | 100
18 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 11 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-B) SL NO. 6 | Assistant Engineer | Junior Engineer | ORD/001075/2022-2023 | 96/PR | 28/02/2023 | 30/03/2023 | INDRAJIT SARKAR | 0.71 | 0.7 | 99.26 | 100
19 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-D) SL NO. 13 | Assistant Engineer | Junior Engineer | ORD/001081/2022-2023 | 103/PR | 28/02/2023 | 30/03/2023 | ANUDIP SAHA | 0.92 | 0.9 | 98.73 | 100
20 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Barabazar SDL, Raghunathpur SDL, Kashipur SDL ,Hura SDL) SL NO.03 | Assistant Engineer | Junior Engineer | ORD/001070/2022-2023 | 93/PR | 28/02/2023 | 30/03/2023 | SUDHANSHU OJHA | 0.66 | 0.66 | 99.75 | 100
21 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-C) | Assistant Engineer | Junior Engineer | ORD/001080/2022-2023 | 102/PR | 28/02/2023 | 30/03/2023 | DEBANJAN SEAL | 0.92 | 0.91 | 99.81 | 100
22 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Requisition for Salary component of laboratory, Laboratory Maintenance charges of 17 laboratory, Festival Bonus of Laboratory personnel and sample collection charges for sampling assistants (2000 rupees per month). |  |  | BILL/00124/2022-2023 |  | 10/01/2023 | 10/01/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PH, DTE | 92.8 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub- District Laboratory under RWS Purulia Sub- Division, PHE Dte. (w.e.f. 01.08.2021 to 30.06.2022) ]Tender No 792/2022-2023 of EE/PD] |  |  | VCH/001525/2022-2023 | BP-2022-23-846 | 31/03/2023 | 31/03/2023 | ANUDIP SAHA | 2.58 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & maintenance & water testing in the laboratory of Balarampur WTP Sub District Laboratory under RWS Purulia Sub-Division PHE Dte. (w.e.f. 01.07.2022 to 31.12.2022) [Tender No- 409/2022-23 of EE/PD] |  |  | VCH/001899/2022-2023 | BP-2023-24-51 | 19/04/2023 | 19/04/2023 | SADHAN GORAIN | 2.59 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | conduct a social awareness programmes Le SWACH SUJAL SHAKTI SAMMAN, WORLD WATER DAY, WORLD HEALTH DAY, SCHOOL AWARNESS PROGRAMMES, SAVE WATER PROGRAMMES, WORLD ENVIRONMENT DAY, VILLAGERS AWARNESS PROGRAMME as per the guidelines of JAL JEEVAN MISSION. We will be organising the programmes at several blocks. |  |  | BILL/00617/2023-2024 | BP-2023-24-370 | 10/08/2023 | 10/08/2023 | M/S SAYAK BHATTACHARYA | 0.66 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Bill paid for Laboratory testing. |  |  | BILL/00443/2023-2024 | BP-2023-24-306 | 18/07/2023 | 18/07/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0 | 0
27 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Bill paid for Calibration of equipment's for Laboratory purpose. |  |  | BILL/00111/2023-2024 | BP-2023-24-71 | 05/05/2023 | 05/05/2023 | MEASURE & PRECISION ENGINEER | 0.35 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Bill paid for RWS Purulia Sub-Division Laboratory Air conditioner repair MB-No.2200/PD, Page No.24 to 25 |  |  | BILL/00603/2023-2024 | BP-2023-24-365 | 09/08/2023 | 09/08/2023 | BABA AMARNATH TRADERS | 0.1 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Office stationary bill paid to NGO. |  |  | BILL/00701/2023-2024 | BP-2023-24-435 | 05/09/2023 | 05/09/2023 | KETIKA CONSUMERS CO-OP STORES LTD | 0.34 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Laboratory payment. |  |  | VCH/001855/2022-2023 | BP-2022-23-625 | 15/02/2023 | 15/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Bonus bill paid for NGO Laboratory staffs against PFMS Vr No. BP-2022-23-574 to BP-2022-23-588; BP-2022-23-590 to BP-2022-23-600; BP-2022-23-602 to BP-2022-23-614 & BP-2022-23-618 & BP-2022-23-620 to BP-2022-23-624. |  |  | VCH/001854/2022-2023 | BP-2022-23-634 | 22/02/2023 | 22/02/2023 | LABORATORY STAFFS | 2.21 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.02 | Assistant Engineer |  | ORD/000439/2022-2023 | 297/PR | 23/06/2022 | 23/06/2023 | BOSE CONSTRUCTION | 3.66 | 2.3 | 63 | 93
33 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Santuri Sub-District Water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.07 | Assistant Engineer | Junior Engineer | ORD/000444/2022-2023 | 302/PR | 23/06/2022 | 23/06/2023 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 2.2 | 60.16 | 100
34 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.08 | Assistant Engineer |  | ORD/000445/2022-2023 | 303/PR | 23/06/2022 | 23/06/2023 | BOSE CONSTRUCTION | 4.76 | 3.04 | 63.85 | 100
35 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Hura Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | Assistant Engineer | Junior Engineer | ORD/000758/2022-2023 | 1354/PD | 31/08/2022 | 30/06/2023 | SUPRIYA MAHANTI MISHRA | 4.81 | 2.57 | 53.38 | 100
36 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Hura WTP, Barabazar & Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | Assistant Engineer | Junior Engineer | ORD/000291/2023-2024 | 378/A/PR | 27/07/2023 | 27/07/2024 | KABERI DUTTA | 0.96 | 0 | 0 | 100
37 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Manbazar-II Sub-District , Dist Lab & others water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 379/PR | 27/07/2023 | 27/07/2024 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
38 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Jhalda-I, Sirkabad & Baghmundi Sub-District water testing Laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | Assistant Engineer | Junior Engineer | ORD/000292/2023-2024 | 378/B/PR | 27/07/2023 | 27/07/2024 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
39 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Santuri, Dubra & Cheliyama Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | Assistant Engineer | Junior Engineer | ORD/000295/2023-2024 | 379/A/PR | 27/07/2023 | 27/07/2024 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
40 | PURULIA |  | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Rghunathpur WTP,Kashipur & Raghunathpur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | Assistant Engineer | Junior Engineer | ORD/000293/2023-2024 | 378/C/PR | 27/07/2023 | 27/07/2024 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
Total | [13 empty] | 209.59 | 81.17 | 38.73