## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-I] | Assistant Engineer | Junior Engineer,Junior Engineer-1,Junior Engineer-3 | ORD/000981/2022-2023 | 93/PD | 20/01/2023 | 28/09/2025 | KHITISH CHANDRA PATHAK | 59.34 | 40.34 | 67.98 | 80
2 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-II] | Assistant Engineer | Junior Engineer | ORD/000982/2022-2023 | 94/PD | 20/01/2023 | 19/02/2023 | MS MITRA SENGUPTA ENTERPRISES | 8.37 | 3.92 | 46.87 | 45
3 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-III] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000983/2022-2023 | 95/PD | 20/01/2023 | 02/10/2024 | CHANDAN CHATTERJEE | 11.22 | 10.41 | 92.71 | 95
4 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-V] | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000984/2022-2023 | 96/PD | 20/01/2023 | 01/04/2025 | AMIT PATHAK | 10.76 | 9.77 | 90.78 | 85
5 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-VI] | Assistant Engineer | Junior Engineer | ORD/000985/2022-2023 | 97/PD | 20/01/2023 | 19/02/2023 | DEBANJAN SEAL | 4.95 | 4.62 | 93.46 | 85
6 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-IV] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/001123/2022-2023 | 396/PD | 16/03/2023 | 30/04/2023 | M/S ACHARJEE CONSTRUCTION | 19.01 | 11.41 | 60.04 | 62
7 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000457/2022-2023 | 297/PMD | 16/03/2023 | 15/05/2023 | GOENKA ENTERPRISE | 33.83 | 8.54 | 25.23 | 20
8 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Supply, Delivery and installation of 30KVA oil cooled voltage stabilizer and allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000458/2022-2023 | 298/PMD | 16/03/2023 | 15/05/2023 | BISHWANATH NANDI | 4.13 | 3.13 | 75.85 | 80
9 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Yard lighting arrangement with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000459/2022-2023 | 299/PMD | 16/03/2023 | 15/05/2023 | S. PATHAK & CO. | 5.02 | 2.93 | 58.34 | 20
10 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Santuri Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000041/2023-2024 | 447/PMD | 20/04/2023 | 20/05/2023 | DAS ENTERPRISE | 21.57 | 12.94 | 60 | 25
11 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - D, Mouza - PORADIHA, BELJHUPA, KALAID] | Assistant Engineer | Junior Engineer | ORD/000062/2023-2024 | 1054/PD | 08/08/2023 | 06/11/2023 | CHATTERJEE CONSTRUCTION | 64.43 | 42.53 | 66.01 | 63
12 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - B, Mouza - Dumdumi] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000061/2023-2024 | 1055/PD | 08/08/2023 | 06/11/2023 | M/S SAYAK BHATTACHARYA | 73.52 | 72.67 | 98.85 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Construction of RCC Over Head Reservoir (OHR) Capacity 100 cum and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000986/2022-2023 | 98/PD | 20/01/2023 | 17/10/2023 | CHATTERJEE CONSTRUCTION | 56.67 | 48.3 | 85.23 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Construction of Switch Room Cum Chlorin Room at Santuri OHR Site of Santuri W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000171/2023-2024 | 933/PD | 19/07/2023 | 27/10/2023 | PURNA CHANDRA TEWARI | 4.21 | 3 | 71.12 | 100
15 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | New Connection for Augmentation of Santuri |  |  | BILL/00252/2023-2024 | BP-2023-24-148 | 14/09/2023 | 14/09/2023 | WBSEDCL PURULIA | 4.95 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS | SM/14459 | Augmentation | Supply, delivery and installation of Submersible pumping machineries ,Al. Armoured cables and laying of Al. armoured cables for Augmentation of Santuri W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 996/PMD | 21/06/2024 | 14/09/2026 | SEN BROTHERS | 4.25 | 3 | 70.59 | 70
Total | [13 empty] | 386.24 | 277.52 | 71.85