## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | Assistant Engineer | Junior Engineer | ORD/000988/2022-2023 | 100/PD | 20/01/2023 | 20/04/2023 | MANATOSH SINGH | 79.67 | 16.61 | 20.84 | 55
2 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra Water Supply Scheme, Block- Para ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2022-2023 | 1749/PD | 22/11/2022 | 22/12/2022 | M/S. DESTINY CONSTRUCTION | 3.48 | 3.48 | 100 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-E] | Assistant Engineer | Junior Engineer | ORD/000990/2022-2023 | 103/PD | 20/01/2023 | 19/02/2023 | M/S SAYAK BHATTACHARYA | 13.69 | 13.65 | 99.75 | 100
4 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-C] | Assistant Engineer | Junior Engineer | ORD/001000/2022-2023 | 101/PD | 20/01/2023 | 19/02/2023 | SOUMITRA CHAKRABORTY | 98.6 | 98.58 | 99.98 | 100
5 | PURULIA |  | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Dubra (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000039/2023-2024 | 445/PMD | 20/04/2023 | 20/05/2023 | DEY ENTERPRISE,MALDAH | 21.63 | 21.63 | 100 | 70
6 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 882/PD | 03/07/2023 | 17/08/2023 | SABYASACHI MISHRA | 11.94 | 11.86 | 99.36 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur W/S Schema along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division, P.WD in the district of Purulia in the year 2023-24. |  |  | BILL/00625/2023-2024 | BP-2023-24-386 | 18/08/2023 | 18/08/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 60.8 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Dubra W/S Schema on Raghunathpur Chandankairy-Chas Road CH-13.963 KM to CH-15.178 Km under Purulia Division, P.W.D in the district of Purulia in the year 2023-2024. |  |  | BILL/00624/2023-2024 | BP-2023-24-387 | 18/08/2023 | 18/08/2023 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 95.57 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System including supply of materials including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | Assistant Engineer | Junior Engineer | ORD/000987/2022-2023 | 99/PD | 20/01/2023 | 29/06/2025 | NANIGOPAL DEY | 97.25 | 55.99 | 57.57 | 40
10 | PURULIA |  | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, HOT, Flowmeter and other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000456/2022-2023 | 296/PMD | 16/03/2023 | 15/05/2023 | TAPAN KUMAR DEY | 42.49 | 22.31 | 52.51 | 40
11 | PURULIA |  | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Dubra water supply scheme under PMD PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000182/2023-2024 | 1172/PMD | 03/11/2023 | 02/01/2024 | SWAPAN ENTERPRISE | 7.21 | 6.02 | 83.48 | 75
12 | PURULIA |  | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Internal and external illumination with other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000184/2023-2024 | 1174/PMD | 03/11/2023 | 02/01/2024 | PINTU DEY | 5.37 | 3.46 | 64.4 | 25
13 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Supply, delivery fitting & fixing of 1 No. Scheme Description Sign board (6' X 3') under Dubra W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Head Work Site | Assistant Engineer | Junior Engineer | ORD/001944/2023-2024 | 25/RNP | 15/01/2024 | 22/01/2024 | M/S SAYAK BHATTACHARYA | 0.17 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-D] | Assistant Engineer | Junior Engineer | ORD/000989/2022-2023 | 102/PD | 20/01/2023 | 06/03/2023 | SUBRATA SINGHADEO | 39.27 | 39.25 | 99.95 | 100
15 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Dubra Mouza, JL No.-79, Plot No.499 at OHR site under Dubra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-4 | ORD/000015/2023-2024 | 544/PD | 12/04/2023 | 31/12/2024 | ASHOK KUMAR CHATTERJEE | 14.79 | 11.38 | 76.91 | 100
16 | PURULIA |  | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | SM/14460 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room and Sinking of 2 (Two) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Dubra W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000892/2023-2024 | 1542/PD | 16/10/2023 | 01/12/2025 | MANATOSH SINGH | 47.18 | 8.16 | 17.29 | 60
Total | [13 empty] | 639.1 | 312.36 | 48.88