## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone 1A/II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000124/2023-2024 | 860/PMD | 20/07/2023 | 19/08/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 14.85 | 68.75 | 75
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Raghunathpur-II Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 527/PD | 10/04/2023 | 25/04/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 4.94 | 99.94 | 100
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 75/PD | 17/01/2023 | 17/01/2023 | Resource Division | 14.94 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), Construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001198/2022-2023 | 472/PD | 28/03/2023 | 01/07/2025 | ASHOK KUMAR CHATTERJEE | 360.46 | 166.24 | 46.12 | 30
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying of distribution pipe line ( 90 mm,75mm & 63 mm dia HDPE pipe ) towards Garhpanchkot Prakriti Kendra under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001140/2022-2023 | 418/PD | 21/03/2023 | 05/05/2023 | CHANDAN CHATTERJEE | 10.97 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 500 Cum with other allied works at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001043/2022-2023 | 275/PD | 27/02/2023 | 28/05/2023 | BOSE CONSTRUCTION | 56.66 | 54.62 | 96.4 | 70
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ketlapur Mouza, JL No.-82, Plot No.-2790 under Para Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 767/PD | 08/06/2023 | 07/08/2023 | PARTHA SARATHI SAHABABU | 10.96 | 8.7 | 79.36 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Construction of Guard Room at WTP Campus under Raghunathpur Pipe Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 664/PD | 17/05/2023 | 25/08/2023 | BISWAJIT MAJI | 6.34 | 6.17 | 97.37 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply & delivery of spreading and levelling Filter media at Rapid Gravity sand filter beds after removal of existing not functioning filter media at Laxmanpur WTP under Purulia Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/003455/2023-2024 | 317/PD | 01/03/2024 | 30/04/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 15.86 | 15.83 | 99.84 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Sinking of 1(One) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Boosting Pump Station (Seleta Mouza) of Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003989/2023-2024 | 518/PD | 16/03/2024 | 30/04/2024 | SUBRATA SINGHADEO | 3.87 | 3.71 | 95.72 | 100
11 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | For new connection at Gobag near uposasthya kendra under augmentation of Raghunathpur zone 1A/1 & zone 1A/II |  |  | BILL/00777/2023-2024 | BP-23-24-277 | 01/02/2024 | 01/02/2024 | WBSEDCL PURULIA | 2.81 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001197/2022-2023 | 471/PD | 28/03/2023 | 01/07/2025 | ASHOK KUMAR CHATTERJEE | 261.64 | 163.68 | 62.56 | 80
13 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site - I (Tube Well -Il), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000646/2024-2025 | 1010/PMD | 24/06/2024 | 09/07/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
14 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000610/2024-2025 | 858/PMD | 03/06/2024 | 13/06/2024 | ANUP KUMAR SAHA | 0.94 | 0 | 0 | 95
15 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- I (Tube well-III), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000649/2024-2025 | 1109/PMD | 11/07/2024 | 26/07/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
16 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Road Crossing of rising main by jack pushing at Raghunathpur-Barakar Road (near Bundla Brize) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001174/2024-2025 | 2328/PD | 31/12/2024 | 01/03/2025 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 17.14 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Earthing arrangement and other works, at OHR site Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000606/2024-2025 | 897/PMD | 10/06/2024 | 25/06/2024 | ANUP KUMAR SAHA | 0.7 | 0 | 0 | 95
18 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- I (Tube well-I), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000656/2024-2025 | 916/PMD | 11/06/2024 | 26/06/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
19 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 243.5 cum at Jharukhamar under Raghunathpur W/S Scheme (Zone-IA) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001146/2024-2025 | 2300/PD | 31/12/2024 | 31/03/2025 | ASHOKE KUMAR CHATTERJEE | 5.76 | 0 | 0 | 0
20 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-III) under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000008/2025-2026 | 619/PMD | 22/04/2025 | 12/05/2025 | ANUP KUMAR SAHA | 0.88 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Continuation work order for the work of Trial Run & Maintenance of Distribution system, opening and closing sluice valves with all allied works related to water supply under Raghunathpur W/S Scheme (German Project) Zone-I-A/II of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (w.e.f. 01.05.2025 to 29.06.2025) | Assistant Engineer | Junior Engineer-1 | ORD/000272/2025-2026 | 227/RNP | 30/04/2025 | 29/06/2025 | ASHOKE KUMAR CHATTERJEE | 0.97 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | SM/14669 | Augmentation | Supply & delivery of ferric alum cake & lime for Raghunathpur W/S Project (German Assisted) Lakhanpur W.T.P within Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000349/2025-2026 | 427/RNP | 12/08/2025 | 19/08/2025 | ANUP KUMAR SAHA | 0.9 | 0 | 0 | 0
Total | [13 empty] | 800.79 | 438.74 | 54.79