## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 73/PD | 17/01/2023 |  | Resource Division | 113.38 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Gobag Mouza, JL No.-58, Plot No.-620 under Neturia Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000078/2023-2024 | 768/PD | 08/06/2023 | 07/08/2023 | ASHOK KUMAR CHATTERJEE | 17.28 | 3.86 | 22.34 | 0
3 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone V B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000126/2023-2024 | 862/PMD | 20/07/2023 | 19/08/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 7.42 | 34.37 | 75
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001067/2022-2023 | 302/PD | 28/02/2023 | 29/04/2023 | M/S KARUNAMOYEE CONSTRUCTION | 149.48 | 93.63 | 62.64 | 57
5 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE VB |  |  | BILL/00479/2023-2024 | BP-23-24-250 | 04/01/2024 |  | WBSEDCL PURULIA | 1.18 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line and other alliedworks of Raghunathpur Water Supply Scheme(Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-I] | Assistant Engineer | Junior Engineer | ORD/001006/2022-2023 | 173/PD | 07/02/2023 | 24/03/2023 | MADHU SUDAN RAKSHIT | 83.87 | 66.06 | 78.76 | 75
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur WaterSupply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-II | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 174/PD | 07/02/2023 | 24/03/2023 | RABIN CHANDRA CHAIL | 77.59 | 26.27 | 33.85 | 30
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Land development by earth filling with carried earth , Concrete road & Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell with other allied works of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2024-2025 | 905/PD | 07/05/2024 | 06/07/2024 | AMIT PATHAK | 16.66 | 10.55 | 63.32 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), Construction of 500 cum OHR staging height of 20 mtr and other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/001158/2022-2023 | 433/PD | 22/03/2023 | 17/12/2023 | MS D.PALIT AND CO. | 450.03 | 167.78 | 37.28 | 47
10 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of kiosk box comprising of motor startering arrangement (DOL), at OHR site V(B) (T/W-1) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000565/2023-2024 | 445/PMD | 11/03/2024 | 21/03/2024 | TAPAN KUMAR DEY | 1 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & laying of cable and other works at OHR site- V(B) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000566/2023-2024 | 443/PMD | 11/03/2024 | 21/03/2024 | TAPAN KUMAR DEY | 0.84 | 0 | 0 | 0
12 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Nanduka-V(B) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000564/2023-2024 | 367/PMD. | 01/03/2024 | 11/03/2024 | ASHOKE ADHIKARY | 0.98 | 0.47 | 48.48 | 80
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) |  |  | ORD/000434/2024-2025 | 1498/PD | 27/08/2024 | 11/10/2024 | M/S KARUNAMOYEE CONSTRUCTION | 30.19 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B)(Nanduka) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000439/2024-2025 | 1502/PD | 27/08/2024 | 26/09/2024 | AMIT PATHAK | 5.07 | 2.28 | 44.92 | 100
Total | [13 empty] | 969.14 | 378.33 | 39.04