## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone V B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000126/2023-2024 | 862/PMD | 20/07/2023 | 19/08/2023 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 0 | 75
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 73/PD | 17/01/2023 | 17/01/2023 | Resource Division | 113.38 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line and other alliedworks of Raghunathpur Water Supply Scheme(Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-I] | Assistant Engineer | Junior Engineer | ORD/001006/2022-2023 | 173/PD | 07/02/2023 | 07/02/2026 | MADHU SUDAN RAKSHIT | 83.87 | 0 | 0 | 75
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur WaterSupply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-II | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 174/PD | 07/02/2023 | 31/05/2026 | RABIN CHANDRA CHAIL | 77.59 | 0 | 0 | 30
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Land development by earth filling with carried earth , Concrete road & Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell with other allied works of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2024-2025 | 905/PD | 07/05/2024 | 06/07/2024 | AMIT PATHAK | 16.66 | 0 | 0 | 100
6 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Nanduka-V(B) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000564/2023-2024 | 367/PMD. | 01/03/2024 | 11/03/2024 | ASHOKE ADHIKARY | 0.98 | 0 | 0 | 80
7 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of kiosk box comprising of motor startering arrangement (DOL), at OHR site V(B) (T/W-1) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000565/2023-2024 | 445/PMD | 11/03/2024 | 21/03/2024 | TAPAN KUMAR DEY | 1 | 0 | 0 | 60
8 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & laying of cable and other works at OHR site- V(B) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000566/2023-2024 | 443/PMD | 11/03/2024 | 21/03/2024 | TAPAN KUMAR DEY | 0.84 | 0 | 0 | 60
9 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-V (Tube well-II), Nanduka under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000598/2024-2025 | 1028/PMD | 25/06/2024 | 10/07/2024 | S. PATHAK & CO. | 0.95 | 0 | 0 | 90
10 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B)(Nanduka) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000439/2024-2025 | 1502/PD | 27/08/2024 | 26/09/2024 | AMIT PATHAK | 5.07 | 0 | 0 | 100
11 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Supply, delivery & installation of earthing arrangement and other works at OHR site-V, Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000599/2024-2025 | 1041/PMD | 26/06/2024 | 11/07/2024 | S. PATHAK & CO. | 0.71 | 0 | 0 | 70
12 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE VB |  |  | BILL/00479/2023-2024 | BP-23-24-250 | 04/01/2024 | 04/01/2024 | WBSEDCL PURULIA | 1.18 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001067/2022-2023 | 302/PD | 28/02/2023 | 01/11/2025 | M/S KARUNAMOYEE CONSTRUCTION | 149.48 | 82.73 | 55.34 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Gobag Mouza, JL No.-58, Plot No.-620 under Neturia Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000078/2023-2024 | 768/PD | 08/06/2023 | 01/04/2025 | ASHOK KUMAR CHATTERJEE | 17.28 | 0 | 0 | 65
15 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | SM/14670 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | Assistant Engineer | Junior Engineer-4 | ORD/000434/2024-2025 | 1498/PD | 27/08/2024 | 01/11/2025 | M/S KARUNAMOYEE CONSTRUCTION | 30.19 | 0 | 0 | 100
Total | [13 empty] | 520.76 | 82.73 | 15.89