## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 1521 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Ramchandrrapur W/S Scheme for source augmentation. | Assistant Engineer | Junior Engineer | ORD/000269/2023-2024 | 1090/PD | 10/08/2023 | 26/11/2025 | ANUP KUMAR SAHA | 213.35 | 192.02 | 90 | 70
2 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Construction of appron & other work inconnection with 100 cum CWR at Ramchandrapur WTP (Zone-II) under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000533/2023-2024 | 398/RNP | 05/09/2023 | 20/09/2023 | MADHU SUDAN RAKSHIT | 0.92 | 0.87 | 95.59 | 100
3 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Laying pipe line across railway track near Mouza-Kotaldih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 1530/PD | 16/10/2023 | 15/11/2023 | NIBHAS SINHA | 34.55 | 34.55 | 100 | 100
4 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Laying pipe line across railway track near Mouza-Mijhardih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000881/2023-2024 | 1531/PD | 16/10/2023 | 15/11/2023 | NIBHAS SINHA | 34.09 | 33.68 | 98.79 | 100
5 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Providing indoor and outdoor lighting, making double tank system and other allied works at OHR site at Rangadanga under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000632/2024-2025 | 1552/PMD | 11/11/2024 | 10/01/2025 | SEN BROTHERS | 5.73 | 0 | 0 | 0
6 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply delivery and installation of Voltage stabilizer at New Pump house for Augmentation of Ramchandrapur water supply scheme under PMD PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000633/2024-2025 | 1553/PMD | 11/11/2024 | 09/02/2025 | KOUSHIK CHATTERJEE | 5.99 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply, Delivery, Storage, Installation and Commissioning of Pre Chlorination Arrangement at WTP and High Lift site under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000643/2024-2025 | 1575/PMD | 14/11/2024 | 12/02/2025 | PREMNATH MITRA | 24.94 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply and delivery of Submersible pumping machineries at Augmentation of Ramchandrapur Water Supply Scheme, under Purulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000050/2024-2025 | 969/PMD | 20/06/2024 | 20/07/2024 | COMBINE ENTERPRISES | 1.69 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at New pump house under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000051/2024-2025 | 964/PMD | 20/06/2024 | 18/09/2024 | S S ENTERPRISE | 25.29 | 4.51 | 17.83 | 80
10 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supplying , fitting and fixing Cast Iron heavy type spiral stiar case at Ramchandrapur under Ramchandrapur W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000258/2024-2025 | 1195/PD | 26/06/2024 | 25/08/2024 | MADHU SUDAN RAKSHIT | 2.7 | 2.69 | 99.96 | 100
11 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply delivery and installation of Submersible pump, MS pipe, specials including allied works in connection with direct pumping under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000631/2024-2025 | 1549/PMD | 11/11/2024 | 10/01/2025 | EASTERN INDIA SALES AND SERVICE | 2.58 | 0 | 0 | 100
12 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply delivery and installation of MS pipe, specials including supply and laying of cables including allied works at Intake site under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000625/2024-2025 | 1547/PMD | 11/11/2024 | 10/01/2025 | EASTERN INDIA SALES AND SERVICE | 4.28 | 0 | 0 | 100
13 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | SM/15039 | Augmentation | Supply and installtion of Pressure Shell / Pressure filter (Size- 3000 mm dia X 1800 mm) and laying of HDPE distribution pipe line at Bathanbari under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(SM Code-SM/15039) | Assistant Engineer | Junior Engineer-3 | ORD/000333/2024-2025 | 1358/PD | 25/07/2024 | 24/08/2024 | M/S SAYAK BHATTACHARYA | 48.06 | 34.3 | 71.38 | 65
Total | [13 empty] | 404.16 | 302.62 | 74.88