## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Laying of parallel distribution pipeline to provide FHTC at Supudih Mouza of Bandwan Water Supply Scheme under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/001053/2022-2023 | 285/PD | 27/02/2023 | 13/04/2023 | BANERJEE CONSTRUCTION | 11.66 | 9.85 | 84.5 | 100
2 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Arrangement for high pressure testing of SubStation equipment for 250 KVA Sub - Station at Bundwan w/s Scheme under Purulia Mechanical Division,PHE,Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2024-2025 | 1016/PMD | 25/06/2024 | 25/07/2024 | M S ENTERPRISE | 1.19 | 1.19 | 100 | 100
3 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Different Electro-Mechanical works at Sub-Station at Bundwan under Augmentation of Bundwan Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000041/2024-2025 | 954/PMD | 19/06/2024 | 17/09/2024 | M S ENTERPRISE | 30.22 | 30.14 | 99.71 | 100
4 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 712 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bandwan W/S Scheme for source augmentation | Assistant Engineer | Junior Engineer-3 | ORD/000539/2023-2024 | 1340/PD | 08/09/2023 | 08/03/2024 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 260.9 | 130.45 | 50 | 85
5 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/000338/2024-2025 | 1364/PD | 25/07/2024 | 22/03/2025 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 0 | 50
6 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | SM/15040 | Augmentation | Laying of distribution pipe line at Jitan Mouza (From Morang Culvert to Jitan garden) under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000355/2025-2026 | 424/PSD | 17/07/2025 | 16/08/2025 | ROY CONSTRUCTION | 0.93 | 0 | 0 | 50
Total | [13 empty] | 395.98 | 171.63 | 43.34