## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 421 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bagmundi W/S Scheme for source augmentation | Assistant Engineer | Junior Engineer | ORD/000546/2023-2024 | 1338/PD | 08/09/2023 | 01/10/2026 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 227.9 | 159.53 | 70 | 5
2 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under BAGHMUNDI Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000003/2023-2024 | 524/PD | 10/04/2023 | 25/04/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.16 | 3.92 | 94.2 | 100
3 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Repairing and Renovation of Pump house cum switch room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 1333/PD | 08/09/2023 | 08/10/2023 | S PATHAK AND CO | 2.89 | 2.82 | 97.63 | 100
4 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Bagmundi w/s scheme for under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000227/2023-2024 | 1205/PMD | 03/11/2023 | 02/03/2024 | BISHWANATH NANDI | 7.74 | 7.74 | 100 | 100
5 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply & delivery of electric cable at Bagmundi water supply scheme for Augmentation of Bagmundi PWSS under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000303/2023-2024 | 385/PMSD(W/S) | 17/10/2023 | 01/11/2023 | SEN BROTHERS | 0.92 | 0.92 | 100 | 100
6 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply & delivery of electric cable at Bagmundi water supply scheme for Augmentation of Bagmundi PWSS under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000584/2023-2024 | 373/PMSD(W/S) | 16/10/2023 | 31/10/2023 | SEN BROTHERS | 0.36 | 0.36 | 100 | 100
7 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply & fitting fixing of Main switch, valve and other electro-mechanical accessories at WTP site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000057/2024-2025 | 975/PMD | 20/06/2024 | 19/08/2024 | SUBRATA DUTTA | 3.98 | 0 | 0 | 100
8 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery, Voltage stabilizer with other allied work for direct pumping at OHR site of Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000109/2024-2025 | 1173/PMD | 31/07/2024 | 21/11/2025 | PINTU DEY | 29.04 | 0 | 0 | 25
9 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply & fitting fixing of Main switch, valve and other electro-mechanical accessories at OHR site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000060/2024-2025 | 989/PMD | 21/06/2024 | 20/08/2024 | PINTU DEY | 1.55 | 1.52 | 97.91 | 100
10 | PURULIA |  | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Construction of pathway at OHR Site of Bugmundi W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003458/2023-2024 | 332/PD | 01/03/2024 | 15/04/2024 | ROY CONSTRUCTION | 2.21 | 2.21 | 99.88 | 100
11 | PURULIA |  | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | SM/15041 | Augmentation | Supply, delivery & installation of Monorail, Lighting conductor & others allied work at WTP site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000619/2024-2025 | 1541/PMD | 11/11/2024 | 09/04/2025 | SAIBAL SARKAR | 4.25 | 0 | 0 | 100
Total | [13 empty] | 285.01 | 179.02 | 62.81