## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Bagmundi | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/15380 | New | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Baghmundi Block [37 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000044/2022-2023 | 100/A/PSD | 08/02/2023 | 01/03/2023 | INDRANIL DUTTA & ASSOCIATES | 4.83 | 3.49 | 72.25 | 60
Total | [13 empty] | 4.83 | 3.49 | 72.25