## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 15m3 including ventury etc. complete at Eklabya Model School Campus, Susunia Manbazar II Block of Manbazar II Block(part) W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 1632/PD | 03/11/2022 | 11/02/2023 | ROY CONSTRUCTION | 4.81 | 4.04 | 83.98 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Guarding arrangement through Registered firm organized by Ex-Military person for WTP site of surface water supply scheme for Manbazar-II Block (Part) under Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | Assistant Engineer |  | ORD/000503/2021-2022 | 531/2/PD | 30/03/2022 | 29/04/2022 | FRONTLINE EX-SERVICEMEN BUREAU | 1.4 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | 1. Identification of parallel distribution pipeline & loop pipeline including preparation of drawing & other allied works to cater the water supply problem in household tap connections at manbazar-II block under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001087/2022-2023 | 355/PD | 14/03/2023 | 13/04/2023 | M/S. DESTINY CONSTRUCTION | 9.54 | 9.23 | 96.75 | 25
4 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 528/PD | 11/04/2023 | 11/04/2023 | Resource Division | 644.45 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on Boro-Jamtoria Road in respect of Augumentation of Manbazar-II water supply scheme JJM in District of Purulia. |  |  | BILL/01013/2023-2024 | BP-2023-24-664 | 10/11/2023 | 10/11/2023 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 6.02 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000614/2022-2023 | 511/PSD | 12/08/2022 | 26/09/2022 | SADHAN GORAIN | 2.43 | 2.09 | 85.98 | 100
7 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Laying of Dedicated distribution pipe line For Paisagora under command area Zone-II under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | Assistant Engineer | Junior Engineer-3 | ORD/000872/2022-2023 | 1840/PD | 12/12/2022 | 26/01/2023 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 32.63 | 31.52 | 96.61 | 100
8 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Conducting reconnaissance of feasible check dam site fo empounding reservoir site over rivers, recommending pinpoint site, conducting contour, longitudinal and traverse level survey on waterways and ponds with all geo reference, submission of report to E-I-C for preparation hydro graphic survey map of intake site at mukutmanipur dam & contour map of proposed WTP site of southern sector at Manbazar - II Block under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/001097/2022-2023 | 364/PD | 14/03/2023 | 13/04/2023 | LEMNISCATE | 11.16 | 10.34 | 92.63 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(From Zone-II OHR to Dhabakata village,Jaragora village Via Boro Mor) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/001213/2022-2023 | 502/PD | 31/03/2023 | 15/05/2023 | PRIYATOSH MUKHERJEE | 94.15 | 81.67 | 86.75 | 100
10 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(Part-II- FromZ-II OHR to Dangardi,Boro PS to Joypur-Chotokadam-Dhadangar Mudipara, Dharampur Namopara, Goialapara Via Rampu Mahato Para) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/001214/2022-2023 | 503/PD | 31/03/2023 | 15/05/2023 | MS D.PALIT AND CO. | 85.65 | 80.16 | 93.59 | 100
11 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | Assistant Engineer | Junior Engineer-3 | ORD/000009/2023-2024 | 537/PD | 12/04/2023 | 27/05/2023 | MOONLIGHT HOUSE | 29.2 | 18.23 | 62.44 | 100
12 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte - i)FromBasantapur mor to Jugiadih village ii) Panra Morto Uppar pannra & Choto Pannra),Olgara, Kumari,) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000010/2023-2024 | 538/PD | 12/04/2023 | 27/05/2023 | RAKSHIT ENTERPRISE | 25.94 | 24.28 | 93.58 | 100
13 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Shifting and laying of HDPE distribution main pipeline from Burudi more to Dharampur village end due to widening of PWD road at Manbazar-2 block under Manbazar-II Water Supply Scheme Under Purulia Division ,PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000047/2023-2024 | 671/PD | 17/05/2023 | 16/07/2023 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 41.18 | 34.4 | 83.53 | 100
14 | PURULIA |  | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | SM/15936 | Augmentation | Day-to-day operation and maintenance of 350 Cum capacity OHR and distribution system of Zone - II of surface water based water supply scheme for Manbazar - II Block (Part) under Purulia Sadar Sub-Division, PHE Dte. [For the period of 01.09.2025 to 31.08.2026] | Assistant Engineer | Junior Engineer-3 | ORD/000514/2025-2026 | 1703/PD | 29/08/2025 | 29/08/2026 | ROY CONSTRUCTION | 11.58 | 0 | 0 | 30
Total | [13 empty] | 1000.15 | 295.96 | 29.59