## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VII B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000044/2023-2024 | 450/PMD | 20/04/2023 | 20/05/2023 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 21.59 | 12.92 | 59.85 | 65
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 76/PD | 17/01/2023 | 17/01/2023 | Resource Division | 65.11 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Laying Distribution System including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII B) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 530/PD | 11/04/2023 | 10/06/2023 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 280.39 | 165.25 | 58.93 | 48
4 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B under Purulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000584/2024-2025 | 1443/PMD | 01/10/2024 | 30/11/2024 | M/S A.D. CONCERN | 3.87 | 0 | 0 | 0
5 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | For new connection of Augmentation of Raghunathpur zone VII B |  |  | BILL/00776/2023-2024 | BP-23-24-278 | 01/02/2024 | 01/02/2024 | WBSEDCL PURULIA | 0.26 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Laying of Distribution System including providing Functional Household Tap Connection (FHTC), Construction of 350 cum OHR and staging height of 20 mtr. and other other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone - VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 583/PD | 20/04/2023 | 15/01/2024 | PRAVAT SARKAR | 321.22 | 215.54 | 67.1 | 78
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Laying Distribution System of pipe line from Borsolia culvert to Sagarka more & Danduya Village including providing House Hold Tap Connection (FHTC)other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone -VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | Assistant Engineer | Junior Engineer-4 | ORD/000491/2024-2025 | 1708/PD | 05/09/2024 | 01/01/2026 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 51.67 | 0 | 0 | 0
8 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Ketlapur of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000609/2024-2025 | 857/PMD | 03/06/2024 | 13/06/2024 | ANUP KUMAR SAHA | 0.64 | 0 | 0 | 95
9 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-l (Tube Well -I), of Ketlapur (Z-VIIB) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000636/2024-2025 | 915/PMD | 11/06/2024 | 26/06/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
10 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Earthing arrangement and other works, at OHR site Ketlapur of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000608/2024-2025 | 905/PMD | 10/06/2024 | 25/06/2024 | ANUP KUMAR SAHA | 0.4 | 0 | 0 | 95
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) |  |  | ORD/000656/2024-2025 | 1875/PD | 01/10/2024 | 15/11/2024 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 21.26 | 0 | 0 | 0
12 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Ketlapur (Z-VIIB)(Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000654/2024-2025 | 1029/PMD | 25/06/2024 | 10/07/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
13 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | SM/16379 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-IV) under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000009/2025-2026 | 620/PMD | 22/04/2025 | 12/05/2025 | ANUP KUMAR SAHA | 0.88 | 0 | 0 | 0
Total | [13 empty] | 768.92 | 393.72 | 51.2