## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. | SM/17197 | Support-WQMSP | Renovation and Maintenance work of Balarampur Water Treatment Plant labrotary. |  |  | ORD/000136/2024-2025 | 906/PD | 07/05/2024 | 06/07/2024 | SAW CONSTRUCTION | 2.99 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. | SM/17197 | Support-WQMSP | Renovation and Repairing including Electrical and Sanitary Plumbing works of Joypur Sub Distict Laboratoty for NABL Accreditation, Part-B | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 835/PD | 26/06/2023 | 25/08/2023 | M/S KHAN ENTERPRISE | 6.22 | 0 | 0 | 100
3 | PURULIA |  | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. | SM/17197 | Support-WQMSP | Construction & Extension of additional building of Sirkabad sub district lab under Purulia R.W.S Subdivision under Purulia Division P.H.E. Dte. |  |  | ORD/000659/2024-2025 | 1899/PD | 04/10/2024 | 03/12/2024 | KABERI DUTTA | 3.26 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. | SM/17197 | Support-WQMSP | Construction and extension of additional building of Shirkabad sub dist lab.Under Purulia R.W.S Sub-Division ubder Purulia Division P.H.E Dte. |  |  | ORD/000660/2024-2025 | 1898/PD | 04/10/2024 | 03/12/2024 | KABERI DUTTA | 3.8 | 0 | 0 | 0
Total | [13 empty] | 16.27 | 0 | 0