## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 77/PD | 17/01/2023 | 17/01/2023 | Resource Division | 4.22 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone II B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000121/2023-2024 | 802/PMD | 12/07/2023 | 11/08/2023 | A G ENTERPRISE | 21.84 | 0 | 0 | 85
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur W/S (Zone-VI-B) at Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000354/2024-2025 | 1382/PD | 25/07/2024 | 23/10/2024 | SOUVIK MANDAL | 92.92 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of Substation Building at Boosting station (Seleta mouza) under Raghunathpur water supply scheme and Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000379/2024-2025 | 1402/PD | 25/07/2024 | 02/01/2026 | SUBRATA SINGHADEO | 40.98 | 0 | 0 | 75
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of Guard Room with toilet block at Zone-IIA under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001040/2024-2025 | 2100/PD | 05/12/2024 | 03/02/2025 | PURNA CHANDRA TEWARI | 6.42 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, hi-lifting boundary wall and other allied works under Raghunathpur W/S Scheme (Zone-II-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001118/2024-2025 | 2190/PD | 13/12/2024 | 13/03/2025 | DILIP MISHRA | 12.66 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of Guard Room with toilet block at Zone-IIB under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001041/2024-2025 | 2101/PD | 05/12/2024 | 03/02/2025 | CHANCHAL MISHRA | 6.43 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of 1 No. Secondary Pannel cum meter Room at Lakhanpur W.T.P. near Intake Bridge under Raghunathpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 883/PD | 03/07/2023 | 02/08/2023 | CHANDAN CHATTERJEE | 6.78 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-II-B (Khajura) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/001361/2023-2024 | 1730/PD | 04/12/2023 | 01/06/2024 | MAA TARA CONSTRUCTION | 4.86 | 0 | 0 | 100
10 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE IIB |  |  | BILL/00478/2023-2024 | BP-23-24-248 | 04/01/2024 | 04/01/2024 | WBSEDCL PURULIA | 2.87 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Construction of Rcc Over Head Reservoir (Torch type with solid raft)of capacity 150 cum and staging heght 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC)and other alliedworks for Aug. work of Raghunathpur Watersupply scheme (German Assisted) (Zone-II B) within Raghunathpur Sub-Division under Purulia Division,PHE Dte.(SL-4) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000555/2023-2024 | 1337/PD | 08/09/2023 | 02/10/2025 | MANIRUL ISLAM SK | 261.26 | 0 | 0 | 63
12 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-II B) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/001145/2024-2025 | 2299/PD | 31/12/2024 | 30/06/2025 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 78.64 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Addition of column pipe including supply along with allied works, at OHR site-II B, Khajura under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000016/2025-2026 | 635/PMD | 24/04/2025 | 09/05/2025 | ANUP KUMAR SAHA | 0.37 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC), and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IIA)within Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-3) | Assistant Engineer | Junior Engineer | ORD/000266/2023-2024 | 1020/PD | 01/08/2023 | 31/05/2025 | ANUP KUMAR SAHA | 401.92 | 0 | 0 | 100
15 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Earthing arrangement and other works, at OHR site Uporkhajura of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000605/2024-2025 | 899/PMD | 10/06/2024 | 25/06/2024 | ANUP KUMAR SAHA | 0.5 | 0 | 0 | 90
16 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | SM/18250 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000655/2024-2025 | 1027/PMD | 25/06/2024 | 10/07/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
Total | [13 empty] | 943.47 | 0 | 0