## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VI B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000122/2023-2024 | 803/PMD | 12/07/2023 | 11/08/2023 | MERCURY ENGINEERING COMPANY | 21.6 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 74/PD | 17/01/2023 | 17/01/2023 | Resource Division | 1.75 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIA) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-8) | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 1041/PD | 04/08/2023 | 01/04/2025 | DEBAKI RANJAN SARKAR | 310.01 | 0 | 0 | 60
4 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-VIB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-9) | Assistant Engineer | Junior Engineer | ORD/000268/2023-2024 | 1021/PD | 01/08/2023 | 27/04/2024 | SWAPAN MANDAL | 280.53 | 0 | 0 | 35
5 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-VI B (Babugram) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001360/2023-2024 | 1729/PD | 04/12/2023 | 13/03/2024 | SAANVI CONSTRUCTION | 4.81 | 0 | 0 | 100
6 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Quotation for new service connection at Zone-VI OHR(Babugram) site under Raghunathpur Aug. water supply scheme. |  |  | BILL/00288/2024-2025 | BP-24-25-75 | 02/08/2024 | 02/08/2024 | WBSEDCL PURULIA | 6.21 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Repairing & Renovation of Existing Rising Main and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL No.4) | Assistant Engineer | Junior Engineer | ORD/000904/2023-2024 | 1578/PD | 30/10/2023 | 30/01/2026 | ANUP KUMAR SAHA | 300.79 | 0 | 0 | 65
8 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 278 cum and other allied works under Raghunathpur W/S Scheme (Zone-VI-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001167/2024-2025 | 2321/PD | 31/12/2024 | 31/05/2026 | CHAIL CONSTRUCTION | 11.41 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Repairing of DI Rising Main, construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(One) no tubewell at OHR Sites of (Zone - VI B) of Raghunathpur Water Supply Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 180 m) | Assistant Engineer | Junior Engineer-4 | ORD/000336/2024-2025 | 1362/PD | 25/07/2024 | 01/01/2026 | BASANTA KUMAR SINGHADEO | 24.88 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-I), under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000965/2024-2025 | 517/PMD | 28/03/2025 | 17/04/2025 | SUJIT MUKHERJEE | 0.99 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | SM/18306 | Augmentation | Addition of column pipe including supply along with allied works at OHR site-VII B, Ketlapur under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000014/2025-2026 | 634/PMD | 24/04/2025 | 09/05/2025 | ANUP KUMAR SAHA | 0.49 | 0 | 0 | 0
Total | [13 empty] | 963.47 | 0 | 0