## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Conducting route survey & investigation of command area map along the road fixing up alignment including showing existing distribution and Rising Main net works,all structures and features at Barabazar Leftout portion under PMU, WBPWSP (Purulia), PHE Dte. |  |  | ORD/000008/2022-2023 | 1300/W-181/JICA/PMU/2013 | 12/07/2022 | 27/07/2022 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 0 | 0 | 100
2 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 100 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-II water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I (C) ,Assistant Engineer-I(C) | JE-I Civil | ORD/000017/2023-2024 | 2347/W-181/JICA/PMU/2022 | 09/08/2023 | 20/01/2027 | M/S S & P CONSTRUCTION | 218.93 | 67.63 | 30.89 | 82
3 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Laying of Rising Main cum Transmission Main for The Piped Water Supply Scheme for Left-Out Mouzas of Barabazar Block, Dist. Purulia under West Bengal Project Management Unit, Purulia, PHE Dte. | Assistant Engineer-I(C) | JE-I Civil | ORD/000018/2023-2024 | 2348/W-181/JICA/PMU/2022 | 09/08/2023 | 21/11/2026 | M/S S & P CONSTRUCTION | 247.24 | 42.94 | 17.37 | 86
4 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000021/2023-2024 | 2392/W-181/JICA/PMU/2022 | 10/08/2023 | 20/07/2026 | ANUP KUMAR SAHA | 26.46 | 0 | 0 | 0
5 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-I water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-II Civil | ORD/000023/2023-2024 | 2351/W-181/JICA/PMU/2022 | 09/08/2023 | 25/04/2026 | SANTANU BANERJEE | 459.23 | 0 | 0 | 80
6 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -I, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000011/2023-2024 | 2386/W-181/JICA/PMU/2022 | 10/08/2023 | 10/02/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.42 | 0 | 0 | 0
7 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 150 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-IV water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-I Civil | ORD/000019/2023-2024 | 2349/W-181/JICA/PMU/2022 | 09/08/2023 | 24/07/2026 | PARTHA PRATIM CHHATAIT | 217.07 | 0 | 0 | 40
8 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -V, OHR Under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000015/2023-2024 | 2390/W-181/JICA/PMU/2022 | 10/08/2023 | 04/07/2025 | M/S SAJAHAN CHOWDHURY | 26.44 | 0 | 0 | 0
9 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VI, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000016/2023-2024 | 2391/W-181/JICA/PMU/2022 | 10/08/2023 | 04/08/2024 | COMBINE ENTERPRISE | 26.46 | 0 | 0 | 0
10 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Providing Mechanical / Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Substation, Gaseous Chlorination, illumination arrangement at Intermediate Booster Pumping Station - I of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-II (M/E),Assistant Engineer-II(M/E) | Sub Assistant Engineer-II (M/E),Sub-Assistant Engineer-II (M/E) | ORD/000026/2023-2024 | 2394/W-181/JICA/PMU/2022 | 10/08/2023 | 28/04/2027 | EASTERN INDIA SALES & SERVICE | 334.6 | 0 | 0 | 22
11 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VI water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-I Civil | ORD/000030/2023-2024 | 2354/W-181/JICA/PMU/2022 | 09/08/2023 | 24/07/2026 | PRINCE INDUSTRIES ( INDIA) | 429.21 | 0 | 0 | 75
12 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VIII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000022/2023-2024 | 2393/W-181/JICA/PMU/2022 | 10/08/2023 | 11/01/2025 | TAPAN KUMAR DEY | 26.44 | 0 | 0 | 0
13 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Providing Yard Lighting and other related works at OHRs for Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Junior Engineer- (M/E),Junior Engineer (M/E) | ORD/000031/2023-2024 | 2402/W-181/JICA/PMU/2022 | 11/08/2023 | 11/02/2026 | PROGRESSIVE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 30.85 | 0 | 0 | 0
14 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -IV, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000014/2023-2024 | 2389/W-181/JICA/PMU/2022 | 10/08/2023 | 12/01/2025 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT. LTD. | 26.46 | 0 | 0 | 0
15 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-II Civil | ORD/000025/2023-2024 | 2353/W-181/JICA/PMU/2022 | 09/08/2023 | 24/07/2026 | S.DUTTA | 464.97 | 0 | 0 | 50
16 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -II, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000012/2023-2024 | 2387/W-181/JICA/PMU/2022 | 10/08/2023 | 23/01/2025 | TAPAN KUMAR DEY | 26.44 | 0 | 0 | 84
17 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-III water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-II Civil | ORD/000028/2023-2024 | 2405/W-181/JICA/PMU/2022 | 11/08/2023 | 26/07/2026 | DEBAKI RANJAN SARKAR | 524.57 | 0 | 0 | 30
18 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of 600 cum capacity CWR, 75 cum capacity CWR, 1 no of Sub-station Building, 2 nos of Pump Houses & Boundary Wall of CWRs of water supply scheme of left-out mouzas of Barabazr under West Bengal Project Management Unit, Purulia, PHE Dte. | Assistant Engineer-I(C) | JE-II Civil | ORD/000020/2023-2024 | 2350/W-181/JICA/PMU/2022 | 09/08/2023 | 24/07/2026 | SAMAN KUMAR MAHATO | 184.49 | 0 | 0 | 40
19 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -III, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Sub Assistant Engineer-I (M/E),Sub-Assistant Engineer-I (M/E) | ORD/000013/2023-2024 | 2388/W-181/JICA/PMU/2022 | 10/08/2023 | 21/01/2025 | SUBRATA DUTTA | 26.46 | 0 | 0 | 0
20 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 400 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VIII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I (C) ,Assistant Engineer-I(C) | JE-I Civil | ORD/000029/2023-2024 | 2406/W-181/JICA/PMU/2022 | 11/08/2023 | 26/07/2026 | ANUP KUMAR SAHA | 658.94 | 0 | 0 | 75
21 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-V water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | Assistant Engineer-I(C) | JE-II Civil | ORD/000024/2023-2024 | 2352/W-181/JICA/PMU/2022 | 09/08/2023 | 24/07/2026 | NIBHAS SINHA | 465.39 | 0 | 0 | 82
22 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Providing Mechanical/ Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Gaseous Chlorination, Illumination arrangement at Intermediate Booster Pumping Station - II of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | Assistant Engineer-I (M/E),Assistant Engineer-I(M/E) | Junior Engineer- (M/E),Junior Engineer (M/E) | ORD/000027/2023-2024 | 2401/W-181/JICA/PMU/2022 | 11/08/2023 | 29/01/2025 | RABINDRA NATH KHAN | 102.5 | 0 | 0 | 40
23 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Soil investigation for determining the safe bearing capacity and other relevant parameters of soil in 8 nos different OHR site & 2 nos CWR site of surface Water Based Piped water Supply Scheme for left out mouzas of Barabazar Block,Purulia under JICA Assisted WBPWSP(P), PHE DTE | Assistant Engineer-I(C) | JE-II Civil | ORD/000037/2023-2024 | 2523/W-181/JICA/PMU/2022 | 22/08/2023 | 16/12/2023 | MABCO CONSULTANT | 7.24 | 0 | 0 | 100
24 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 2147/W-181/JICA/PMU/2013 | 26/07/2023 | 26/07/2023 | Resource Division | 91.65 | 0 | 0 | 0
25 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 2068/W-34/JICA/PMU/2013 | 24/07/2023 | 24/07/2023 | Resource Division | 2368.36 | 0 | 0 | 0
26 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1001/W-181/JIC/PMU/2022 | 30/04/2024 | 30/04/2024 | Resource Division | 194.9 | 0 | 0 | 0
27 | PURULIA | Barabazar | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme | SM/18319 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 594/W-181/JICA/PMU/2022 | 06/03/2024 | 06/03/2024 | Resource Division | 38.92 | 0 | 0 | 0
Total | [13 empty] | 7255.27 | 110.56 | 1.52