## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | SM/18333 | New | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Executive Engineer, Purulia Mechanical Division PHE, Dte. (01/10/24 to 31/03/25) |  | JUNIOR ENGINEER | ORD/000615/2024-2025 | 400/PMSD(W/S) | 23/09/2024 | 24/03/2025 | TAPAN KUMAR DEY | 0.86 | 0 | 0 | 0
2 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | SM/18333 | New | Continuation work order for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Division, PHE Dte. (w.e.f.01.09.2023 to 31.08.2024.) | Assistant Engineer | Junior Engineer | ORD/004200/2023-2024 | 477/A/PR | 31/08/2023 | 31/08/2024 | ANUP KUMAR SAHA | 1.76 | 0 | 0 | 0
3 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | SM/18333 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - III, IV & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000221/2025-2026 | 1086/PD | 17/06/2025 | 15/10/2025 | RANI SATI CONSTRUCTION | 43.06 | 0 | 0 | 0
Total | [13 empty] | 45.68 | 0 | 0