## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Details survey of WTP site as well as intake site to ascertion depth and area basin at Shiulibari Mouza, Nituria Block under Northern Zone W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 549/PD | 12/04/2023 | 12/05/2023 | ROY CHOWDHURY ASSOCIATES | 5.39 | 5.38 | 99.76 | 100
2 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 1904/PD | 21/10/2024 | 21/10/2024 | Resource Division | 66.57 | 0 | 0 | 0
3 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Electric quotation along with M.B No1200/PMD for payment of shifting of 11KV PHE feeder & 11 KV Rampur feeder from Northern Sector WTP Campus for payment from your end. |  |  | BILL/01971/2023-2024 | BP-2023-24-889 | 18/03/2024 | 18/03/2024 | WBSEDCL | 45.82 | 0 | 0 | 0
4 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | Assistant Engineer | Junior Engineer,Junior Engineer-2 | ORD/000895/2023-2024 | 1560/PD | 18/10/2023 | 01/01/2027 | RAJ BROTHERS | 264.65 | 100.42 | 37.95 | 22
5 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Assistant Engineer, Purulia Mechanical Sub-Division (W/S) PHE, Dte. (01/10/24 to 31/03/25) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000614/2024-2025 | 399/PMSD(W/S) | 23/09/2024 | 24/03/2025 | PINTU DEY | 0.86 | 0.43 | 49.87 | 0
6 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - V & VI of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 270 m). | Assistant Engineer | Junior Engineer-4 | ORD/001825/2023-2024 | 63/PD | 10/01/2024 | 28/02/2025 | SUBHAS CHANDRA MAHATO | 37.7 | 15.83 | 41.99 | 100
Total | [13 empty] | 421 | 122.06 | 28.99