## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-III & IV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 3) | Assistant Engineer | Junior Engineer-3 | ORD/000765/2023-2024 | 1371/PD | 14/09/2023 | 16/04/2026 | ANUP KUMAR SAHA | 671.47 | 0 | 0 | 40
2 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 12) | Assistant Engineer | Junior Engineer | ORD/000762/2023-2024 | 1368/PD | 14/09/2023 | 05/06/2026 | ANUP KUMAR SAHA | 449.89 | 83.16 | 18.48 | 70
3 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL - 4) | Assistant Engineer | Junior Engineer | ORD/000764/2023-2024 | 1370/PD | 14/09/2023 | 01/09/2026 | SAMAN KUMAR MAHATO | 184.53 | 61.12 | 33.12 | 40
4 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-X & XI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 7) | Assistant Engineer | Junior Engineer | ORD/000763/2023-2024 | 1369/PD | 14/09/2023 | 05/06/2026 | ANUP KUMAR SAHA | 854.21 | 287.44 | 33.65 | 70
5 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-V & VI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 4) | Assistant Engineer | Junior Engineer-3 | ORD/000761/2023-2024 | 1367/PD | 14/09/2023 | 20/07/2025 | ANUP KUMAR SAHA | 647.66 | 0 | 0 | 0
6 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Opearation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector ) under Purulia Divn. PHE Dte. (SL-11) | Assistant Engineer | Junior Engineer-3 | ORD/000777/2023-2024 | 1419/PD | 29/09/2023 | 05/12/2025 | MS D.PALIT AND CO. | 400.45 | 64.67 | 16.15 | 10
7 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL-2) | Assistant Engineer | Junior Engineer | ORD/000781/2023-2024 | 1421/PD | 29/09/2023 | 05/12/2025 | MS D.PALIT AND CO. | 478.83 | 119.57 | 24.97 | 75
8 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte. (SL-8) | Assistant Engineer |  | ORD/000801/2023-2024 | 1431/PD | 29/09/2023 | 25/06/2024 | MD AAMIR KHAN | 552.37 | 0 | 0 | 0
9 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the peroid of thirty six (36) month at Zone- VII & VIII of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 3) | Assistant Engineer | Junior Engineer-3 | ORD/000797/2023-2024 | 1430/PD | 29/09/2023 | 13/09/2026 | ANUP KUMAR SAHA | 649.84 | 203.63 | 31.34 | 55
10 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1128/PD | 17/08/2023 | 17/08/2023 | Resource Division | 8279.54 | 0 | 0 | 0
11 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XIV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (3rd Call) | Assistant Engineer | Junior Engineer-3 | ORD/002260/2023-2024 | 146/PD | 29/01/2024 | 12/12/2032 | ANUP KUMAR SAHA | 247.75 | 0 | 0 | 10
12 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Design, Surveying,Engineering, Supplying and Construction, Erection, Installation, Testing,Commissioning, of Fixed type Intake Jetty with Pump house, Construction of Sub-station; Raw Water Raising Main Bank Protection, 40 MLD (Minimum) capacity Water Treatment Plant (WTP) based on conventional technologies + 20% overloading; Clear Water Pumping Mains, Booster Stations (11 numbers) at Arsha, Baghmundi, Balarampur, Bandwan, Manbazar I (part), Manbazar II & Purulia I (Part) Blocks including pumping machineries on EPC/ Turnkey basis in a single package including 3 (three) months Trial Run and Operation & Maintenance for 3 years for Surface Based W/S scheme for Southern Sector under Purulia Distric. | Assistant Engineer | Junior Engineer,Junior Engineer-1,Junior Engineer-3 | ORD/001820/2023-2024 | 53/PD | 09/01/2024 | 08/10/2027 | WPIL LIMITED | 32180 | 241.35 | 0.75 | 15
13 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VI) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000205/2024-2025 | 902/PD | 07/05/2024 | 01/10/2026 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 94.42 | 0 | 0 | 0
14 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-X) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000486/2024-2025 | 1073/PD | 07/06/2024 | 06/08/2024 | SAIKAT RAY | 95.21 | 0 | 0 | 0
15 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. (Ajodhya Hill Area) | Assistant Engineer | Junior Engineer-2 | ORD/000230/2024-2025 | 1065/PD | 07/06/2024 | 02/06/2026 | VIVEKANANDA CONSTRUCTION | 94.95 | 0 | 0 | 35
16 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000095/2024-2025 | 1053/PMD | 28/06/2024 | 28/06/2025 | DAS ENTERPRISE | 50.63 | 0 | 0 | 0
17 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000096/2024-2025 | 1054/PMD | 28/06/2024 | 28/06/2025 | M/S S.G.ENTERPRISE | 31.65 | 0 | 0 | 0
18 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2024-2025 | 1055/PMD | 28/06/2024 | 28/06/2025 | ANUP KUMAR SAHA | 50.65 | 0 | 0 | 0
19 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000514/2023-2024 | 516/PMD | 15/03/2024 | 15/03/2025 | GOENKA ENTERPRISE | 258.09 | 0 | 0 | 0
20 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000515/2023-2024 | 517/PMD | 15/03/2024 | 15/03/2025 | SINHA ELECTRICALS | 206.55 | 0 | 0 | 0
21 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000519/2023-2024 | 480/PMD | 14/03/2024 | 14/03/2025 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 69.58 | 0 | 0 | 0
22 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000518/2023-2024 | 479/PMD | 14/03/2024 | 14/03/2025 | SUBRATA DUTTA | 69.61 | 0 | 0 | 0
23 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000521/2023-2024 | 482/PMD | 14/03/2024 | 14/03/2025 | M/S D.G.B.ENTERPRISE | 39.77 | 0 | 0 | 0
24 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000513/2023-2024 | 515/PMD | 15/03/2024 | 15/03/2025 | COMBINE ENTERPRISES | 154.79 | 0 | 0 | 0
25 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000341/2024-2025 | 1367/PD | 25/07/2024 | 01/04/2025 | KOUSHIK CHATTERJEE | 20.13 | 0 | 0 | 0
26 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000520/2023-2024 | 481/PMD | 14/03/2024 | 14/03/2025 | RABINDRA NATH KHAN | 109.36 | 0 | 0 | 0
27 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000098/2024-2025 | 1056/PMD | 28/06/2024 | 28/06/2025 | RABINDRA NATH KHAN | 25.32 | 0 | 0 | 0
28 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Araea) | Assistant Engineer | Junior Engineer-2 | ORD/000259/2024-2025 | 1071/PD | 07/06/2024 | 03/08/2026 | SHREYA ENTERPRISES | 94.55 | 0 | 0 | 0
29 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000204/2024-2025 | 901/PD | 07/05/2024 | 03/08/2026 | M/S ANMOL ENGICON | 96.02 | 0 | 0 | 0
30 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IX) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Area) | Assistant Engineer | Junior Engineer-2 | ORD/000220/2024-2025 | 1072/PD | 07/06/2024 | 03/08/2026 | SAROJ KUMAR SINGH | 96.58 | 0 | 0 | 0
31 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000221/2024-2025 | 1095/PD | 07/06/2024 | 06/08/2024 | SUBRATA MAHAPATRA | 25.01 | 0 | 0 | 0
32 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000674/2024-2025 | 1680/PMD | 05/12/2024 | 05/12/2025 | SUBRATA DUTTA | 3.88 | 0 | 0 | 0
33 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000203/2024-2025 | 900/PD | 07/05/2024 | 01/10/2026 | STABILITY INFRASTRUCTURE PVT. LTD. | 96.08 | 0 | 0 | 0
34 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of New Boundary wall and other allied works at Manbazar Riversite (Harekishtapur) under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000236/2024-2025 | 1077/PD | 07/06/2024 | 06/08/2024 | CHANDAN CHATTERJEE | 31.23 | 0 | 0 | 0
35 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000675/2024-2025 | 1681/PMD | 05/12/2024 | 05/12/2025 | S. PATHAK & CO. | 3.88 | 0 | 0 | 0
36 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000676/2024-2025 | 1682/PMD | 05/12/2024 | 05/12/2025 | RABINDRA NATH KHAN | 6.1 | 0 | 0 | 0
37 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000677/2024-2025 | 1683/PMD | 05/12/2024 | 05/12/2025 | PINTU DEY | 2.22 | 0 | 0 | 0
38 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte.(2nd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000701/2024-2025 | 1740/PMD | 16/12/2024 | 16/12/2025 | R.N.S. TRADING | 470.76 | 0 | 0 | 0
39 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/11/24 to 30/04/25) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,JUNIOR ENGINEER (MECHANICAL) | ORD/000779/2024-2025 | 473/PMSD(Drilling) | 24/09/2024 | 24/03/2025 | NUPUR CHANDRA HALDER | 0.86 | 0.36 | 41.44 | 0
40 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of branch pipeline & parallel pipeline over existing pipeline from Burudi More to Dharampur to providing existing FHTC due to widening of PWD road under Purulia water supply scheme (Southern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000237/2024-2025 | 1083/PD` | 07/06/2024 | 06/08/2024 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 7.64 | 0 | 0 | 100
41 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003527/2023-2024 | 353/PD | 04/03/2024 | 03/05/2024 | PRIYATOSH MUKHERJEE | 20.95 | 5.41 | 25.85 | 100
42 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Internal and external illumination with other allied works at Satra high lift(Boosting station) and low lift for augmentation of Satra water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000567/2024-2025 | 1357/PMD | 12/09/2024 | 11/11/2024 | GOLAP KR. GHOSH | 4.88 | 0 | 0 | 100
43 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 1979/PD | 18/11/2024 | 18/11/2024 | Resource Division | 8491.44 | 0 | 0 | 0
44 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000040/2024-2025 | 2254/PD | 19/12/2024 | 19/12/2024 | Resource Division | 5956.59 | 0 | 0 | 0
45 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 290/PD | 03/03/2025 | 03/03/2025 | Resource Division | 4561.24 | 0 | 0 | 0
46 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Payment of Quotation for New Connection at BPS-2 (NORTHERN SECTOR) under Kashipur Block (Application Id: 2005087354) vide memo no. 2005087354/Quot/03/163 dated 16/05/2025 for Demand: 350 KVA. |  |  | BILL/00143/2025-2026 |  | 23/05/2025 | 23/05/2025 | WBSEDCL PURULIA | 53.59 | 0 | 0 | 0
47 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Payment of Quotation for New Connection at CWR-1 (BUNDWAN) under BUNDWAN Block (Application Id: 2005087590) vide memo no. 2005087590/Quot/03/74 dated 28/04/2025 for Demand: 289 KVA |  |  | BILL/00141/2025-2026 |  | 23/05/2025 | 23/05/2025 | WBSEDCL PURULIA | 33.77 | 0 | 0 | 0
48 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Payment of Quotation for New Connection at BPS-1 (SOUTHERN SECTOR) under MANBAZAR-II Block (Application Id: 2005087730) vide memo no. 2005087730/Quot/03/128 dated 07/05/2025 for Demand: 717 KVA |  |  | BILL/00140/2025-2026 |  | 23/05/2025 | 23/05/2025 | WBSEDCL PURULIA | 124.95 | 0 | 0 | 0
49 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Payment of Quotation for New Connection at CWR-2 (BANDWAN) under BUNDWAN Block (Application Id: 2005087141) vide memo no. 2005095536/Quot/03/73 dated 28/04/2025 for Demand: 99450 WATT |  |  | BILL/00142/2025-2026 |  | 23/05/2025 | 23/05/2025 | WBSEDCL PURULIA | 19.15 | 0 | 0 | 0
Total | [13 empty] | 67168.6 | 1066.71 | 1.59