## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte. (SL-8) | Assistant Engineer |  | ORD/000801/2023-2024 | 1431/PD | 29/09/2023 | 25/06/2024 | MD AAMIR KHAN | 552.37 | 0 | 0 | 0
2 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1128/PD | 17/08/2023 | 17/08/2023 | Resource Division | 8279.54 | 0 | 0 | 0
3 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-X & XI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 7) | Assistant Engineer | Junior Engineer | ORD/000763/2023-2024 | 1369/PD | 14/09/2023 | 12/03/2025 | ANUP KUMAR SAHA | 854.21 | 287.44 | 33.65 | 70
4 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-V & VI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 4) | Assistant Engineer | Junior Engineer-3 | ORD/000761/2023-2024 | 1367/PD | 14/09/2023 | 23/10/2024 | ANUP KUMAR SAHA | 647.66 | 0 | 0 | 0
5 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Opearation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector ) under Purulia Divn. PHE Dte. (SL-11) | Assistant Engineer | Junior Engineer-3 | ORD/000777/2023-2024 | 1419/PD | 29/09/2023 | 07/11/2024 | MS D.PALIT AND CO. | 400.45 | 64.67 | 16.15 | 10
6 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL-2) | Assistant Engineer | Junior Engineer | ORD/000781/2023-2024 | 1421/PD | 29/09/2023 | 22/03/2025 | MS D.PALIT AND CO. | 478.83 | 119.57 | 24.97 | 75
7 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the peroid of thirty six (36) month at Zone- VII & VIII of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 3) | Assistant Engineer | Junior Engineer-3 | ORD/000797/2023-2024 | 1430/PD | 29/09/2023 | 22/03/2025 | ANUP KUMAR SAHA | 649.84 | 203.63 | 31.34 | 55
8 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VI) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000205/2024-2025 | 902/PD | 07/05/2024 | 06/07/2024 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 94.42 | 0 | 0 | 0
9 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-X) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000486/2024-2025 | 1073/PD | 07/06/2024 | 06/08/2024 | SAIKAT RAY | 95.21 | 0 | 0 | 0
10 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000095/2024-2025 | 1053/PMD | 28/06/2024 | 28/06/2025 | DAS ENTERPRISE | 50.63 | 0 | 0 | 0
11 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000096/2024-2025 | 1054/PMD | 28/06/2024 | 28/06/2025 | M/S S.G.ENTERPRISE | 31.65 | 0 | 0 | 0
12 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2024-2025 | 1055/PMD | 28/06/2024 | 28/06/2025 | ANUP KUMAR SAHA | 50.65 | 0 | 0 | 0
13 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000514/2023-2024 | 516/PMD | 15/03/2024 | 15/03/2025 | GOENKA ENTERPRISE | 258.09 | 0 | 0 | 0
14 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000515/2023-2024 | 517/PMD | 15/03/2024 | 15/03/2025 | SINHA ELECTRICALS | 206.55 | 0 | 0 | 0
15 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000519/2023-2024 | 480/PMD | 14/03/2024 | 14/03/2025 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 69.58 | 0 | 0 | 0
16 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000518/2023-2024 | 479/PMD | 14/03/2024 | 14/03/2025 | SUBRATA DUTTA | 69.61 | 0 | 0 | 0
17 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000521/2023-2024 | 482/PMD | 14/03/2024 | 14/03/2025 | M/S D.G.B.ENTERPRISE | 39.77 | 0 | 0 | 0
18 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000513/2023-2024 | 515/PMD | 15/03/2024 | 15/03/2025 | COMBINE ENTERPRISES | 154.79 | 0 | 0 | 0
19 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000520/2023-2024 | 481/PMD | 14/03/2024 | 14/03/2025 | RABINDRA NATH KHAN | 109.36 | 0 | 0 | 0
20 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000098/2024-2025 | 1056/PMD | 28/06/2024 | 28/06/2025 | RABINDRA NATH KHAN | 25.32 | 0 | 0 | 0
21 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Araea) |  |  | ORD/000259/2024-2025 | 1071/PD | 07/06/2024 | 06/08/2024 | SHREYA ENTERPRISES | 94.55 | 0 | 0 | 0
22 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000204/2024-2025 | 901/PD | 07/05/2024 | 06/07/2024 | M/S ANMOL ENGICON | 96.02 | 0 | 0 | 0
23 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IX) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Area) | Assistant Engineer | Junior Engineer-2 | ORD/000220/2024-2025 | 1072/PD | 07/06/2024 | 06/08/2024 | SAROJ KUMAR SINGH | 96.58 | 0 | 0 | 0
24 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000221/2024-2025 | 1095/PD | 07/06/2024 | 06/08/2024 | SUBRATA MAHAPATRA | 25.01 | 0 | 0 | 0
25 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000674/2024-2025 | 1680/PMD | 05/12/2024 | 05/12/2025 | SUBRATA DUTTA | 3.88 | 0 | 0 | 0
26 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000203/2024-2025 | 900/PD | 07/05/2024 | 06/07/2024 | STABILITY INFRASTRUCTURE PVT. LTD. | 96.08 | 0 | 0 | 0
27 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000676/2024-2025 | 1682/PMD | 05/12/2024 | 05/12/2025 | RABINDRA NATH KHAN | 6.1 | 0 | 0 | 0
28 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000677/2024-2025 | 1683/PMD | 05/12/2024 | 05/12/2025 | PINTU DEY | 2.22 | 0 | 0 | 0
29 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Supply Delivery and Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte.(2nd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000701/2024-2025 | 1740/PMD | 16/12/2024 | 16/12/2025 | R.N.S. TRADING | 470.76 | 0 | 0 | 0
30 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003527/2023-2024 | 353/PD | 04/03/2024 | 03/05/2024 | PRIYATOSH MUKHERJEE | 20.95 | 5.41 | 25.85 | 100
31 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 1979/PD | 18/11/2024 | 18/11/2024 | Resource Division | 8491.44 | 0 | 0 | 0
32 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Material Requisition To Resource Division |  |  | RTOR000040/2024-2025 | 2254/PD | 19/12/2024 | 19/12/2024 | Resource Division | 5956.59 | 0 | 0 | 0
33 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-III & IV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 3) | Assistant Engineer | Junior Engineer-3 | ORD/000765/2023-2024 | 1371/PD | 14/09/2023 | 20/07/2025 | ANUP KUMAR SAHA | 671.47 | 0 | 0 | 40
34 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 12) | Assistant Engineer | Junior Engineer | ORD/000762/2023-2024 | 1368/PD | 14/09/2023 | 12/03/2025 | ANUP KUMAR SAHA | 449.89 | 83.16 | 18.48 | 70
35 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL - 4) | Assistant Engineer | Junior Engineer | ORD/000764/2023-2024 | 1370/PD | 14/09/2023 | 02/04/2025 | SAMAN KUMAR MAHATO | 184.53 | 61.12 | 33.12 | 40
36 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XIV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (3rd Call) | Assistant Engineer | Junior Engineer-3 | ORD/002260/2023-2024 | 146/PD | 29/01/2024 | 22/07/2025 | ANUP KUMAR SAHA | 247.75 | 0 | 0 | 10
37 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Design, Surveying,Engineering, Supplying and Construction, Erection, Installation, Testing,Commissioning, of Fixed type Intake Jetty with Pump house, Construction of Sub-station; Raw Water Raising Main Bank Protection, 40 MLD (Minimum) capacity Water Treatment Plant (WTP) based on conventional technologies + 20% overloading; Clear Water Pumping Mains, Booster Stations (11 numbers) at Arsha, Baghmundi, Balarampur, Bandwan, Manbazar I (part), Manbazar II & Purulia I (Part) Blocks including pumping machineries on EPC/ Turnkey basis in a single package including 3 (three) months Trial Run and Operation & Maintenance for 3 years for Surface Based W/S scheme for Southern Sector under Purulia Distric. | Assistant Engineer | Junior Engineer,Junior Engineer-1,Junior Engineer-3 | ORD/001820/2023-2024 | 53/PD | 09/01/2024 | 09/04/2026 | WPIL LIMITED | 32180 | 241.35 | 0.75 | 15
38 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. (Ajodhya Hill Area) | Assistant Engineer | Junior Engineer-2 | ORD/000230/2024-2025 | 1065/PD | 07/06/2024 | 02/06/2025 | VIVEKANANDA CONSTRUCTION | 94.95 | 0 | 0 | 35
39 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000341/2024-2025 | 1367/PD | 25/07/2024 | 24/08/2024 | KOUSHIK CHATTERJEE | 20.13 | 0 | 0 | 0
40 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Construction of New Boundary wall and other allied works at Manbazar Riversite (Harekishtapur) under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000236/2024-2025 | 1077/PD | 07/06/2024 | 06/08/2024 | CHANDAN CHATTERJEE | 31.23 | 0 | 0 | 0
41 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000675/2024-2025 | 1681/PMD | 05/12/2024 | 05/12/2025 | S. PATHAK & CO. | 3.88 | 0 | 0 | 0
42 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/11/24 to 30/04/25) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,JUNIOR ENGINEER (MECHANICAL) | ORD/000779/2024-2025 | 473/PMSD(Drilling) | 24/09/2024 | 24/03/2025 | NUPUR CHANDRA HALDER | 0.86 | 0.36 | 41.44 | 0
43 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 | New | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/05/25 to 28/10/25)" | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000021/2025-2026 | 76/PMSD(Drilling) | 28/04/2025 | 26/10/2025 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0 | 0
Total | [13 empty] | 62364.23 | 1066.71 | 1.71