## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-12) | Assistant Engineer |  | ORD/000277/2023-2024 | 1104/PD | 14/08/2023 | 10/05/2024 | ANUP KUMAR SAHA | 449.89 | 0 | 0 | 0
2 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-2) | Assistant Engineer |  | ORD/000279/2023-2024 | 1095/PD | 14/08/2023 | 10/05/2024 | MS D.PALIT AND CO. | 478.83 | 0 | 0 | 0
3 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-11) | Assistant Engineer |  | ORD/000276/2023-2024 | 1108/PD | 16/08/2023 | 12/05/2024 | MS D.PALIT AND CO. | 400.45 | 0 | 0 | 0
4 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-4) | Assistant Engineer |  | ORD/000274/2023-2024 | 1092/PD | 14/08/2023 | 10/05/2024 | SAMAN KUMAR MAHATO | 184.53 | 0 | 0 | 0
5 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-I of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-8) | Assistant Engineer |  | ORD/000905/2023-2024 | 1574/PD | 30/10/2023 | 26/07/2024 | BOSE CONSTRUCTION | 181.34 | 0 | 0 | 0
6 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of Distribution pipeline From Balarampur OHR site CWR to Petrol Pump near Bihari bandh at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. |  |  | ORD/001110/2024-2025 | 2202/PD | 13/12/2024 | 11/02/2025 | SADHAN GORAIN | 93.97 | 0 | 0 | 0
7 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001116/2024-2025 | 2164/PD | 13/12/2024 | 11/02/2025 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.04 | 0 | 0 | 0
8 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000133/2024-2025 | 903/PD | 07/05/2024 | 06/07/2024 | CHATTERJEE CONSTRUCTION | 95.89 | 0 | 0 | 0
9 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/000134/2024-2025 | 904/PD | 07/05/2024 | 06/07/2024 | M/S SB CONSTRUCTION | 95.99 | 0 | 0 | 0
10 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Purulia-I (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000148/2024-2025 | 919/PD | 07/05/2024 | 06/07/2024 | M/S SB CONSTRUCTION | 61 | 24.53 | 40.22 | 50
11 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-X under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001101/2024-2025 | 2191/PD | 13/12/2024 | 11/02/2025 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 22.55 | 0 | 0 | 0
12 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001114/2024-2025 | 2206/PD | 13/12/2024 | 11/02/2025 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 87.13 | 0 | 0 | 0
13 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-III under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001072/2024-2025 | 2095/PD | 05/12/2024 | 03/02/2025 | M D CONSTRUCTION | 25.74 | 0 | 0 | 0
14 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-II under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001037/2024-2025 | 2097/PD | 05/12/2024 | 03/02/2025 | CHINMOY SEN | 26.6 | 0 | 0 | 0
15 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001073/2024-2025 | 2167/PD | 13/12/2024 | 11/02/2025 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 84.97 | 0 | 0 | 0
16 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of Distribution pipeline From Balarampur Bihari Bandh to Rail Phatak (bagmundiRoad ) at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. |  |  | ORD/001109/2024-2025 | 2201/PD | 13/12/2024 | 11/02/2025 | SADHAN GORAIN | 83.98 | 0 | 0 | 0
17 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-XI under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001038/2024-2025 | 2098/PD | 05/12/2024 | 03/02/2025 | INDRAJIT SARKAR | 19.27 | 0 | 0 | 0
18 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-V under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001039/2024-2025 | 2099/PD | 05/12/2024 | 03/02/2025 | BANERJEE CONSTRUCTION | 23.55 | 0 | 0 | 0
19 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Left out laying of Distribution Pipe Line for distribution System at Chatambari Mouza under command area of Jhalda Rural W/S Scheme Under Purulia W/S Scheme (Southern Sector) of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000445/2024-2025 | 1507/PD | 27/08/2024 | 11/10/2024 | BHAGABAN DAS KUMAR | 2.73 | 2.73 | 99.88 | 100
20 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution pipe line and providing FHTC including other allied work & Operation & Maintenance of Distribution, pipe line (Dt/HDPE),including Sluce Valve & FHTC for the period of thirty six (36) month at zone-Ix of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (Sl No.6) | Assistant Engineer | Junior Engineer-3 | ORD/000271/2023-2024 | 1099/PD | 14/08/2023 | 01/11/2025 | JAL PRAVAHIKA PVT. LTD. | 492.94 | 137.48 | 27.89 | 40
21 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-II & III of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (SL No.2) | Assistant Engineer | Junior Engineer-2 | ORD/000909/2023-2024 | 1584/PD | 30/10/2023 | 28/12/2025 | DEBAKI RANJAN SARKAR | 667.42 | 99.43 | 14.9 | 50
22 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-V & VI of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.10) | Assistant Engineer | Junior Engineer-1 | ORD/000914/2023-2024 | 1579/PD | 30/10/2023 | 01/06/2026 | ANUP KUMAR SAHA | 982.47 | 134.7 | 13.71 | 40
23 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001141/2024-2025 | 44/PD | 10/01/2025 | 24/02/2025 | SUDHANSHU OJHA | 19.2 | 0 | 0 | 0
24 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-XI Bandwan Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/001365/2024-2025 | 503/PD | 25/03/2025 | 22/08/2025 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0 | 0
25 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-XV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001206/2024-2025 | 111/PD | 21/01/2025 | 22/03/2025 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.32 | 0 | 0 | 0
26 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-X Bandwan Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/001366/2024-2025 | 502/PD | 25/03/2025 | 22/08/2025 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0 | 0
27 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000237/2025-2026 | 1089/PD | 17/06/2025 | 15/10/2025 | PURNIMA ELECTRICS AND DECORATORS | 28.82 | 0 | 0 | 0
28 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - IX&X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000238/2025-2026 | 1093/PD | 17/06/2025 | 15/10/2025 | PARADISE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 28.84 | 0 | 0 | 0
29 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-IV Bandwan Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/001337/2024-2025 | 483/PD | 25/03/2025 | 22/08/2025 | ROY CONSTRUCTION | 15.71 | 0 | 0 | 0
30 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-XII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001341/2024-2025 | 490/PD | 25/03/2025 | 22/08/2025 | MOONLIGHT HOUSE | 16.2 | 0 | 0 | 0
31 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001225/2024-2025 | 2199/PD | 13/12/2024 | 11/02/2025 | INFINITE INFRATECH EPC | 85.98 | 0 | 0 | 0
32 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000225/2025-2026 | 1090/PD | 17/06/2025 | 15/10/2025 | M/S SB CONSTRUCTION | 28.5 | 0 | 0 | 0
33 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000226/2025-2026 | 1094/PD | 17/06/2025 | 15/10/2025 | PRAKASH DESHMUKH | 28.73 | 0 | 0 | 0
34 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - VI, VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000228/2025-2026 | 1097/PD | 17/06/2025 | 15/10/2025 | SUJIT SAHANA | 49.71 | 0 | 0 | 0
35 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II, IV & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000229/2025-2026 | 1100/PD | 17/06/2025 | 15/10/2025 | SAHADEV HALDER | 50.09 | 0 | 0 | 0
36 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000233/2025-2026 | 1095/PD | 17/06/2025 | 15/10/2025 | MAA SARADA CONSTRUCTION | 28.82 | 0 | 0 | 0
37 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001224/2024-2025 | 2208/PD | 13/12/2024 | 11/02/2025 | AKHANDAMRIT METALS PRIVATE LIMITED | 68.26 | 0 | 0 | 0
38 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Ajodhya Hill of Baghmundi Block (Zone-XIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. |  |  | ORD/001226/2024-2025 | 2207/PD | 13/12/2024 | 11/02/2025 | ELITE ENGINEERING AND CONSTRUCTION | 96.42 | 0 | 0 | 0
39 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - II, III & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000227/2025-2026 | 1096/PD | 17/06/2025 | 15/10/2025 | SOUHARDYA BUSINESS LINE | 49.99 | 0 | 0 | 0
40 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-I Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/001346/2024-2025 | 495/PD | 25/03/2025 | 22/08/2025 | SINGHA ENTERPRISE | 16.53 | 0 | 0 | 0
41 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-II Bandwan Block within Southern Sector Purulia District under Purulia Division, PHE Dte. |  |  | ORD/001328/2024-2025 | 476/PD | 25/03/2025 | 22/08/2025 | GANGULY ENTERPRISES | 15.52 | 0 | 0 | 0
42 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-III Bandwan Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/001332/2024-2025 | 480/PD | 25/03/2025 | 22/08/2025 | AMITAVA KUNDU | 16.52 | 0 | 0 | 0
43 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Bandwan (Zone - VII, XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000232/2025-2026 | 1088/PD | 17/06/2025 | 15/10/2025 | BLUEDOT CONSTRUCTION | 43.22 | 0 | 0 | 0
44 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-III Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001349/2024-2025 | 497/PD | 25/03/2025 | 22/08/2025 | CHANCHAL MISHRA | 16.61 | 0 | 0 | 0
45 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - IX, XI & XII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000273/2025-2026 | 1098/PD | 17/06/2025 | 15/10/2025 | SOUMYAJIT SAHANA | 49.71 | 0 | 0 | 0
46 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - I, IV & X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000331/2025-2026 | 1427/PD | 05/08/2025 | 03/12/2025 | M/S BHABATARAN MEHTA | 42.84 | 0 | 0 | 0
47 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - I, II & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000621/2025-2026 | 1099/PD | 17/06/2025 | 15/10/2025 | M/S. SAJEDA ENTERPRISE | 50.11 | 0 | 0 | 0
48 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XV& XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000274/2025-2026 | 1092/PD | 17/06/2025 | 15/10/2025 | BABA LOKNATH WORKS CONTRACTOR | 28.73 | 0 | 0 | 0
49 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-VIII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. |  |  | ORD/000362/2025-2026 | 1521/PD | 19/08/2025 | 17/12/2025 | KOUSHIK CHATTERJEE | 16.63 | 0 | 0 | 0
50 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Bandwan (Zone - XV & XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000369/2025-2026 | 1529/PD | 19/08/2025 | 17/12/2025 | ROY CONSTRUCTION | 28.49 | 0 | 0 | 0
51 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Repairing of existing AC/UPVC distribution pipeline due to widening of PWD Road ,Laying of Rising main Pipeline for Jica Projects on Emergency basis and Relevant other allied works at Manbazar-1 under Purulia W/S Scheme under Purulia Division,PHEDte | Assistant Engineer | Junior Engineer-3 | ORD/001111/2024-2025 | 2203/PD | 13/12/2024 | 11/02/2025 | MACHINO TECHNO | 10.39 | 0 | 0 | 100
52 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000442/2024-2025 | 1504/PD | 27/08/2024 | 11/10/2024 | RANJIB GHATAK | 21.02 | 0 | 0 | 100
53 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of PVC Pipeline and HDPE Pipeline due to laying of NCC pipeline at Manbazar Town portion and other repairing works at Manbazar under Purulia W/S Scheme under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001107/2024-2025 | 2198/PD | 13/12/2024 | 11/02/2025 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 8.39 | 0 | 0 | 100
54 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan, Zone-XV under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001036/2024-2025 | 2096/PD | 05/12/2024 | 19/04/2026 | TOTAL INFRA | 25 | 0 | 0 | 60
55 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of Distribution pipeline (HDPE and DI Pipeline) (Loop Line) and Repairing of Damage House Connection of Manbazar II (Zone-4) under Purulia W/S Scheme (Southern Sector) under Purulia Division PHE Dte.(Haridih to Mudidih Chowrasta,Jambedia more Domandih Village , Jambedia Hattola to Dhadkidih Village,Raghunathpur Village to karabahal Village) | Assistant Engineer | Junior Engineer-3 | ORD/001188/2024-2025 | 2343/PD | 31/12/2024 | 29/06/2026 | SUBODH PRAMANIK | 30.44 | 0 | 0 | 80
56 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan ,Zone-II under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001047/2024-2025 | 2108/PD | 05/12/2024 | 19/01/2025 | GANGULY ENTERPRISES | 22.48 | 0 | 0 | 80
57 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Laying of balance distribution pipeline at gap portion of Boludih and Madhupur Mouza under Augmentation of Manbazar under Purulia W/S Scheme under Purulia Division, PHE Dte [SOUTHERN SECTOR] | Assistant Engineer | Junior Engineer-3 | ORD/001081/2024-2025 | 2176/PD | 13/12/2024 | 11/02/2025 | ROY CONSTRUCTION | 44.15 | 0 | 0 | 0
58 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-I under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001088/2024-2025 | 2094/PD | 05/12/2024 | 03/02/2025 | ARATI MAHATO | 22.53 | 0 | 0 | 0
59 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Making bypass arrangement & other allied works at Baghmundi OHR site & WTP site of Baghmundi under Purulia W/S Scheme under Purulia Division, PHE Dte. |  |  | ORD/001080/2024-2025 | 2175/PD | 13/12/2024 | 27/01/2025 | KOUSHIK CHATTERJEE | 6.96 | 0 | 0 | 0
60 | PURULIA | Arsha,Bagmundi,Balarampur,Bundwan,Manbazar-I,Manbazar-II,Purulia-I | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-IX Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001353/2024-2025 | 501/PD | 25/03/2025 | 19/01/2026 | SANJAY KUMAR NARSARIA | 16.69 | 0 | 0 | 0
Total | [13 empty] | 5893.24 | 398.87 | 6.77