## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - A , Mouza - Dhenksila, Ledasan] | Assistant Engineer | Junior Engineer | ORD/000246/2023-2024 | 1062/PD | 08/08/2023 | 07/10/2023 | BOSE CONSTRUCTION | 83.17 | 0 | 0 | 0
2 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-6) | Assistant Engineer |  | ORD/000270/2023-2024 | 1098/PD | 14/08/2023 | 10/05/2024 | PRAVAT SARKAR | 406.17 | 0 | 0 | 0
3 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C , Mouza - Saoradi & Kushtor] | Assistant Engineer | Junior Engineer | ORD/000259/2023-2024 | 1079/PD | 10/08/2023 | 24/09/2023 | BASANTA PARAMANIK | 28.33 | 0 | 0 | 0
4 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-5) | Assistant Engineer |  | ORD/000275/2023-2024 | 1093/PD | 14/08/2023 | 10/05/2024 | MS D.PALIT AND CO. | 373.13 | 0 | 0 | 0
5 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte.(SL-16) | Assistant Engineer |  | ORD/000273/2023-2024 | 1094/PD | 14/08/2023 | 10/05/2024 | KOUSHIK CHATTERJEE | 274.47 | 0 | 0 | 0
6 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of boundary wall at Zone IV H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer |  | ORD/000286/2023-2024 | 1144/PD | 17/08/2023 | 16/09/2023 | DILIP MISHRA | 17.51 | 0 | 0 | 0
7 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 500 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-VI of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-12) | Assistant Engineer |  | ORD/000906/2023-2024 | 1575/PD | 30/10/2023 | 26/07/2024 | SADHAN GORAIN | 704.66 | 0 | 0 | 0
8 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Raibanbh Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001018/2023-2024 | 1646/PD | 08/11/2023 | 07/01/2024 | ROY CONSTRUCTION | 19.01 | 0 | 0 | 0
9 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Belguma mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001017/2023-2024 | 1645/PD | 08/11/2023 | 07/01/2024 | S.R ENTERPRISE | 58.5 | 0 | 0 | 0
10 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-IV of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-1) | Assistant Engineer | Junior Engineer-2 | ORD/000898/2023-2024 | 1564/PD | 26/10/2023 | 22/07/2024 | PARTHA PRATIM CHHATAIT | 393.93 | 0 | 0 | 0
11 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I Block (Zone-VI) For Buridi Mouza under Purulia Division. PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001075/2023-2024 | 1638/PD | 08/11/2023 | 23/12/2023 | TAPAS KUMBHAKAR | 46.5 | 0 | 0 | 0
12 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012)with allied works for Zone- V of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2023-2024 | 692/PD | 22/05/2023 | 18/12/2023 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 81.57 | 0 | 0 | 0
13 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Kendthol & Kharbar] | Assistant Engineer | Junior Engineer | ORD/000255/2023-2024 | 1070/PD | 08/08/2023 | 07/10/2023 | ASHOKE ADHIKARY | 28.6 | 16.01 | 55.98 | 45
14 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Amlagarya, Shaltora & Rambhatdi] | Assistant Engineer | Junior Engineer | ORD/000245/2023-2024 | 1061/PD | 08/08/2023 | 02/01/2026 | SUBRATA SINGHADEO | 76.77 | 55.79 | 72.67 | 30
15 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Amdiha, Bidhakata] | Assistant Engineer | Junior Engineer | ORD/000251/2023-2024 | 1064/PD | 08/08/2023 | 02/12/2024 | CHANDAN CHATTERJEE | 37.59 | 23.69 | 63.02 | 60
16 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Palash Pahari & Benrya] | Assistant Engineer | Junior Engineer | ORD/000256/2023-2024 | 1071/PD | 08/08/2023 | 07/10/2023 | M/S KHAN ENTERPRISE | 42.09 | 25.87 | 61.47 | 70
17 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Jiyataal, Chhayrabari, Ambari] | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 1052/PD | 08/08/2023 | 07/10/2023 | M/S. BADAL GHOSH | 93.96 | 73.9 | 78.66 | 60
18 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC) including other allied work for Zone VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza-kulal &gothbathanj] | Assistant Engineer | Junior Engineer | ORD/000254/2023-2024 | 1069/PD | 08/08/2023 | 07/10/2023 | SK ABBAS | 31.68 | 17.87 | 56.43 | 45
19 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Salberya] | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 1058/PD | 08/08/2023 | 24/10/2024 | SUBHAS CHANDRA MAHATO | 42.72 | 19.44 | 45.51 | 48
20 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Benagaria(5%), Ghutgarya, Latulbad & Dulalgora] | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 1060/PD | 08/08/2023 | 07/10/2023 | PRATIK SAHA | 93.7 | 69.11 | 73.75 | 70
21 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Lapahari, Nuhichabad, Moraldi] | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 1051/PD | 08/08/2023 | 07/10/2023 | SUMIT KUMAR CHAKRABORTY | 58.97 | 36.61 | 62.08 | 60
22 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Brindabanpur] | Assistant Engineer | Junior Engineer | ORD/000264/2023-2024 | 1078/PD | 10/08/2023 | 09/10/2023 | M/S MONDAL ENTERPRISE | 74.83 | 54.33 | 72.6 | 60
23 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Kankarkiari, Malibana, Dubrajpur] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000252/2023-2024 | 1065/PD | 08/08/2023 | 04/09/2026 | MADHU SUDAN RAKSHIT | 59.37 | 40.91 | 68.9 | 65
24 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Tarabari, Gumra] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000249/2023-2024 | 1050/PD | 08/08/2023 | 01/04/2025 | KHITISH CHANDRA PATHAK | 96.93 | 71.88 | 74.15 | 60
25 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Muktipur] | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 1083/PD | 10/08/2023 | 09/10/2023 | CHATTERJEE CONSTRUCTION | 94.06 | 85.86 | 91.28 | 75
26 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including submission of complete detailed drawing of distribution system, rising main etc. after execution of work and other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division , PHE Dte. [Part - C, Mouza - Pachandapur, Beliapur & Kalikapur] | Assistant Engineer | Junior Engineer | ORD/000263/2023-2024 | 1084/PD | 10/08/2023 | 09/10/2023 | RANJIB GHATAK | 91.79 | 71.12 | 77.48 | 60
27 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F, Mouza - Goalberya &Matidundra] | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 1072/PD | 08/08/2023 | 07/10/2023 | TAPAN CHANDRA | 49.95 | 31.6 | 63.25 | 48
28 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Benagaria] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000247/2023-2024 | 1063/PD | 08/08/2023 | 07/10/2023 | KABERI DUTTA | 32.36 | 23.94 | 73.99 | 76
29 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Kinaidih & Majharadih] | Assistant Engineer | Junior Engineer,Junior Engineer-4 | ORD/000260/2023-2024 | 1080/PD | 10/08/2023 | 20/01/2025 | THE BUSINESS ENGINEERS INDIA | 25.17 | 0 | 0 | 65
30 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A , Mouza - Kandberya & Authumajhirdi] | Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 1077/PD | 10/08/2023 | 09/10/2023 | M/S KALYANI ENTERPRISE | 95.29 | 74.78 | 78.48 | 60
31 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Amandih mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000856/2023-2024 | 1495/PD | 12/10/2023 | 26/11/2023 | SUSANTA KR DUTTA | 60.42 | 0 | 0 | 0
32 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-V) for Hulka & Kultanr alias nadiyara Under Purulia Divn PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000854/2023-2024 | 1493/PD | 12/10/2023 | 26/11/2023 | KABERI DUTTA | 11.47 | 0 | 0 | 0
33 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Jibanpur Alias Ramjibanpur, Barhanti & Talberya] | Assistant Engineer | Junior Engineer-3 | ORD/000889/2023-2024 | 1540/PD | 16/10/2023 | 01/01/2025 | M/S SB CONSTRUCTION | 65.75 | 20.42 | 31.05 | 55
34 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month for Zone-XI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-8) | Assistant Engineer | Junior Engineer | ORD/000838/2023-2024 | 1426/PD | 29/09/2023 | 01/09/2025 | SUJIT SAHANA | 361.35 | 146.87 | 40.65 | 15
35 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six (36) month Zone - X , XI & XIV of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | Assistant Engineer | Junior Engineer | ORD/000832/2023-2024 | 1415/PD | 29/09/2023 | 23/09/2024 | LUKE ENGICON | 1374.87 | 123.81 | 9.01 | 30
36 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Mahalitora Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000852/2023-2024 | 1491/PD | 12/10/2023 | 26/11/2023 | SOUVIK MANDAL | 33.54 | 0 | 0 | 0
37 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Narayanpur & Nadiha (20%) ] | Assistant Engineer | Junior Engineer | ORD/000994/2023-2024 | 1634/PD | 08/11/2023 | 23/12/2023 | BABA LOKNATH ENTERPRISE | 59.46 | 37.4 | 62.91 | 60
38 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Kalipahari, Hansdima] | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 1536/PD | 16/10/2023 | 01/04/2025 | KHITISH CHANDRA PATHAK | 77.29 | 56.4 | 72.97 | 60
39 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Pirargoriya & Lediam] | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 1538/PD | 16/10/2023 | 15/12/2023 | GHOSH AND ROY ENTERPRISE | 52.38 | 33.82 | 64.57 | 55
40 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-VIII) for Dimdiha Mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/000875/2023-2024 | 1526/PD | 16/10/2023 | 30/11/2023 | BHAGABANDAS KUMAR | 31.72 | 0 | 0 | 0
41 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A, Mouza - Marbedya, Ghoramurga] | Assistant Engineer | Junior Engineer-3 | ORD/000885/2023-2024 | 1535/PD | 16/10/2023 | 02/03/2026 | AMIT PATHAK | 64.16 | 35.79 | 55.77 | 55
42 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-15) | Assistant Engineer | Junior Engineer | ORD/000899/2023-2024 | 1567/PD | 26/10/2023 | 01/04/2026 | KM ENTERPRISES | 243.33 | 130.89 | 53.79 | 65
43 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Raghunathpur - I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-14) | Assistant Engineer | Junior Engineer-2 | ORD/000893/2023-2024 | 1559/PD | 18/10/2023 | 28/09/2026 | ASHOKE KUMAR CHATTERJEE | 413.23 | 31.4 | 7.6 | 5
44 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Nadiha (80%)] | Assistant Engineer | Junior Engineer | ORD/000992/2023-2024 | 1633/PD | 08/11/2023 | 07/01/2024 | MOLLA ENTERPRISE | 67.12 | 36.69 | 54.66 | 60
45 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Khojda Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/000998/2023-2024 | 1636/PD | 08/11/2023 | 23/12/2023 | SOUVIK MANDAL | 51.27 | 0 | 0 | 0
46 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-IV) for Chakra, Kultanr alias Nadiyara Under Purulia Divn. PHE DTE. | Assistant Engineer |  | ORD/000878/2023-2024 | 1528/PD | 16/10/2023 | 30/11/2023 | SOUHARDYA BUSINESS LINE | 34.94 | 0 | 0 | 0
47 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Chhota Pathar, Kashikunri, Baghadabar & Kushunda] | Assistant Engineer | Junior Engineer | ORD/000887/2023-2024 | 1537/PD | 16/10/2023 | 15/12/2023 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 84.9 | 67.35 | 79.33 | 60
48 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Bamra Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001005/2023-2024 | 1640/PD | 08/11/2023 | 07/01/2024 | CHATTERJEE CONSTRUCTION | 15.46 | 0 | 0 | 0
49 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Simulia Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001006/2023-2024 | 1641/PD | 08/11/2023 | 07/01/2024 | RAJAT KARMAKAR | 43.25 | 0 | 0 | 0
50 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Kanali Mouza under Purulia Division. PHE Dte. | Assistant Engineer |  | ORD/001001/2023-2024 | 1637/PD | 08/11/2023 | 23/12/2023 | MANATOSH SINGH | 50.19 | 0 | 0 | 0
51 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Chakda Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001015/2023-2024 | 1643/PD | 08/11/2023 | 07/01/2024 | MS D.PALIT AND CO. | 88.91 | 0 | 0 | 0
52 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Dhadhka mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/000858/2023-2024 | 1497/PD | 12/10/2023 | 26/11/2023 | KOUSHIK CHATTERJEE | 22.91 | 0 | 0 | 0
53 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kalipur Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001008/2023-2024 | 1642/PD | 08/11/2023 | 07/01/2024 | DEBANJAN SEAL | 22.77 | 0 | 0 | 0
54 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- PurbaBero, JL No-195, Plot No-1839) of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 330 mtr.) |  |  | ORD/001853/2023-2024 | 83/PD | 15/01/2024 | 15/03/2024 | SABYASACHI MISHRA | 38.55 | 0 | 0 | 0
55 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line including FHTC and other allied work for Zone-I of Neturia Block at Mouza-Pochhara under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHEDte.(Part-B) | Assistant Engineer | Junior Engineer,Junior Engineer-2,Junior Engineer-3 | ORD/001867/2023-2024 | 92/PD | 15/01/2024 | 01/04/2026 | BISWAJIT MAJI | 22.45 | 10.65 | 47.44 | 60
56 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XV & XVI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 290 m) | Assistant Engineer | Junior Engineer | ORD/001849/2023-2024 | 81/PD | 15/01/2024 | 15/03/2024 | SUMIT KUMAR CHAKRABORTY | 39.78 | 15.76 | 39.63 | 50
57 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line including other allied work for Zone-I of Neturia Block under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte.(Part-D) |  |  | ORD/001879/2023-2024 | 94/PD | 15/01/2024 | 15/03/2024 | KANJILAL AND CO. | 12.5 | 0 | 0 | 0
58 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- V & VI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) |  |  | ORD/001832/2023-2024 | 70/PD | 10/01/2024 | 10/03/2024 | HUSSAIN CONSTRUCTION | 38.75 | 0 | 0 | 0
59 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - VII & VIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer | Junior Engineer | ORD/001848/2023-2024 | 80/PD | 15/01/2024 | 15/03/2024 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 38.78 | 15.14 | 39.05 | 50
60 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VII of Purulia-I block for Golbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-4 | ORD/002901/2023-2024 | 239/PD | 15/02/2024 | 15/04/2024 | MARAUTI CONSTRUCTION AND CO | 83.25 | 0 | 0 | 0
61 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VI of Purulia-I block for Shibdi Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 30) |  |  | ORD/000202/2024-2025 | 1030/PD | 04/06/2024 | 03/08/2024 | MS D.PALIT AND CO. | 120.66 | 0 | 0 | 0
62 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Neturia (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/000150/2024-2025 | 923/PD | 07/05/2024 | 06/07/2024 | M/S SB CONSTRUCTION | 63.99 | 0 | 0 | 0
63 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 600 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) with allied works for Zone- I of Purulia-1 Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Sl No. 01) | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000198/2024-2025 | 1026/PD | 04/06/2024 | 01/03/2025 | SADHAN GORAIN | 141.19 | 0 | 0 | 0
64 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (Part B) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-1,Junior Engineer-3 | ORD/000224/2024-2025 | 1060/PD | 07/06/2024 | 06/08/2024 | SOUMITRA CHAKRABORTY | 77.87 | 0 | 0 | 0
65 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and Laying Distribution Pipe Lines with allied works for Zone-II of Neturia Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.[ Part - A, Mouza- Puapur ] (Sl No. 06) | Assistant Engineer | Junior Engineer-2 | ORD/000199/2024-2025 | 1029/PD | 04/06/2024 | 01/03/2025 | KHITISH CHANDRA PATHAK | 157.44 | 0 | 0 | 0
66 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and providing Functional Household Tap Connection (Mouza - Bhul) with allied works for Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 01) | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000201/2024-2025 | 1027/PD | 04/06/2024 | 01/03/2025 | M DHARA & BROTHERS | 131.3 | 0 | 0 | 0
67 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Lalgarh] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000261/2023-2024 | 1082/PD | 10/08/2023 | 09/10/2023 | M/S SAYAK BHATTACHARYA | 71.84 | 70.22 | 97.74 | 100
68 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Kotaldih] | Assistant Engineer | Junior Engineer | ORD/000265/2023-2024 | 1081/PD | 10/08/2023 | 24/09/2023 | HAFIJUR RAHAMAN MIDYA | 39.96 | 39.94 | 99.97 | 90
69 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Ranipur Colliery & Deiliya] | Assistant Engineer | Junior Engineer | ORD/000996/2023-2024 | 1635/PD | 08/11/2023 | 08/12/2023 | M/S SAYAK BHATTACHARYA | 89.86 | 83.16 | 92.54 | 100
70 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) | Assistant Engineer | Junior Engineer-4 | ORD/001834/2023-2024 | 72/PD | 10/01/2024 | 10/03/2024 | SAMAN KUMAR MAHATO | 38.79 | 8.96 | 23.1 | 100
71 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying distribution system including providing FHTC(Lalpur Paharpur , Domsota) and other allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/001874/2023-2024 | 99/PD | 15/01/2024 | 15/03/2024 | M/S SAYAK BHATTACHARYA | 51.94 | 0 | 0 | 100
72 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- III & IV of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300 m) | Assistant Engineer | Junior Engineer | ORD/001831/2023-2024 | 69/PD | 10/01/2024 | 01/03/2025 | CHANCHAL MISHRA | 40.76 | 31.17 | 76.48 | 95
73 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division,P.H.E. Dte.(Total Length of Boundary Wall: 280m) | Assistant Engineer | Junior Engineer | ORD/001828/2023-2024 | 66/PD | 10/01/2024 | 04/10/2024 | M/S KALYANI ENTERPRISE | 38.8 | 36.12 | 93.09 | 100
74 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- I & II of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | Assistant Engineer | Junior Engineer | ORD/001830/2023-2024 | 68/PD | 10/01/2024 | 10/03/2024 | AMIT PATHAK | 39.72 | 30.17 | 75.96 | 65
75 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - I & II of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer | Junior Engineer | ORD/002299/2023-2024 | 192/PD | 02/02/2024 | 02/04/2024 | TOTAL INFRA | 38.57 | 37.26 | 96.6 | 100
76 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XVII & XVIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | Assistant Engineer | Junior Engineer | ORD/001852/2023-2024 | 82/PD | 15/01/2024 | 15/03/2024 | SANJAY KUMAR NARSARIA | 38.72 | 15.37 | 39.69 | 100
77 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003465/2023-2024 | 334/PD | 01/03/2024 | 30/04/2024 | VIVEKANANDA CONSTRUCTION | 22.85 | 18.12 | 79.29 | 100
78 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI rising main including bypass arrangement & other allied works & construction of boundary wall at Baghmundi WTP Site in Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 895/PD | 07/05/2024 | 06/07/2024 | ROY CONSTRUCTION | 36.11 | 31.51 | 87.25 | 100
79 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Sinking of 1(One) nos tube well, Withdrawing and relaying of DI Pipe, Earth filling and surface dressing Near Northern Sector Head work site under Purulia Piped w/s Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 912/PD | 07/05/2024 | 06/06/2024 | CHATTERJEE CONSTRUCTION | 7.82 | 7.44 | 95.18 | 85
80 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Sinking of 1(One) no 200 mm dia DTH rigbored tubewell at OHR Sites of Zone - II ( Fusrabad) of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000438/2024-2025 | 1501/PD | 27/08/2024 | 26/09/2024 | BISWAJIT MAJI | 5.49 | 5.38 | 97.98 | 100
81 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Sinking of 1(One) nos tubewell at OHR Site of Zone - V of Raghunathpur-II Block under Northen Sector Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000462/2024-2025 | 1521/PD | 27/08/2024 | 26/09/2024 | CHAIL CONSTRUCTION | 5.08 | 4.65 | 91.51 | 100
82 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 2255/PD | 19/12/2024 | 19/12/2024 | Resource Division | 157.32 | 0 | 0 | 0
83 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050611202404020185125751XX DT.06-11-2024. |  |  | BILL/00957/2024-2025 | BP-2024-25-527 | 14/11/2024 | 14/11/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
84 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052611202406351574709356XX DT.26-11-2024. |  |  | BILL/01024/2024-2025 | BP-2024-25-532 | 02/12/2024 | 02/12/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
85 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412201575410323XX DT.11-11-2024. |  |  | BILL/00958/2024-2025 | BP-2024-25-529 | 14/11/2024 | 14/11/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
86 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.924/PWD dt.19.06.2024) (Norther Sector) |  |  | BILL/00579/2024-2025 | BP-2024-25-340 | 28/08/2024 | 28/08/2024 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0 | 0
87 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.1536/PWD dt.27.09.2024) (Norther Sector) |  |  | BILL/00961/2024-2025 | BP-2024-25-530 | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0 | 0
88 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412211573995764XX DT.11-11-2024. |  |  | BILL/00959/2024-2025 | BP-2024-25-528 | 14/11/2024 | 14/11/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
89 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. |  |  | ORD/000198/2025-2026 | 1058/PD | 17/06/2025 | 01/08/2025 | SWAPAN MANDAL | 0 | 0 | NAN | 0
90 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution pipeline, providing FHTC including other allied works for Zone- II of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A Mouza- MURULIA (3.5%)] | Assistant Engineer | Junior Engineer,Junior Engineer-3 | ORD/000063/2023-2024 | 694/PD | 22/05/2023 | 10/10/2025 | MAHARSHI BANERJEE | 95.06 | 0 | 0 | 90
91 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Bhagabandh, Kherad] | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000243/2023-2024 | 1059/PD | 08/08/2023 | 07/01/2025 | SINGHA ENTERPRISE | 51.36 | 0 | 0 | 0
92 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone- VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Gorsika] | Assistant Engineer | Junior Engineer | ORD/000253/2023-2024 | 1068/PD | 08/08/2023 | 03/02/2025 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 71.26 | 35.85 | 50.31 | 50
93 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution Pipe Line with allied works for Zone- VII of Santuri Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. [Part - A Mouza-Gorsika] | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1138/PD | 17/08/2023 | 09/08/2026 | AMIT PATHAK | 94.37 | 32.79 | 34.75 | 20
94 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six month for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - VII & VIII) under Purulia Divn. PHE Dte. (SL-3) | Assistant Engineer | Junior Engineer-3 | ORD/000809/2023-2024 | 1416/PD | 29/09/2023 | 26/06/2025 | JAYANTA KUMAR MONDAL | 888.48 | 247.84 | 27.9 | 38
95 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) for Zone-III & IV of Raghunathpur - II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-21) | Assistant Engineer | Junior Engineer | ORD/000803/2023-2024 | 1428/PD | 29/09/2023 | 19/12/2025 | NIBHAS SINHA | 863.77 | 145.1 | 16.8 | 12
96 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Manbazar-I Block(Zone - I to IV) under Purulia Divn. PHE Dte. (SL-4) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 1417/PD | 29/09/2023 | 17/11/2025 | SHYAM KUMAR | 1479.87 | 248.04 | 16.76 | 50
97 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied Works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone- I of Raghunathpur - II block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-19) | Assistant Engineer | Junior Engineer-1 | ORD/000805/2023-2024 | 1424/PD | 29/09/2023 | 28/09/2026 | TUMPA GORAIN | 117.63 | 0 | 0 | 15
98 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Hulka & kultanr Alias nadiyara under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) |  | ORD/000853/2023-2024 | 1492/PD | 12/10/2023 | 06/01/2025 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 41.55 | 0 | 0 | 0
99 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)with allied works for Purulia Water Supply Scheme.(Location:-Block-Purulia-1 , Zone-VIII) for Northern Zone | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000855/2023-2024 | 1494/PD | 12/10/2023 | 03/04/2025 | KM ENTERPRISES | 81.93 | 6.05 | 7.39 | 45
100 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block (zone-IV & V) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 11) | Assistant Engineer | Junior Engineer-3 | ORD/000903/2023-2024 | 1573/PD | 30/10/2023 | 01/05/2026 | JAYANTA KUMAR MONDAL | 1398.36 | 102.6 | 7.34 | 42
101 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-IV of Chakra, Kultanr alias Nadiyara,Palkiri,Baroyadi of Purulia-I block under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000877/2023-2024 | 1527/PD | 16/10/2023 | 01/03/2026 | M/S SAWDESH ENTERPRISE | 63.56 | 0 | 0 | 60
102 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-13) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000907/2023-2024 | 1576/PD | 30/10/2023 | 26/07/2024 | SADHAN GORAIN | 692.19 | 0 | 0 | 25
103 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kotloi Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-4 | ORD/001013/2023-2024 | 1644/PD | 08/11/2023 | 06/01/2025 | SUBODH PRAMANIK | 40.95 | 0 | 0 | 0
104 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for different Zones in Joypur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.1) | Assistant Engineer | Junior Engineer-1 | ORD/000926/2023-2024 | 1594/PD | 31/10/2023 | 25/10/2025 | PRITI EPC PRIVATE LIMITED | 5517.66 | 0 | 0 | 10
105 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VI & VII of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.7) | Assistant Engineer | Junior Engineer-2 | ORD/000910/2023-2024 | 1583/PD | 30/10/2023 | 17/10/2026 | DEBAKI RANJAN SARKAR | 973.78 | 0 | 0 | 32
106 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)Including soil testing with other allied works for Zone-III of Santuri Block under Purulia Piped Water Supply Scheme(Northern) under Puru;ia Divn. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 1282/PD | 31/08/2023 | 23/11/2025 | CHATTERJEE CONSTRUCTION | 81.76 | 22.18 | 27.12 | 10
107 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-I of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-13) | Assistant Engineer | Junior Engineer-2 | ORD/000900/2023-2024 | 1566/PD | 26/10/2023 | 22/07/2024 | KOUSHIK CHATTERJEE | 144.2 | 0 | 0 | 0
108 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I block(Zone-II) for Satar Mouza under Purulia Division. PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000990/2023-2024 | 1632/PD | 08/11/2023 | 26/11/2025 | HIRAK KUMAR SAO | 70.4 | 0 | 0 | 60
109 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) AT Zone-VIII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-12) | Assistant Engineer | Junior Engineer | ORD/000902/2023-2024 | 1565/PD | 26/10/2023 | 18/04/2025 | BBC ENTERPRISE | 535.9 | 76.91 | 14.35 | 45
110 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied work & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 10) | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 1433/PD | 29/09/2023 | 27/06/2026 | MADHU SUDAN RAKSHIT | 296.95 | 12.04 | 4.05 | 25
111 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Dimdiha Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-1,Junior Engineer-3 | ORD/000876/2023-2024 | 1525/PD | 16/10/2023 | 01/01/2026 | GOUTAM CHAKRABORTY | 112.33 | 0 | 0 | 0
112 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Gondhudi Mouza under Purulia Division. PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) |  | ORD/001002/2023-2024 | 1639/PD | 08/11/2023 | 01/01/2026 | M/S CHAKRABORTY CONSTRUCTION | 49.52 | 0 | 0 | 0
113 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III & IV of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.2) | Assistant Engineer | Junior Engineer-2 | ORD/000911/2023-2024 | 1582/PD | 30/10/2023 | 17/10/2026 | DEBAKI RANJAN SARKAR | 787.54 | 0 | 0 | 10
114 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - I , II & III) under Purulia Divn. PHE Dte. (SL-1) | Assistant Engineer | Junior Engineer-3 | ORD/000834/2023-2024 | 1432/PD | 29/09/2023 | 01/07/2025 | HANNAN BUILDERS PRIVATE LIMITED | 1240.82 | 218.91 | 17.64 | 30
115 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-III of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-7) | Assistant Engineer | Junior Engineer | ORD/000918/2023-2024 | 1592/PD | 31/10/2023 | 01/08/2025 | SWAPAN MANDAL | 295.01 | 41.46 | 14.05 | 70
116 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-I of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 1) | Assistant Engineer | Junior Engineer | ORD/000920/2023-2024 | 1593/PD | 31/10/2023 | 30/05/2026 | SANTANU BANERJEE | 574.33 | 136.14 | 23.7 | 70
117 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 400 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-II of Raghunathpur-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 20) | Assistant Engineer | Junior Engineer-1 | ORD/000917/2023-2024 | 1599/PD | 31/10/2023 | 17/10/2026 | DEBAKI RANJAN SARKAR | 404.59 | 0 | 0 | 0
118 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII & VIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL No.5) | Assistant Engineer | Junior Engineer-1 | ORD/000921/2023-2024 | 1591/PD | 31/10/2023 | 01/06/2026 | SANTANU BANERJEE | 769.41 | 0 | 0 | 40
119 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-7) | Assistant Engineer | Junior Engineer-1 | ORD/000894/2023-2024 | 1557/PD | 18/10/2023 | 11/04/2025 | RANJIB GHATAK | 277.73 | 93.24 | 33.57 | 75
120 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001658/2023-2024 | 4783/PSD | 24/08/2023 | 24/02/2024 | BOSE CONSTRUCTION | 0.88 | 1.4 | 158.93 | 0
121 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- IX to XV of Purulia-II Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | Assistant Engineer | Junior Engineer-3 | ORD/001600/2023-2024 | 41/PD | 08/01/2024 | 23/12/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3673.24 | 132.14 | 3.6 | 15
122 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- I,II,III,IV,V,VI,VII,VIII,IX,XII,XIII of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | Assistant Engineer | Junior Engineer | ORD/001606/2023-2024 | 1761/PD | 07/12/2023 | 23/11/2026 | S & P ENTERPRISE | 5304.39 | 243.05 | 4.58 | 55
123 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte (Northen Zone) | Assistant Engineer | Junior Engineer-3 | ORD/001657/2023-2024 | 4769/PSD | 21/08/2023 | 21/02/2024 | ANUP KUMAR SAHA | 0.9 | 0 | 0 | 0
124 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone- I to XVIII of Para Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001599/2023-2024 | 1821/PD | 12/12/2023 | 01/12/2025 | M/S ANAND SINGH | 7701.69 | 1226.82 | 15.93 | 40
125 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XIII & XIV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 260m) | Assistant Engineer | Junior Engineer-4 | ORD/001829/2023-2024 | 67/PD | 10/01/2024 | 01/01/2025 | S.S CONSTRUCTION | 36.76 | 5.35 | 14.54 | 65
126 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) with allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001865/2023-2024 | 91/PD | 15/01/2024 | 13/10/2024 | SIMA ENTERPRISE | 70.28 | 53.5 | 76.12 | 85
127 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- GamarKunri, JL No-167, Plot No-756) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 380 mtr.) | Assistant Engineer | Junior Engineer-1 | ORD/001855/2023-2024 | 85/PD | 15/01/2024 | 31/05/2026 | CHAIL CONSTRUCTION | 43.63 | 0 | 0 | 0
128 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat BPS Site (Mouza- Tara, JL No-182, Plot No-1587) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 400 mtr.) | Assistant Engineer | Junior Engineer | ORD/001854/2023-2024 | 84/PD | 15/01/2024 | 15/03/2024 | NANIGOPAL DEY | 45.63 | 4.11 | 9 | 10
129 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001184/2024-2025 | 2339/PD | 31/12/2024 | 01/03/2025 | JULI ENTERPRISE | 30.06 | 0 | 0 | 0
130 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of distribution pipe line and other allied work for Zone-III of Santuri Block under Surface water based water supply scheme for Purulia district (Northern Sector) Under Purulia Division PHE. DTE. Part-B Mouza- Brindabanpur |  |  | ORD/001135/2024-2025 | 2015/PD | 22/11/2024 | 21/01/2025 | M/S MONDAL ENTERPRISE | 17.47 | 0 | 0 | 0
131 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001158/2024-2025 | 2310/PD | 31/12/2024 | 01/12/2025 | VIVEKANANDA CONSTRUCTION | 33.11 | 0 | 0 | 0
132 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/004806/2023-2024 | 130B/PSD | 14/03/2024 | 13/09/2024 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
133 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-X) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001170/2024-2025 | 2324/PD | 31/12/2024 | 01/03/2025 | M/S CONTRACTORS SYNDICATE | 34.06 | 0 | 0 | 0
134 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001169/2024-2025 | 2323/PD | 31/12/2024 | 01/03/2025 | SEKH ABBAS | 34.09 | 0 | 0 | 0
135 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of distributuion pipe line and other allied work for Zone-I of Santuri Block under Surface Water Based Water Supply Scheme for Purulia District (Northern Sector) under Purulia Division PHE. DTE. Part-C (Mouza- Pachandapur, Beliapur & Kalikapur ) | Assistant Engineer | Junior Engineer-3 | ORD/001136/2024-2025 | 2014/PD | 22/11/2024 | 22/12/2024 | RANJIB GHATAK | 3.49 | 0 | 0 | 100
136 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-III) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001144/2024-2025 | 2298/PD | 31/12/2024 | 01/03/2025 | PRATIK SAHA | 34.03 | 0 | 0 | 0
137 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte.(01/03/2024 to 31/08/2024) |  | Junior Engineer-3 | ORD/004307/2023-2024 | 101/PSD | 27/02/2024 | 27/08/2024 | BOSE CONSTRUCTION | 0.88 | 2.21 | 250.55 | 0
138 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for the Assistant Engineer to look after the ongoing works under RWS Purulia Sub-Division PHE Dte (For12 months ) (w.e.f. 01/09/2022 to 31/08/2023). | Assistant Engineer | Junior Engineer | ORD/001328/2022-2023 | 415/A/PR | 30/08/2022 | 30/08/2023 | ANUP KUMAR SAHA | 1.76 | 0 | 0 | 100
139 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001178/2024-2025 | 2332/PD | 31/12/2024 | 01/03/2025 | UTTAM KUMAR PARAMANIK | 29.89 | 0 | 0 | 0
140 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001179/2024-2025 | 2333/PD | 31/12/2024 | 01/03/2025 | SUMIT KUMAR MITRA | 32.38 | 0 | 0 | 0
141 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-IX)under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4,Junior Engineer-5 | ORD/001192/2024-2025 | 2318/PD | 31/12/2024 | 21/08/2026 | SAPAN KUMAR PARAMANIK | 34 | 0 | 0 | 0
142 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Air conditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/004286/2023-2024 | 213/A/PR | 27/03/2024 | 23/09/2024 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
143 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001160/2024-2025 | 2312/PD | 31/12/2024 | 01/03/2025 | SUBHAS CHANDRA MAHATO | 31.96 | 0 | 0 | 0
144 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001102/2024-2025 | 2192/PD | 13/12/2024 | 01/01/2026 | BISWAJIT MAJI | 22.64 | 0 | 0 | 0
145 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 13/09/2024 to 14/03/2025) |  | Junior Engineer-3 | ORD/000766/2024-2025 | 432/PSD | 11/09/2024 | 13/03/2025 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
146 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01/10/2023 to 31/03/2024) |  | Junior Engineer-3 | ORD/003320/2023-2024 | 4857/PSD | 29/09/2023 | 30/03/2024 | KOUSHIK CHATTERJEE | 0.9 | 1.85 | 205.99 | 0
147 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(w.e.f. 01/03/2024 to 30/08/2024)=184 days |  | Junior Engineer-3 | ORD/003682/2023-2024 | 102/PSD | 27/02/2024 | 29/08/2024 | ANUP KUMAR SAHA | 0.9 | 1.17 | 129.95 | 0
148 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000653/2024-2025 | 1862/PD | 30/09/2024 | 29/11/2025 | BANERJEE CONSTRUCTION | 14.37 | 0 | 0 | 20
149 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Hiring of Ambassador Car / Bolero for JJM related works for the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. (w.e.f. 01.09.2024 to 31.08.2025) | Assistant Engineer | Junior Engineer-1 | ORD/000646/2024-2025 | 1653/PD | 30/08/2024 | 30/08/2025 | CHANDRA SHEKHAR KUNDU | 1.76 | 2.33 | 132.34 | 0
150 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IX) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001150/2024-2025 | 2301/PD | 31/12/2024 | 01/03/2025 | S S ENTERPRISE | 34.25 | 0 | 0 | 0
151 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001154/2024-2025 | 2306/PD | 31/12/2024 | 01/03/2025 | MAHATO CONSTRUCTION | 29.14 | 0 | 0 | 0
152 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 20) | Assistant Engineer(HQ) | Junior Engineer-4 | ORD/000197/2024-2025 | 1031/PD | 04/06/2024 | 02/08/2025 | ANUP KUMAR SAHA | 148.36 | 0 | 0 | 0
153 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-II of Purulia-I block for Bhul Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 02) | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/000200/2024-2025 | 1028/PD | 04/06/2024 | 28/02/2025 | SOUMITRA CHAKRABORTY | 113.07 | 52.44 | 46.38 | 50
154 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at PURULIA-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-4 | ORD/001193/2024-2025 | 2313/PD | 31/12/2024 | 01/08/2025 | TARA MAA SHAKTI CONSTRUCTION | 37.61 | 0 | 0 | 90
155 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001189/2024-2025 | 85/PD | 16/01/2025 | 01/12/2025 | M/S KHAN ENTERPRISE | 31.36 | 0 | 0 | 95
156 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-II) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001195/2024-2025 | 2348/PD | 31/12/2024 | 24/02/2026 | SANTOSH KUMAR | 29.24 | 0 | 0 | 60
157 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | Assistant Engineer | Junior Engineer-1,Junior Engineer-3 | ORD/004785/2023-2024 | 130A/PSD | 14/03/2024 | 13/09/2024 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
158 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001180/2024-2025 | 2334/PD | 31/12/2024 | 01/01/2026 | BHAGABAN DAS KUMAR | 30.63 | 0 | 0 | 90
159 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000060/2025-2026 | 715/PD | 24/04/2025 | 22/08/2025 | JULI ENTERPRISE | 33.35 | 0 | 0 | 0
160 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000063/2025-2026 | 719/PD | 24/04/2025 | 22/08/2025 | TARA MAA SHAKTI CONSTRUCTION | 50.06 | 0 | 0 | 0
161 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001208/2024-2025 | 2305/PD | 31/12/2024 | 01/03/2025 | BISWAJIT SINGH | 29.87 | 0 | 0 | 0
162 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line work for zone-l of Neturia Block at Mouza - Pochhara under Purulia water supply scheme (Northern Sector ) under Purulia Division Phe. Dte | Assistant Engineer | Junior Engineer-2 | ORD/001299/2024-2025 | 439/PD | 24/03/2025 | 01/04/2026 | BISWAJIT MAJI | 16 | 0 | 0 | 65
163 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI, VII & VIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000057/2025-2026 | 712/PD | 24/04/2025 | 22/08/2025 | AMITAVA KUNDU | 49.74 | 0 | 0 | 0
164 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001205/2024-2025 | 2338/PD | 31/12/2024 | 24/02/2026 | PAMPA DAS AND COMPANY | 30.46 | 0 | 0 | 0
165 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Baram under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001209/2024-2025 | 110/PD | 21/01/2025 | 21/04/2025 | AKUL SUTRADHAR | 3.86 | 0 | 0 | 0
166 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XI, & XIII of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000037/2025-2026 | 686/PD | 24/04/2025 | 17/08/2026 | MADHU SUDAN RAKSHIT | 33.04 | 0 | 0 | 0
167 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000039/2025-2026 | 680/PD | 24/04/2025 | 22/08/2025 | M D CONSTRUCTION | 33.33 | 0 | 0 | 0
168 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII, IX & X of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000042/2025-2026 | 693/PD | 24/04/2025 | 22/08/2025 | SANTANU BANERJEE | 49.72 | 0 | 0 | 0
169 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000044/2025-2026 | 697/PD | 24/04/2025 | 22/08/2025 | M/S CONTRACTORS SYNDICATE | 33.19 | 0 | 0 | 0
170 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- X of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000163/2025-2026 | 718/PD | 24/04/2025 | 22/08/2025 | BISHAL ENTERPRISE | 16.68 | 0 | 0 | 0
171 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 15/03/2025 to 13/09/2025) | Assistant Engineer | Junior Engineer-3 | ORD/001385/2024-2025 | 131A/PSSD | 13/03/2025 | 12/09/2025 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
172 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte(w.e.f.01.09.2024 to 28.02.2025). | Assistant Engineer | Junior Engineer-3 | ORD/001137/2024-2025 | 397A/PSD | 29/08/2024 | 28/02/2025 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 100
173 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001168/2024-2025 | 2322/PD | 31/12/2024 | 01/03/2025 | AMIT CHOURASIA | 31.62 | 0 | 0 | 0
174 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- XVI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000109/2025-2026 | 694/PD | 24/04/2025 | 22/08/2025 | PROBODH CHANDRA MAJHI | 16.69 | 0 | 0 | 0
175 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) w.e.f. 15/03/2025 to 13/09/2025 | Assistant Engineer | Junior Engineer-3 | ORD/001384/2024-2025 | 131/PSSD | 13/03/2025 | 12/09/2025 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
176 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-2 | ORD/000040/2025-2026 | 691/PD | 24/04/2025 | 01/04/2026 | PRINCE INDUSTRIES ( INDIA) | 16.7 | 0 | 0 | 0
177 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XV & XVI of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000162/2025-2026 | 695/PD | 24/04/2025 | 22/08/2025 | BISHAL ENTERPRISE | 33.38 | 0 | 0 | 0
178 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. |  |  | ORD/001185/2024-2025 | 2340/PD | 31/12/2024 | 01/03/2025 | DEBANJAN SEAL | 29.19 | 0 | 0 | 0
179 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block (Zone-II) For Tentlo Mouza under Purulia Division. PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001200/2024-2025 | 2011/PD | 21/11/2024 | 31/07/2025 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 64.02 | 0 | 0 | 0
180 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Jack pushing between Sanka & Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000013/2025-2026 | 570/PD | 07/04/2025 | 31/05/2026 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0 | 0
181 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte (w.e.f.01.03.2025 to 31.08.2025) |  | Junior Engineer-3 | ORD/001383/2024-2025 | 96/PSD | 27/02/2025 | 27/08/2025 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
182 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VII & VIII of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000070/2025-2026 | 690/PD | 24/04/2025 | 22/08/2025 | SATYA NARAYAN BELTHARIA | 33.04 | 0 | 0 | 0
183 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000034/2025-2026 | 684/PD | 24/04/2025 | 22/08/2025 | GANGULY ENTERPRISES | 33.21 | 0 | 0 | 0
184 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII & IX of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000035/2025-2026 | 685/PD | 24/04/2025 | 22/08/2025 | SEKH ABBAS | 33.39 | 0 | 0 | 0
185 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII & XIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/000036/2025-2026 | 687/PD | 24/04/2025 | 20/12/2025 | BASANTA PARAMANIK | 33.34 | 0 | 0 | 0
186 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001276/2024-2025 | 337/PD | 11/03/2025 | 10/05/2025 | SAZID HOSSEN ANSARI | 24.7 | 0 | 0 | 0
187 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI, VII of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000052/2025-2026 | 707/PD | 24/04/2025 | 22/08/2025 | SANTOSH KUMAR | 33.33 | 0 | 0 | 0
188 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000053/2025-2026 | 708/PD | 24/04/2025 | 22/08/2025 | SUDHANSHU OJHA | 16.6 | 0 | 0 | 0
189 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- IV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000047/2025-2026 | 701/PD | 24/04/2025 | 22/08/2025 | CHINMOY SEN | 16.58 | 0 | 0 | 0
190 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XIV & XV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000048/2025-2026 | 702/PD | 24/04/2025 | 22/08/2025 | CHANDAN CHATTERJEE | 33.16 | 0 | 0 | 0
191 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001277/2024-2025 | 336/PD | 10/03/2025 | 09/05/2025 | SAZID HOSSEN ANSARI | 24.78 | 0 | 0 | 0
192 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I & III of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000031/2025-2026 | 677/PD | 24/04/2025 | 22/08/2025 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0 | 0
193 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000032/2025-2026 | 679/PD | 24/04/2025 | 22/08/2025 | BHAGABAN DAS KUMAR | 16.55 | 0 | 0 | 0
194 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IX & X of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000033/2025-2026 | 681/PD | 24/04/2025 | 22/08/2025 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0 | 0
195 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V of Santuri Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000046/2025-2026 | 700/PD | 24/04/2025 | 22/08/2025 | MAA TARA CONSTRUCTION | 16.7 | 0 | 0 | 0
196 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000054/2025-2026 | 709/PD | 24/04/2025 | 22/08/2025 | SINGHA ENTERPRISE | 50.03 | 0 | 0 | 0
197 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- XI of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000058/2025-2026 | 713/PD | 24/04/2025 | 22/08/2025 | CHANCHAL MISHRA | 16.66 | 0 | 0 | 0
198 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Left out HDPE pipe line and pushing of 600mm dia MS pre cast pipe and 100 mm dia GI water carrier pipe by hydraulic jacking method across Purulia Ranchi NH Road for laying distribution line in connection with Jal Jeevan Mission at for Zone-III of Purulia -I block for Belkuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-1 | ORD/001305/2024-2025 | 444/PD | 24/03/2025 | 01/01/2026 | GOUTAM CHAKRABORTY | 64.98 | 0 | 0 | 75
199 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000055/2025-2026 | 710/PD | 24/04/2025 | 22/08/2025 | DEBSHANKAR LAYEK | 16.62 | 0 | 0 | 0
200 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-II, III & IV of Raghunathpur-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000067/2025-2026 | 724/PD | 24/04/2025 | 22/08/2025 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 50.1 | 0 | 0 | 0
201 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Allied work of laying Distribution pipe line and other allied works for Zone-III of Santuri Block Purulia pipe Water Supply Scheme (Northern Sector ) under Purulia Division PHE Dte Part-C ( Mouza- Brindabanpur, Vill.- Asharikand ) |  |  | ORD/000250/2025-2026 | 1117/PD | 23/06/2025 | 07/08/2025 | M/S MONDAL ENTERPRISE | 55.57 | 0 | 0 | 0
202 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Kashipur (Zone - VII & XII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000218/2025-2026 | 1082/PD | 17/06/2025 | 12/06/2026 | MADHU SUDAN RAKSHIT | 28.7 | 0 | 0 | 0
203 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Neturia (Zone - I) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000208/2025-2026 | 1067/PD | 17/06/2025 | 15/10/2025 | SAANVI CONSTRUCTION | 14.4 | 0 | 0 | 0
204 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VII of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000059/2025-2026 | 714/PD | 24/04/2025 | 22/08/2025 | CHANCHAL MISHRA | 16.65 | 0 | 0 | 0
205 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Para (Zone - X&XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000231/2025-2026 | 1077/PD | 17/06/2025 | 15/10/2025 | AMRIT CONSTRUCTION | 28.63 | 0 | 0 | 0
206 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-II (Zone - II, III & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000219/2025-2026 | 1083/PD | 17/06/2025 | 15/10/2025 | MAHATO CONSTRUCTION | 43.05 | 0 | 0 | 0
207 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000061/2025-2026 | 716/PD | 24/04/2025 | 22/08/2025 | TOTAL INFRA | 50.08 | 0 | 0 | 0
208 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000064/2025-2026 | 721/PD | 24/04/2025 | 21/04/2026 | M/S S & P CONSTRUCTION | 50.09 | 0 | 0 | 0
209 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1,Junior Engineer-2 | ORD/000066/2025-2026 | 723/PD | 24/04/2025 | 01/04/2026 | PRINCE INDUSTRIES ( INDIA) | 50.11 | 0 | 0 | 0
210 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XI of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000164/2025-2026 | 706/PD | 24/04/2025 | 22/08/2025 | B.M ENTERPRISE | 16.66 | 0 | 0 | 0
211 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000199/2025-2026 | 1058/PD | 17/06/2025 | 01/01/2026 | SWAPAN MANDAL | 23.25 | 0 | 0 | 80
212 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V & VI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte |  |  | ORD/000069/2025-2026 | 678/PD | 24/04/2025 | 22/08/2025 | AIM CONSTRUCTION | 33.38 | 0 | 0 | 0
213 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - II & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000211/2025-2026 | 1072/PD | 17/06/2025 | 15/10/2025 | SUBHAS CHANDRA MAHATO | 28.7 | 0 | 0 | 0
214 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Hura (Zone - III & IX) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000212/2025-2026 | 1073/PD | 17/06/2025 | 15/10/2025 | MOHOR CONSTRUCTION | 28.69 | 0 | 0 | 0
215 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Hura (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000214/2025-2026 | 1075/PD | 17/06/2025 | 15/10/2025 | MS D.PALIT AND CO. | 28.8 | 0 | 0 | 0
216 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Pushing of 600mm dia RCC pre cast pipe and 200 mm dia MS water carrier pipe by hydraulic jacking method across Pirargaria Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and Installation of 2(two) nos of Tubewell through DTH process at OHR site of Zone-III of Purulia-II Block Purulia piped W/S Scheme( Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000254/2025-2026 | 929/PD | 27/05/2025 | 01/01/2026 | SOUVIK MANDAL | 13.1 | 0 | 0 | 60
217 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Raghunathpur-I (Zone - I & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000255/2025-2026 | 999/PD | 11/06/2025 | 09/10/2025 | DILIP MISHRA | 28.4 | 0 | 0 | 0
218 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Santuri (Zone - I, VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000220/2025-2026 | 1084/PD | 17/06/2025 | 15/10/2025 | CHATTERJEE CONSTRUCTION | 43.27 | 0 | 0 | 0
219 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall at OHR(200 cum)site of ZONE III at Dhunari Mouza of Purulia 2 Block under Purulia piped water supply scheme( Northern Sector) under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000196/2025-2026 | 1056/PD | 17/06/2025 | 24/06/2026 | BISWAJIT MAJI | 16.97 | 0 | 0 | 0
220 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - IV & VII) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000209/2025-2026 | 1069/PD | 17/06/2025 | 15/10/2025 | MANTAJ ANSARI | 28.8 | 0 | 0 | 0
221 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Para (Zone - V & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000215/2025-2026 | 1076/PD | 17/06/2025 | 15/10/2025 | M/S CONTRACTORS SYNDICATE | 28.66 | 0 | 0 | 0
222 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000244/2025-2026 | 689/PD | 24/04/2025 | 22/08/2025 | SUMANTA GHOSH | 49.86 | 0 | 0 | 0
223 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V & VII of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000245/2025-2026 | 698/PD | 24/04/2025 | 22/08/2025 | SUMANTA GHOSH | 33.24 | 0 | 0 | 0
224 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XVI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000062/2025-2026 | 717/PD | 24/04/2025 | 22/08/2025 | JOGMAYA CONSTRUCTION | 16.54 | 0 | 0 | 0
225 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Continuation Order for the Work of Jack pushing between Sanka &Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000259/2025-2026 | 1208/PD | 08/07/2025 | 31/05/2026 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0 | 0
226 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000326/2025-2026 | 1384/PD | 29/07/2025 | 26/11/2025 | ZAKIR HOSSIN MONDAL | 28.83 | 0 | 0 | 0
227 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - X & XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000329/2025-2026 | 1388/PD | 29/07/2025 | 26/11/2025 | SEKH IRFAN | 28.69 | 0 | 0 | 0
228 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IX of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000363/2025-2026 | 1523/PD | 19/08/2025 | 17/12/2025 | AMIT PATHAK | 16.61 | 0 | 0 | 0
229 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000364/2025-2026 | 1524/PD | 19/08/2025 | 17/12/2025 | MAHATO CONSTRUCTION | 49.86 | 0 | 0 | 0
230 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-II of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000365/2025-2026 | 1525/PD | 19/08/2025 | 17/12/2025 | DILIP MISHRA | 16.33 | 0 | 0 | 0
231 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, & III of Manbazar-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000366/2025-2026 | 1526/PD | 19/08/2025 | 17/12/2025 | SAZID HOSSEN ANSARI | 33.38 | 0 | 0 | 0
232 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, III of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. (Group-B) |  |  | ORD/000367/2025-2026 | 1527/PD | 19/08/2025 | 17/12/2025 | BABA LOKNATH ENTERPRISE | 32.99 | 0 | 0 | 0
233 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Manbazar-I (Zone - II & IV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000560/2025-2026 | 1078/PD | 17/06/2025 | 15/10/2025 | M/S MECHANICAL AND CIVIL | 28.8 | 0 | 0 | 0
234 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - XV & XVII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000399/2025-2026 | 1580/PD | 20/08/2025 | 18/12/2025 | MAHATO CONSTRUCTION | 28.7 | 0 | 0 | 0
235 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000480/2025-2026 | 1522/PD | 19/08/2025 | 17/12/2025 | PRATIMA CONSTRUCTION | 50.06 | 0 | 0 | 0
236 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Puncha (Zone - II) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000561/2025-2026 | 1068/PD | 17/06/2025 | 15/10/2025 | M/S SAMARESH SARKAR | 13.81 | 0 | 0 | 0
237 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - IX & X) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000327/2025-2026 | 1390/PD | 29/07/2025 | 26/11/2025 | PRASENJIT CHOUDHURY | 28.56 | 0 | 0 | 0
238 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - IV & V) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. |  |  | ORD/000328/2025-2026 | 1389/PD | 29/07/2025 | 26/11/2025 | DALIM ENTERPRISE | 28.27 | 0 | 0 | 0
239 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Repairing and Renovation of Boundary wall including other allied works at Kanchanpur boosting site in connection with Jal Jeevan Mission (JJM) at Kudagara under Purulia W/S Scheme (Northern Sector) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-2 | ORD/000500/2023-2024 | 1332/PD | 08/09/2023 | 08/10/2023 | MITRA CONSTRUCTION | 2.56 | 2.56 | 99.86 | 100
240 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300m) | Assistant Engineer | Junior Engineer-4 | ORD/001827/2023-2024 | 65/PD | 10/01/2024 | 04/01/2025 | WATER TECH | 40.82 | 0 | 0 | 100
241 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | Assistant Engineer | Junior Engineer-4 | ORD/001833/2023-2024 | 71/PD | 10/01/2024 | 29/03/2025 | SUJIT CHAKRABORTY | 39.58 | 0 | 0 | 100
242 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - III & IV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 260 m) | Assistant Engineer | Junior Engineer,Junior Engineer-4 | ORD/002303/2023-2024 | 193/PD | 02/02/2024 | 28/03/2025 | JULI ENTERPRISE | 36.69 | 9.17 | 25 | 100
243 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Construction of Boundary wall, RCC Pillar & Sinking of 1(one) no tubewellat OHR Site of Zone - XIV(Mohulkoka) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001199/2024-2025 | 1994/PD | 20/11/2024 | 19/01/2025 | PURNA CHANDRA TEWARI | 4.83 | 0 | 0 | 95
244 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001143/2024-2025 | 2297/PD | 31/12/2024 | 07/10/2025 | SANJAY KUMAR NARSARIA | 29.31 | 0 | 0 | 100
Total | [13 empty] | 47063.66 | 5131.81 | 10.9