## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 300 CUM andstaging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone-I of Purulia-2 block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-5) | Assistant Engineer |  | ORD/000835/2023-2024 | 1427/PD | 29/09/2023 | 25/06/2024 | HANNAN BUILDERS PRIVATE LIMITED | 441.37 | 0 | 0 | 0
2 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 500 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-V Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | Assistant Engineer |  | ORD/000896/2023-2024 | 1558/PD | 18/10/2023 | 14/07/2024 | M/S TARUN KUMAR PATRA | 869.94 | 0 | 0 | 0
3 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kalipur mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001261/2023-2024 | 1568/PD | 26/10/2023 | 10/12/2023 | PRADIPTA CHOUDHURY | 1.3 | 0 | 0 | 0
4 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line including FHTC and other allied work for Zone-III of Purulia-I block for Simulbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001330/2023-2024 | 1713/PD | 04/12/2023 | 02/02/2024 | THE STAR & CO. | 41.68 | 0 | 0 | 0
5 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -H , Mouza - Nabaghanadi alias Patharbad&Khayerbasia Chak] | Assistant Engineer |  | ORD/001357/2023-2024 | 1727/PD | 04/12/2023 | 02/02/2024 | IKBAL CONSTRUCTION | 19.32 | 0 | 0 | 0
6 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 145 mtr.) | Assistant Engineer |  | ORD/001457/2023-2024 | 1774/PD | 08/12/2023 | 06/02/2024 | IKBAL CONSTRUCTION | 19.41 | 0 | 0 | 0
7 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Dulmi mouza under Purulia Water Supply Scheme ( Northern Sector) Under Purulia Division , PHE Dte. | Assistant Engineer |  | ORD/001251/2023-2024 | 1699/PD | 30/11/2023 | 29/01/2024 | SUNNY ELECTRIC CO | 72.3 | 0 | 0 | 0
8 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1127/PD | 17/08/2023 | 17/08/2023 | Resource Division | 19846.99 | 0 | 0 | 0
9 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone VI H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000287/2023-2024 | 1146/PD | 17/08/2023 | 16/09/2023 | HUSSAIN CONSTRUCTION | 21.51 | 11.11 | 51.67 | 70
10 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (SL-16) | Assistant Engineer | Junior Engineer | ORD/000780/2023-2024 | 1418/PD | 29/09/2023 | 22/03/2025 | KOUSHIK CHATTERJEE | 274.47 | 82.14 | 29.93 | 70
11 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL-5) | Assistant Engineer | Junior Engineer-3 | ORD/000783/2023-2024 | 1420/PD | 29/09/2023 | 04/08/2025 | MS D.PALIT AND CO. | 373.13 | 140.63 | 37.69 | 50
12 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | Assistant Engineer | Junior Engineer | ORD/000836/2023-2024 | 1425/PD | 29/09/2023 | 01/09/2025 | SUJIT SAHANA | 274.06 | 60.38 | 22.03 | 22
13 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012), Laying of Distribution Pipe line & providing Functional Household Tap Connection (FHTC) including other allied works, for Zone- I of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A, Mouza - Mohanpur] | Assistant Engineer | Junior Engineer-3 | ORD/001345/2023-2024 | 697/PD | 22/05/2023 | 01/04/2025 | KHITISH CHANDRA PATHAK | 93.94 | 11.86 | 12.62 | 40
14 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Maguria mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001257/2023-2024 | 1515/PD | 16/10/2023 | 30/11/2023 | SOUVIK MANDAL | 45.44 | 0 | 0 | 0
15 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Kukurgarya mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-1 | ORD/001332/2023-2024 | 1715/PD | 04/12/2023 | 27/11/2025 | HIRAK KUMAR SAO | 72.48 | 3.97 | 5.48 | 65
16 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) with allied works for purulia water supply scheme.(Location:-Block-Purulia -I, Zone-III) for Northern Zone. | Assistant Engineer | Junior Engineer-1 | ORD/001334/2023-2024 | 1717/PD | 04/12/2023 | 30/08/2024 | M/S RAJ KUMAR KHAN | 96.67 | 45.04 | 46.59 | 30
17 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Raibandh Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001258/2023-2024 | 1561/PD | 18/10/2023 | 02/12/2023 | CHATTERJEE CONSTRUCTION | 12.16 | 0 | 0 | 0
18 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Dulmi Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001265/2023-2024 | 1604/PD | 01/11/2023 | 16/12/2023 | CHANCHAL MISHRA | 8.03 | 0 | 0 | 0
19 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Simulia mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001262/2023-2024 | 1600/PD | 31/10/2023 | 15/12/2023 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 31.76 | 0 | 0 | 0
20 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ghagharjuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001333/2023-2024 | 1716/PD | 04/12/2023 | 13/03/2024 | BALAJI UDDYOG | 93.8 | 0 | 0 | 0
21 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Chakda mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001259/2023-2024 | 1562/PD | 18/10/2023 | 02/12/2023 | M DHARA & BROTHERS | 38.95 | 0 | 0 | 0
22 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme ( Northern Sector )at Purulia-I Block(Zone-VI) For Bhuinadi Mouza under Purulia Division. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001447/2023-2024 | 1763/PD | 07/12/2023 | 05/02/2024 | MOONLIGHT HOUSE | 49.26 | 0 | 0 | 0
23 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VI of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001477/2023-2024 | 1788/PD | 08/12/2023 | 06/02/2024 | SOUVIK MANDAL | 20.95 | 16.46 | 78.57 | 80
24 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including providing FHTC including other allied work allied works for purulia water supply scheme.(Northern Sector ) at Purulia -I Block (Zone-IV) for Hulka Mouza under Purulia Division PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001495/2023-2024 | 1794/PD | 08/12/2023 | 01/04/2025 | SUBRATA MAHAPATRA | 82.06 | 0 | 0 | 65
25 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (part) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001637/2023-2024 | 1826/PD | 12/12/2023 | 10/02/2024 | BARI ENTERPRISE | 29.81 | 0 | 0 | 0
26 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1, Zone-VI) for Northern Zone | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001481/2023-2024 | 1792/PD | 08/12/2023 | 03/09/2024 | SADHAN GORAIN | 74.45 | 0 | 0 | 0
27 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ketuabera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | Assistant Engineer |  | ORD/001331/2023-2024 | 1714/PD | 04/12/2023 | 02/02/2024 | M/S SB CONSTRUCTION | 47.7 | 0 | 0 | 0
28 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Talberya (20%)] | Assistant Engineer | Junior Engineer | ORD/001356/2023-2024 | 1726/PD | 04/12/2023 | 02/02/2024 | VINCI CONSTRUCTION | 12.23 | 5.76 | 47.1 | 60
29 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Gopalpur, Mahukura] | Assistant Engineer | Junior Engineer | ORD/001448/2023-2024 | 1807/PD | 08/12/2023 | 22/01/2024 | S. S. ENTERPRISE | 30.88 | 18.57 | 60.12 | 64
30 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer | Junior Engineer | ORD/001462/2023-2024 | 1777/PD | 08/12/2023 | 06/02/2024 | BHUTNATH MISHRA | 23.66 | 16.73 | 70.71 | 100
31 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Shibdi Mouza (Zone-VI) Under Purulia Divn PHE DTE | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001482/2023-2024 | 1793/PD | 08/12/2023 | 22/01/2024 | S.PATHAK & CO. | 14.48 | 0 | 0 | 0
32 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001470/2023-2024 | 1783/PD | 08/12/2023 | 21/03/2025 | SUBRATA SINGHADEO | 20.81 | 14.86 | 71.4 | 65
33 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Belguma mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer | Junior Engineer | ORD/001256/2023-2024 | 1514/PD | 16/10/2023 | 30/11/2023 | SEKH ABBAS | 28.09 | 0 | 0 | 0
34 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Golbera mouza (Zone-VII) Under Purulia Divn PHE DTE | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001483/2023-2024 | 1795/PD | 08/12/2023 | 22/01/2024 | SEKH ABBAS | 19.55 | 0 | 0 | 0
35 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-V) for Mahalitora mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001692/2023-2024 | 1867/PD | 21/12/2023 | 19/02/2024 | BHAGABANDAS KUMAR | 15.2 | 0 | 0 | 0
36 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-VIII) for Rudra mouza Under Purulia Divn PHE DTE. | Assistant Engineer |  | ORD/001615/2023-2024 | 1827/PD | 12/12/2023 | 10/02/2024 | SUSANTA KR DUTTA | 24.58 | 0 | 0 | 0
37 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1 , Zone-V ) for Northern Zone. | Assistant Engineer | Junior Engineer-2 | ORD/001616/2023-2024 | 1828/PD | 12/12/2023 | 07/09/2024 | M/S SB CONSTRUCTION | 70.03 | 0 | 0 | 60
38 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. |  |  | ORD/001819/2023-2024 | 51/PD | 09/01/2024 | 09/03/2024 | ANUP KUMAR SAHA | 148.36 | 0 | 0 | 0
39 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000466/2023-2024 | 471/PMD | 14/03/2024 | 14/03/2025 | SUNRISE ENGINEERING CORPORATION | 19.89 | 0 | 0 | 0
40 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000470/2023-2024 | 496/PMD | 15/03/2024 | 15/03/2025 | DEY ENTERPRISE, HOWRAH | 474.14 | 0 | 0 | 0
41 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000467/2023-2024 | 493/PMD | 15/03/2024 | 15/03/2025 | A G ENTERPRISE | 413.21 | 0 | 0 | 0
42 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000472/2023-2024 | 498/PMD | 15/03/2024 | 15/03/2025 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 103.28 | 0 | 0 | 0
43 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000476/2023-2024 | 502/PMD | 15/03/2024 | 15/03/2025 | AHALYA ENGINEERING WORKS | 206.45 | 0 | 0 | 0
44 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000663/2024-2025 | 1669/PMD | 05/12/2024 | 05/12/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.32 | 0 | 0 | 0
45 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000664/2024-2025 | 1670/PMD | 05/12/2024 | 05/12/2025 | SEN BROTHERS | 2.77 | 0 | 0 | 0
46 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000092/2024-2025 | 1050/PMD | 28/06/2024 | 28/06/2025 | BISHWANATH NANDI | 22.86 | 0 | 0 | 0
47 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Santuri Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000094/2024-2025 | 1052/PMD | 28/06/2024 | 28/06/2025 | NUPUR CHANDRA HALDER | 22.16 | 0 | 0 | 0
48 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2024-2025 | 1018/PMD | 25/06/2024 | 25/06/2025 | TAPAN KUMAR DEY | 53.82 | 0 | 0 | 0
49 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000083/2024-2025 | 1019/PMD | 25/06/2024 | 25/06/2025 | JAL PRAVAHIKA PVT. LTD | 41.16 | 0 | 0 | 0
50 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Kashipur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000085/2024-2025 | 1021/PMD | 25/06/2024 | 25/06/2025 | DEBJYOTI BASU | 53.82 | 0 | 0 | 0
51 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000086/2024-2025 | 1022/PMD | 25/06/2024 | 25/06/2025 | SANTU MITRA | 12.66 | 0 | 0 | 0
52 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Para Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000088/2024-2025 | 1024/PMD | 25/06/2024 | 25/06/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 56.98 | 0 | 0 | 0
53 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-XV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/004306/2023-2024 | 503/PD | 16/03/2024 | 15/05/2024 | MANTAJ ANSARI | 25.17 | 0 | 0 | 0
54 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Joypur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000084/2024-2025 | 1020/PMD | 25/06/2024 | 25/06/2025 | A G ENTERPRISE | 34.82 | 0 | 0 | 0
55 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000091/2024-2025 | 1049/PMD | 28/06/2024 | 28/06/2025 | SAIBAL SARKAR | 47.49 | 0 | 0 | 0
56 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000032/2024-2025 | 945/PMD | 19/06/2024 | 19/06/2025 | ASHOKE ADHIKARY | 39.78 | 0 | 0 | 0
57 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Neturia Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000087/2024-2025 | 1023/PMD | 25/06/2024 | 25/06/2025 | SEN BROTHERS | 6.33 | 0 | 0 | 0
58 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000028/2024-2025 | 941/PMD | 19/06/2024 | 19/06/2025 | WEST BENGAL ENGINEERING CO | 568.2 | 0 | 0 | 0
59 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003531/2023-2024 | 356/PD | 04/03/2024 | 03/05/2024 | CHOUDHURY STONE CRUSHING | 25.14 | 19.89 | 79.11 | 85
60 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000480/2023-2024 | 506/PMD | 15/03/2024 | 15/03/2025 | PREMNATH MITRA | 206.89 | 0 | 0 | 0
61 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000462/2023-2024 | 467/PMD | 14/03/2024 | 14/03/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 59.66 | 0 | 0 | 0
62 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000464/2023-2024 | 469/PMD | 14/03/2024 | 14/03/2025 | SEN BROTHERS | 19.88 | 0 | 0 | 0
63 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-XIV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003493/2023-2024 | 348/PD | 04/03/2024 | 03/05/2024 | UTTAM KUMAR DUTTA | 19.44 | 0 | 0 | 0
64 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000461/2023-2024 | 466/PMD | 14/03/2024 | 14/03/2025 | DEBJYOTI BASU | 59.65 | 0 | 0 | 0
65 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000465/2023-2024 | 470/PMD | 14/03/2024 | 14/03/2025 | NUPUR CHANDRA HALDER | 69.62 | 0 | 0 | 0
66 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000485/2023-2024 | 474/PMD | 14/03/2024 | 14/03/2025 | SANTU MITRA | 9.94 | 0 | 0 | 0
67 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000489/2023-2024 | 477/PMD | 14/03/2024 | 14/03/2025 | PINTU DEY | 19.89 | 0 | 0 | 0
68 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000469/2023-2024 | 495/PMD | 15/03/2024 | 15/03/2025 | EASTERN INDIA SALES AND SERVICE | 413.27 | 0 | 0 | 0
69 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000473/2023-2024 | 499/PMD | 15/03/2024 | 15/03/2025 | JAL PRAVAHIKA PVT. LTD | 51.65 | 0 | 0 | 0
70 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000475/2023-2024 | 501/PMD | 15/03/2024 | 15/03/2025 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 309.93 | 0 | 0 | 0
71 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Disinfection Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000463/2023-2024 | 468/PMD | 14/03/2024 | 14/03/2025 | DAS ENTERPRISE | 49.68 | 0 | 0 | 0
72 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000483/2023-2024 | 472/PMD | 14/03/2024 | 14/03/2025 | M/S A.D. CONCERN | 9.94 | 0 | 0 | 0
73 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000488/2023-2024 | 476/PMD | 14/03/2024 | 14/03/2025 | M/S D. PALIT & CO. | 19.89 | 0 | 0 | 0
74 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000484/2023-2024 | 473/PMD | 14/03/2024 | 14/03/2025 | SAIBAL SARKAR | 39.78 | 0 | 0 | 0
75 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000487/2023-2024 | 475/PMD | 14/03/2024 | 14/03/2025 | JAL PRAVAHIKA PVT. LTD | 39.76 | 0 | 0 | 0
76 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000478/2023-2024 | 504/PMD | 15/03/2024 | 15/03/2025 | TAPAN KUMAR DEY | 257.9 | 0 | 0 | 0
77 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000479/2023-2024 | 505/PMD | 15/03/2024 | 15/03/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 154.78 | 0 | 0 | 0
78 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003521/2023-2024 | 349/PD | 04/03/2024 | 03/05/2024 | SUMIT KUMAR MITRA | 19.31 | 7.39 | 38.28 | 60
79 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/003535/2023-2024 | 359/PD | 04/03/2024 | 03/05/2024 | SAZID HOSSEN ANSARI | 25.1 | 0 | 0 | 0
80 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER |  | ORD/000490/2023-2024 | 478/PMD | 14/03/2024 | 14/03/2025 | COMBINE ENTERPRISES | 29.84 | 0 | 0 | 0
81 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) |  |  | ORD/003960/2023-2024 | 502/PD | 16/03/2024 | 15/05/2024 | SUMIT KUMAR MITRA | 23.95 | 0 | 0 | 0
82 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector ) at Purulia-I Block(Zone-VII) For Kalidasdi Mouza under Purulia Division. PHE Dte. | Assistant Engineer(HQ) |  | ORD/003987/2023-2024 | 492/PD | 16/03/2024 | 15/05/2024 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 34.47 | 0 | 0 | 0
83 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-II) For Bhalumara Mouza under Purulia Division. PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer,Junior Engineer-4 | ORD/004026/2023-2024 | 490/PD | 16/03/2024 | 28/08/2024 | RAHIBUDDIN MONDAL | 23.46 | 6.14 | 26.18 | 50
84 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Under Northern Sector W/S Scheme) | Assistant Engineer | Junior Engineer-2 | ORD/003956/2023-2024 | 498/PD | 16/03/2024 | 15/05/2024 | SEKH ABBAS | 25.08 | 0 | 0 | 0
85 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Shyamdasdi Alias shyampur Mouza under Purulia Division. PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/003988/2023-2024 | 530/PD | 16/03/2024 | 15/05/2024 | M/S ACHARJEE CONSTRUCTION | 33.22 | 0 | 0 | 0
86 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000030/2024-2025 | 943/PMD | 19/06/2024 | 19/06/2025 | ORIENTAL ENGINEERING CO. | 723.12 | 0 | 0 | 0
87 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Puncha Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000089/2024-2025 | 1025/PMD | 25/06/2024 | 25/06/2025 | SUBRATA DUTTA | 22.15 | 0 | 0 | 0
88 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000670/2024-2025 | 1676/PMD | 05/12/2024 | 05/12/2025 | ASHOKE ADHIKARY | 2.22 | 0 | 0 | 0
89 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000672/2024-2025 | 1678/PPMD | 05/12/2024 | 05/12/2025 | PINTU DEY | 1.11 | 0 | 0 | 0
90 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000031/2024-2025 | 944/PMD | 19/06/2024 | 19/06/2025 | MAHADEV ENTERPRISE | 561.07 | 0 | 0 | 0
91 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and Providing FHTC including other allied work for Nadiyara mouza ( Zone-V Part-B) Northern Zone at Purulia-I Block under Purulia Water Supply Scheme Under Purulia Division ,PHE Dte. |  |  | ORD/000246/2024-2025 | 1136/PD | 18/06/2024 | 17/08/2024 | NANIGOPAL DEY | 74.58 | 0 | 0 | 0
92 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000090/2024-2025 | 1048/PMD | 28/06/2024 | 28/06/2025 | ASHOKE ADHIKARY | 25.32 | 0 | 0 | 0
93 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000093/2024-2025 | 1051/PMD | 28/06/2024 | 28/06/2025 | S. PATHAK & CO. | 15.82 | 0 | 0 | 0
94 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Para and Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000668/2024-2025 | 1674/PMD | 05/12/2024 | 05/12/2025 | M/S A.D. CONCERN | 2.77 | 0 | 0 | 0
95 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia I and Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000669/2024-2025 | 1675/PMD | 05/12/2024 | 05/12/2025 | SANTU MITRA | 2.77 | 0 | 0 | 0
96 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000671/2024-2025 | 1677/PMD | 05/12/2024 | 05/12/2025 | M/S D. PALIT & CO. | 1.11 | 0 | 0 | 0
97 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000673/2024-2025 | 1679/PMD | 05/12/2024 | 05/12/2025 | COMBINE ENTERPRISES | 1.66 | 0 | 0 | 0
98 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000665/2024-2025 | 1671/PMD | 05/12/2024 | 05/12/2025 | SEN BROTHERS | 1.11 | 0 | 0 | 0
99 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Internal illumination and outdoor lighting arrangement and other allied works for Augmentation of Balitora Water Supply Scheme under Purulia Mechanical Division. PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000466/2024-2025 | 1292/PMD | 30/08/2024 | 29/10/2024 | PREMNATH MITRA | 7.83 | 0 | 0 | 2
100 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000662/2024-2025 | 1668/PMD | 05/12/2024 | 05/12/2025 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0 | 0
101 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000029/2024-2025 | 942/PMD | 19/06/2024 | 19/06/2025 | CONCORD ENGINEERING | 516.53 | 0 | 0 | 0
102 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000666/2024-2025 | 1672/PMD | 05/12/2024 | 05/12/2025 | NUPUR CHANDRA HALDER | 3.88 | 0 | 0 | 0
103 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone VII H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 1147/PD | 17/08/2023 | 16/09/2023 | GANGULY ENTERPRISES | 16.72 | 14.99 | 89.64 | 100
104 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone V H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2023-2024 | 1145/PD | 17/08/2023 | 16/09/2023 | SUMIT KUMAR MITRA | 15.1 | 13.61 | 90.15 | 100
105 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone III H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2023-2024 | 1143/PD | 17/08/2023 | 16/09/2023 | BABA LOKNATH ENTERPRISE | 18.56 | 18.5 | 99.69 | 100
106 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone II H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000290/2023-2024 | 1142/PD | 17/08/2023 | 16/09/2023 | SANTOSH KUMAR | 15.35 | 15.11 | 98.46 | 100
107 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - V of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 165 mtr.) | Assistant Engineer | Junior Engineer | ORD/001352/2023-2024 | 1725/PD | 04/12/2023 | 02/02/2024 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 21.47 | 18.37 | 85.55 | 100
108 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - I of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 145 mtr.) | Assistant Engineer | Junior Engineer-1 | ORD/001338/2023-2024 | 1721/PD | 04/12/2023 | 02/02/2024 | S.PATHAK & CO. | 19.47 | 16.58 | 85.15 | 100
109 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - IV of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 115 mtr.) | Assistant Engineer | Junior Engineer | ORD/001350/2023-2024 | 1724/PD | 04/12/2023 | 02/02/2024 | MOUSUMI BANERJEE | 16.44 | 14.21 | 86.41 | 75
110 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | Assistant Engineer | Junior Engineer | ORD/001450/2023-2024 | 1768/PD | 08/12/2023 | 06/02/2024 | CHAIL CONSTRUCTION | 21.95 | 15.88 | 72.38 | 100
111 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer | Junior Engineer-1 | ORD/001449/2023-2024 | 1767/PD | 08/12/2023 | 08/03/2025 | PRINCE INDUSTRIES ( INDIA) | 21.48 | 0 | 0 | 100
112 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | Assistant Engineer |  | ORD/001451/2023-2024 | 1769/PD | 08/12/2023 | 06/02/2024 | M/S SAYAK BHATTACHARYA | 21.97 | 21.95 | 99.94 | 100
113 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer | Junior Engineer | ORD/001463/2023-2024 | 1778/PD | 08/12/2023 | 06/02/2024 | M/S KHAN ENTERPRISE | 21.46 | 14.38 | 67.01 | 60
114 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer | ORD/001471/2023-2024 | 1784/PD | 08/12/2023 | 06/02/2024 | BISWAJIT MAJI | 20.94 | 19.66 | 93.92 | 100
115 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - V of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer | Junior Engineer | ORD/001453/2023-2024 | 1771/PD | 08/12/2023 | 06/02/2024 | SUBHAS CHANDRA MAHATO | 22.82 | 18.97 | 83.11 | 98
116 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer | Junior Engineer | ORD/001456/2023-2024 | 1773/PD | 08/12/2023 | 06/02/2024 | NANIGOPAL DEY | 23.75 | 13.52 | 56.94 | 10
117 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 125 mtr.) | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 1770/PD | 08/12/2023 | 06/02/2024 | CHINMOY SEN | 17.39 | 17.36 | 99.78 | 70
118 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - X of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer | ORD/001460/2023-2024 | 1776/PD | 08/12/2023 | 06/02/2024 | CHANCHAL MISHRA | 20.96 | 16.07 | 76.67 | 97
119 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 65 mtr.) | Assistant Engineer | Junior Engineer | ORD/001466/2023-2024 | 1780/PD | 08/12/2023 | 06/02/2024 | PURNA CHANDRA TEWARI | 11.43 | 9.73 | 85.15 | 98
120 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying of Collecting line from Kanshabati Riverbed to Harekishtapur Riversite Pump House under Manbazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-3 | ORD/001485/2023-2024 | 1798/PD | 08/12/2023 | 06/02/2024 | RAJAT KARMAKAR | 24.44 | 23.1 | 94.48 | 100
121 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-3 | ORD/001473/2023-2024 | 1785/PD | 08/12/2023 | 25/11/2024 | KM ENTERPRISES | 20.98 | 5.55 | 26.47 | 100
122 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Fencing work with concrete pillars for 15 Nos vested land for Northern & Southern Sector water supply scheme Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000452/2024-2025 | 1513/PD | 27/08/2024 | 11/10/2024 | CHATTERJEE CONSTRUCTION | 5.9 | 5.86 | 99.33 | 100
123 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Making arrangement of interconnection at distribution pipeline with newly laid distribution pipeline & installation of sluice valves on pipeline at jiudaru mouza under Kotshila W/S at Purulia Water Supply scheme (Northern Sector) under Purulia Division,PHEDte. | Assistant Engineer | Junior Engineer-3 | ORD/000347/2024-2025 | 1377/PD | 25/07/2024 | 23/09/2024 | GOUTAM CHAKRABORTY | 12.21 | 11.85 | 97.05 | 100
124 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003524/2023-2024 | 351/PD | 04/03/2024 | 03/05/2024 | JAHANGIR ANSARI | 19.45 | 18.94 | 97.4 | 100
125 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division-under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003523/2023-2024 | 350/PD | 04/03/2024 | 03/05/2024 | BHAGABANDAS KUMAR | 22.86 | 17.62 | 77.07 | 100
126 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) | Assistant Engineer | Junior Engineer-2 | ORD/003957/2023-2024 | 499/PD | 16/03/2024 | 15/05/2024 | BANERJEE CONSTRUCTION | 20.41 | 5.08 | 24.89 | 100
127 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Sinking of 3 nos New 200 mm dia horizontal tube-well and laying of 100mm dia GI pipe collecting main from RBT to common manifold at river side of Satra Head Works site of Purulia water supply scheme (Northern Sector) under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000206/2024-2025 | 1064/PD | 07/06/2024 | 22/07/2024 | SUBODH PRAMANIK | 32.54 | 17.96 | 55.19 | 100
128 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | New sinking of 2(Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line of Puncha W/S at Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000346/2024-2025 | 1376/PD | 25/07/2024 | 24/08/2024 | SOUVIK MANDAL | 7.56 | 6.43 | 85.08 | 100
129 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 1980/PD | 18/11/2024 | 18/11/2024 | Resource Division | 9544.07 | 0 | 0 | 0
130 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 2253/PD | 19/12/2024 | 19/12/2024 | Resource Division | 8838.63 | 0 | 0 | 0
131 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 1342/PD | 24/07/2024 | 24/07/2024 | Resource Division | 1191.18 | 0 | 0 | 0
132 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050912202411333713585370XX DT.09-12-2024. |  |  | BILL/01062/2024-2025 | BP-2024-25-535 | 13/12/2024 | 13/12/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
133 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401322652788750XX DT.16-12-2024. |  |  | BILL/01078/2024-2025 | BP-2024-25-539 | 19/12/2024 | 19/12/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
134 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411410689904167XX DT.24-10-2024. |  |  | BILL/00943/2024-2025 | BP-2024-25-520 | 29/10/2024 | 29/10/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.93 | 0 | 0 | 0
135 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411113832563388047XX DT.24-10-2024. |  |  | BILL/00944/2024-2025 | BP-2024-25-521 | 29/10/2024 | 29/10/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.04 | 0 | 0 | 0
136 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401360237000585XX DT.16-12-2024. |  |  | BILL/01079/2024-2025 | BP-2024-25-538 | 19/12/2024 | 19/12/2024 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
137 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone I H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000282/2023-2024 | 1139/PD | 17/08/2023 | 01/07/2025 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 0 | 100
138 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone II H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000283/2023-2024 | 1140/PD | 17/08/2023 | 01/04/2026 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 0 | 0
139 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(Sl No. 8) | Assistant Engineer | Junior Engineer-3 | ORD/000779/2023-2024 | 1423/PD | 29/09/2023 | 22/03/2025 | KHAN ENTERPRISE | 430.24 | 100.02 | 23.25 | 20
140 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 6) | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 1429/PD | 29/09/2023 | 01/08/2025 | PRAVAT SARKAR | 406.17 | 0 | 0 | 30
141 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone- I of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 1) | Assistant Engineer | Junior Engineer | ORD/000919/2023-2024 | 1596/PD | 31/10/2023 | 29/03/2026 | PRINCE INDUSTRIES ( INDIA) | 405.49 | 22.31 | 5.5 | 8
142 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Zone- V & VI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL N.3) | Assistant Engineer | Junior Engineer | ORD/000922/2023-2024 | 1595/PD | 31/10/2023 | 29/03/2026 | PRINCE INDUSTRIES ( INDIA) | 1031.22 | 225.35 | 21.85 | 12
143 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTC for the period of thirty six month (36) at Zone-V of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-2) | Assistant Engineer | Junior Engineer-2 | ORD/000916/2023-2024 | 1597/PD | 31/10/2023 | 29/03/2026 | PRINCE INDUSTRIES ( INDIA) | 536.56 | 51.3 | 9.56 | 5
144 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Design, Surveying, Engineering, Supplying, Construction, Erection, Installation, Testing And Commissioning Of Fixed Type Intake Jetty With Pump House, Construction Of Subs Stations; Raw Water Rising Main, Bank Protection, 158 MLD (Minimum) Capacity Water Treatment Plant (WTP) Based On Conventional Technologies Considering Extra 20% Overloading; at Siulibari Mouza of Neturia Block to supply water for 14 nos. Block Including Pumping Machineries On EPC/Turnkey Basis In A Single Package (Package-1) Including 3 (Three) Months Trial Run And Operation & Maintenance For 3 Years For Surface Based W/S Scheme For Northern Sector Under Purulia District. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 1563/PD | 26/10/2023 | 02/07/2026 | GAJA ENGINEERING PRIVATE LIMITED | 36300 | 6793.92 | 18.72 | 27
145 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Rudra Mouza under Purulia Division. PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001253/2023-2024 | 1700/PD | 30/11/2023 | 01/08/2025 | M/S CHAKRABORTY CONSTRUCTION | 59.01 | 0 | 0 | 0
146 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kotloi Mouza (Zone-I) Under Purulia Divn PHE DTE. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer,Junior Engineer-4 | ORD/001264/2023-2024 | 1603/PD | 01/11/2023 | 15/12/2024 | SUBODH PRAMANIK | 37.61 | 0 | 0 | 0
147 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XVI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001469/2023-2024 | 1782/PD | 08/12/2023 | 31/05/2025 | PARTHASARATHI SAHABABU | 20.67 | 0 | 0 | 50
148 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001474/2023-2024 | 1786/PD | 08/12/2023 | 01/03/2025 | SUBRATA SINGHADEO | 20.83 | 0 | 0 | 0
149 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IX of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/001458/2023-2024 | 1775/PD | 08/12/2023 | 29/04/2025 | SUJIT CHAKRABORTY | 23.75 | 0 | 0 | 0
150 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001478/2023-2024 | 1789/PD | 08/12/2023 | 23/03/2025 | DEBAKI RANJAN SARKAR | 21.19 | 0 | 0 | 65
151 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | Assistant Engineer | Junior Engineer-1 | ORD/001465/2023-2024 | 1779/PD | 08/12/2023 | 11/02/2026 | MADHU SUDAN RAKSHIT | 20.95 | 0 | 0 | 0
152 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 205 mtr.) | Assistant Engineer | Junior Engineer-2 | ORD/001467/2023-2024 | 1781/PD | 08/12/2023 | 21/03/2025 | CHANDAN CHATTERJEE | 25.44 | 3.65 | 14.34 | 100
153 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Nadiyara Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) |  | ORD/001613/2023-2024 | 1825/PD | 12/12/2023 | 06/02/2025 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 53.85 | 0 | 0 | 1
154 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Design, Surveying, Engineering, Supplying and Construction, Erection, Installation, Testing and Commissioning of 9 Nos of Boosting Station, Pump house , Sub-station Building, Clear Water Raising Main upto 30 Nos of Delivery Point (Existing) & 145 Nos of OHR¿s zone within 14 Nos of block on EPC/ Turnkey Basic in A Single Package (Package II) including 3 (Three) months Trial Run and 3 years Operation & Maintenance for Surface Based W/S scheme; for Northern Sector under Purulia District. | Assistant Engineer | Junior Engineer | ORD/001824/2023-2024 | 74/PD | 10/01/2024 | 10/04/2026 | WPIL LIMITED | 42535 | 8393.5 | 19.73 | 1
155 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-XI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte.. | Assistant Engineer | Junior Engineer-3 | ORD/003534/2023-2024 | 358/PD | 04/03/2024 | 28/04/2025 | SINGHA ENTERPRISE | 21.01 | 0 | 0 | 0
156 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC) including other allied work at gap portion of Tiyashi for Zone-IV of Santuri Block under Purulia Pipe water supply scheme (Northern section) under Purulia Dvision PHED te [ Part-A Mouza- Tiyashi, Marbedya, Ghoramurga]. | Assistant Engineer | Junior Engineer-3 | ORD/001060/2024-2025 | 2121/PD | 05/12/2024 | 01/01/2026 | AMIT PATHAK | 44.28 | 0 | 0 | 0
157 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Satra under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001210/2024-2025 | 109/PD | 21/01/2025 | 01/02/2026 | AKUL SUTRADHAR | 3.92 | 0 | 0 | 60
158 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tube well along with necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Maheshnadi Under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001053/2024-2025 | 2114/PD | 05/12/2024 | 04/05/2025 | ASHOKE KUMAR CHATTERJEE | 19.19 | 0 | 0 | 0
159 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing Left Out &Parallal distribution pipe line including Functional Household Tap Connection (FHTC) and Distribution main in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000217/2024-2025 | 1246/PD | 04/07/2024 | 01/04/2025 | S.S. CONSTRUCTION | 95.44 | 0 | 0 | 0
160 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/003528/2023-2024 | 354/PD | 04/03/2024 | 03/05/2024 | KANJILAL AND CO. | 29.22 | 2.1 | 7.2 | 30
161 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-I ,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division,PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/003530/2023-2024 | 355/PD | 04/03/2024 | 11/11/2024 | KM ENTERPRISES | 21.04 | 0 | 0 | 45
162 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/004042/2023-2024 | 500/PD | 16/03/2024 | 09/07/2025 | SOUMITRA KUMAR DAS | 28.26 | 0 | 0 | 55
163 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying a dedicated pipe Line for Jaratanr, briddhitanr for the distribution System and repairing work at Gungligora of BORAM Under Purulia W/S scheme (Northern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001050/2024-2025 | 2111/PD | 05/12/2024 | 01/04/2025 | SOUMITRA CHAKRABORTY | 11.94 | 0 | 0 | 50
164 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000667/2024-2025 | 1673/PMD | 05/12/2024 | 05/12/2025 | S. PATHAK & CO. | 1.11 | 0 | 0 | 0
165 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying of Balance Pipeline under Command area of Purulia -1 (Northern Sector) under Jal Jeevan Mission Project under Purulia Division, PHE Dte (Bhul Mouza) | Assistant Engineer(HQ) | Junior Engineer-3 | ORD/001051/2024-2025 | 2112/PD | 05/12/2024 | 03/02/2025 | SOUMITRA CHAKRABORTY | 38.35 | 0 | 0 | 70
166 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Making arrangement for support structure for completion of Jack Pushing work under railway line for laying of distribution pipeline & other allied works at lagda Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001064/2024-2025 | 2125/PD | 05/12/2024 | 03/02/2025 | SADHAN GORAIN | 11.12 | 0 | 0 | 100
167 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 28/02/2025 | AVISHEK ENTERPRISE | 5.97 | 0 | 0 | 100
168 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001147/2024-2025 | 2187/PD | 13/12/2024 | 11/02/2025 | JOGMAYA CONSTRUCTION | 20.09 | 0 | 0 | 0
169 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying Distribution Pipe line and other allied work under Balitora Zone-1 at Balitora under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division ,PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001069/2024-2025 | 2129/PD | 05/12/2024 | 31/05/2025 | KHITISH CHANDRA PATHAK | 27.97 | 0 | 0 | 75
170 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Providing Left Out &Parallal distribution pipe line in connection with Jal Jeevan Mission (JJM and) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000241/2024-2025 | 1245/PD | 04/07/2024 | 01/04/2025 | M/S. S. CHOUDHURY | 66.92 | 0 | 0 | 0
171 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Hura Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000328/2024-2025 | 1253/PMD | 22/08/2024 | 22/08/2025 | KAMAKHYA ENTERPRISE | 45.76 | 0 | 0 | 0
172 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone XIII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001339/2024-2025 | 488/PD | 25/03/2025 | 23/07/2025 | MADHU SUDAN RAKSHIT | 59.38 | 0 | 0 | 95
173 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone VI within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001344/2024-2025 | 493/PD | 25/03/2025 | 01/12/2025 | PRINCE INDUSTRIES ( INDIA) | 89.76 | 0 | 0 | 50
174 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Pushing of 600mm dia MS pre cast pipe and 200 mm dia and 150 mm dia MS water carrier pipe by hydraulic jacking method across PMGSY Road for laying distribution line in connection with Jal Jeevan Mission at 3 (three) different location for Zone-II of Purulia - II block for Mahuda Bazar under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/001352/2024-2025 | 500/PD | 25/03/2025 | 23/07/2025 | RANJIB GHATAK | 24.15 | 0 | 0 | 100
175 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000997/2024-2025 | 531/PMD | 28/03/2025 | 27/09/2025 | PINTU DEY | 0.87 | 0 | 0 | 30
176 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector ), Kashipur Block Zone XI & XII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001331/2024-2025 | 477/PD | 25/03/2025 | 23/07/2025 | SUJIT SAHANA | 29.95 | 0 | 0 | 0
177 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Continuation Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. w.e.f- 01.10.2025 to 31.03.2026. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000114/2025-2026 | 1419/PMD | 24/09/2025 | 25/03/2026 | PINTU DEY | 0.86 | 0 | 0 | 0
178 | PURULIA | Hura,Jaipur,Jhalda-I,Jhalda-II,Kashipur,Manbazar-I,Neturia,Para,Puncha,Purulia-I,Purulia-II,Raghunathpur-I,Raghunathpur-II,Santuri | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 | New | Construction of boundary wall at Zone I H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 1141/PD | 17/08/2023 | 16/09/2023 | MAA TARA CONSTRUCTION | 18.03 | 17.77 | 98.55 | 100
Total | [13 empty] | 132441.85 | 16442.14 | 12.41