## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply and Installation of 4KG/HR Gaseous Chlorination system and Chlorine leak absorption system at Lakshmanpur WTP under Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000174/2023-2024 | 1126PMD | 11/10/2023 | 08/02/2024 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 80.55 | 0 | 0 | 0
2 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply delivery and installation of electro mechanical equipments, HSC pump motor sets, MCC, HOT, Valves, Flowmeter ,400 KVA electrical substation, Gaseous chlorination system at Clear water Boosting pump house Under Augmentation of Raghunathpur water supply project Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000178/2023-2024 | 1147/PMD | 16/10/2023 | 13/02/2024 | MAHADEV ENTERPRISE | 331.9 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 71/PD | 17/01/2023 | 17/01/2023 | Resource Division | 1429.07 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1759/PD | 07/12/2023 | 07/12/2023 | Resource Division | 40.12 | 0 | 0 | 0
5 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply delivery and installation of electro mechanical equipment's, HSC pump motor sets, MCC, HOT, Valves, Flowmeter at Proposed Clear water pump house in Lakshmanpur WTP Under Augmentation of Raghunathpur water supply project Bolck : Neturia, Under Purulia Mechanical Division PHE Dte Dist-Purulia. |  |  | ORD/000177/2023-2024 | 458/PMD | 14/03/2024 | 12/07/2024 | NEW ALIGNMENT | 192.41 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Sinking of 1No. 200 mm dia DTH Rigbored TW with allied works at office campus under Aug. of Raghunathpur W/S Scheme (Zone-IB) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/001059/2024-2025 | 2120/PD | 05/12/2024 | 03/02/2025 | MANATOSH SINGH | 4.21 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Providing Mechanical / Electrical Works with all accessories for High Lift Pumping Machinary at Booster Pumping Station - Zone VIII, Augmentation of Raghunathpur Water Supply Project under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000638/2024-2025 | 1570/PMD | 14/11/2024 | 13/05/2025 | COMBINE ENTERPRISES | 47.9 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying balance Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Madhutati or Mautor ,Baldi , Dhanara) |  |  | ORD/001093/2024-2025 | 2182/PD | 13/12/2024 | 11/02/2025 | CHATTERJEE CONSTRUCTION | 90.91 | 0 | 0 | 0
9 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Continuation Work Order for "Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.04.2024 to 30.09.2024 | AE | JUNIOR ENGINEER | ORD/000499/2023-2024 | 525/PMD | 18/03/2024 | 17/09/2024 | PINTU DEY | 0.89 | 0 | 0 | 55
10 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000650/2024-2025 | 1115/PMD | 12/07/2024 | 27/07/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Repering& renovation of 4 (Four) Nos I.E Plant under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000238/2024-2025 | 1086/PD | 07/06/2024 | 06/08/2024 | SADHAN GORAIN | 22.12 | 0 | 0 | 70
12 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery, installation and commissioning of chlorine leak absorption System at different OHR sites of Raghunathpur Water Supply Project under PMD PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000644/2024-2025 | 1576/PMD | 14/11/2024 | 12/02/2025 | TAPAN KUMAR DEY | 90.02 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000207/2023-2024 | 1086/PMD | 29/09/2023 | 30/03/2024 | PINTU DEY | 0.89 | 0 | 0 | 84
14 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply and installation of A.C Machine at Ground floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000606/2023-2024 | 446/PMD | 11/03/2024 | 21/03/2024 | S PATHAK AND CO | 0.79 | 0 | 0 | 99
15 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply and installation of A.C Machine at first floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000608/2023-2024 | 385/PMD | 04/03/2024 | 14/03/2024 | S PATHAK AND CO | 0.79 | 0 | 0 | 99
16 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-I), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000577/2024-2025 | 906/PMD | 10/06/2024 | 25/06/2024 | M/S A.D. CONCERN | 0.95 | 0 | 0 | 80
17 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply and installation of 1 Ton A.C machine at Lakshmanpur Bungalow of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000578/2024-2025 | 1116/PMD | 12/07/2024 | 27/07/2024 | TAPAN KUMAR DEY | 0.62 | 0 | 0 | 100
18 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-V), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000653/2024-2025 | 1324/PMD | 04/09/2024 | 19/09/2024 | PINTU DEY | 0.96 | 0 | 0 | 90
19 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube well-3), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000647/2024-2025 | 1259/PMD | 22/08/2024 | 06/09/2024 | M/S UJJAL DIESEL SERVICE | 0.96 | 0 | 0 | 90
20 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-IV), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000652/2024-2025 | 1323/PMD | 04/09/2024 | 16/12/2024 | M/S A.D. CONCERN | 0.96 | 0 | 0 | 90
21 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying of HDPE Pipe (PE-100, PN-10) for collecting line of riverbed tubewell (for 1, 2, 3 & 4) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division, under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000235/2024-2025 | 1075/PD | 07/06/2024 | 06/08/2024 | KHITISH CHANDRA PATHAK | 6.9 | 0 | 0 | 100
22 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000576/2024-2025 | 1009/PMD | 24/06/2024 | 09/07/2024 | SUJIT MUKHERJEE | 0.95 | 0 | 0 | 80
23 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, fitting, fixing Swajal Gram Village signboard and thorough repairing and Renovation of R.C.C. Elevated Reservoir (Intze Type with solid raft) of Capcaity 1049.84 cum and staging height 25 mtralongwith high lifting of boundary wall and construction of approach road with all allied works and laying of HDPE pipe at Soudagar Para , Goraipara, Bandanga Village and Supply of Chair, Table and Almirah for Seating arrangement of contractual Junior Engineers at the office of the Assistant Engineer, Raghunathpur Sub-Division under Raghunathpur W/S Scheme(German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 1096/PD | 07/06/2024 | 05/09/2024 | M/S SAYAK BHATTACHARYA | 45.37 | 0 | 0 | 100
24 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 1712/PD | 06/09/2024 | 06/09/2024 | Resource Division | 408.72 | 0 | 0 | 0
25 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Quotation for new connection |  |  | BILL/00457/2023-2024 | BP-23-24-281 | 16/02/2024 | 16/02/2024 | WBSEDCL PURULIA | 1.63 | 0 | 0 | 0
26 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply of Diesel & Mobil for vehicle WB56V-4010 for the month of March-2024 under PMD, PHE Dte. |  |  | BILL/00227/2024-2025 | BP-24-25-80 | 02/08/2024 | 02/08/2024 | M/S SANKAR AUTO SERVICE | 0.22 | 0 | 0 | 0
27 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | New Connection for Augmentation of Raghunathpur ZOne- I B (Nanduara) |  |  | BILL/00821/2023-2024 | BP-24-25-27 | 11/06/2024 | 11/06/2024 | WBSEDCL PURULIA | 0.25 | 0 | 0 | 0
28 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Bulk power supply at 11 KV, Purulia for a contractual demand of 400/400/400/400/400 KVA respectively for next consecutive five years, Mouza-Salata, Block-Raghunathpur -I , Purulia |  |  | BILL/00864/2023-2024 | BP-23-24-299 | 05/03/2024 | 05/03/2024 | WBSEDCL PURULIA | 38.16 | 0 | 0 | 0
29 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Quotation for new connection |  |  | BILL/00456/2023-2024 | BP-23-24-221 | 05/12/2023 | 05/12/2023 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
30 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Quotation for new connection |  |  | BILL/00458/2023-2024 | BP-23-24-280 | 16/02/2024 | 16/02/2024 | WBSEDCL PURULIA | 0.61 | 0 | 0 | 0
31 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | New Connection for Augmentation of Raghunathpur ZOne-I B (Sohardi Mouza Babugram, Sanka) |  |  | BILL/00823/2023-2024 |  | 08/02/2024 | 08/02/2024 | WBSEDCL PURULIA | 2.32 | 0 | 0 | 0
32 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Payment to WBSEDCL , Chelyama CCC for new connection at Vill. + P.O. - Chelyama , Rghunathpur , application no,- 2004770178 , reference Id.- 204327440 . |  |  | BILL/00289/2024-2025 | BP-24-25-76 | 02/08/2024 | 02/08/2024 | WBSEDCL PURULIA | 5.36 | 0 | 0 | 0
33 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Payment of New Electric Connection charge at Salata mouza ,Babugram site , Zone - IV B Raghunathpur - 1 under Augmentation of Raghunathpur W.S. Project and payment to WBSEDCL Raghunathpur CCC . Referance Id - 204346008 |  |  | BILL/00191/2024-2025 | BP-24-25-48 | 16/07/2024 | 16/07/2024 | ASSISTANT ENGINEER & IN CHARGE, RAGHUNATHPUR 132 KV SUB STATION (WBSETCL) | 3.11 | 0 | 0 | 0
34 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Replacement of existing two number old VT pumps with new pumps at intake pump house of Lakshmanpur WTP for Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000175/2023-2024 | 1127/PMD | 11/10/2023 | 01/06/2025 | COMBINE ENTERPRISES | 31.33 | 0 | 0 | 91
35 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping machinery at Existing 8 nos OHR and Proposed 6nos OHR site under Augmentation of Raghunathpur water supply project under PMD, PHE, Dte. District Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000231/2023-2024 | 1125/PMD | 11/10/2023 | 01/04/2025 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.79 | 0 | 0 | 50
36 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Construction of Pump House (13 X 8.5 mtr) at Laxmanpur WTP site to accommodate electromechanical equipment as well as safety device under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000328/2024-2025 | 1353/PD | 25/07/2024 | 18/07/2025 | BOSE CONSTRUCTION | 31.86 | 0 | 0 | 25
37 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supplying, laying , fitting fixing Parallel pipe line with allied works at Shaharjuri village , Kharapara village ,Deshra village , KP Rangadihi village &Rangadihi village for increase pressure of Retrofitting works for creation of ' Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kolaboni under Aug. of Raghunathpur W/S Scheme , Zone-IB of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1,Junior Engineer-2,Junior Engineer-3,Junior Engineer-4 | ORD/001151/2024-2025 | 2302/PD | 31/12/2024 | 01/03/2025 | SUBRATA SINGHADEO | 54.42 | 0 | 0 | 0
38 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Name of Mouzas- Rangamati , Gobranda , Charanbandh , Muldi , Bagmanni , Nanduka) |  |  | ORD/001140/2024-2025 | 43/PD | 10/01/2025 | 11/03/2025 | KHITISH CHANDRA PATHAK | 96.11 | 0 | 0 | 0
39 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Sinking of 3 (Three) no tubewell with necessary Pipe line at Bhamuria Head work site under Raghunathpur Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-2 | ORD/001157/2024-2025 | 2309/PD | 31/12/2024 | 01/03/2025 | KHITISH CHANDRA PATHAK | 18.96 | 0 | 0 | 40
40 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying of 250 mm D.I. pipe line for Raw water rising main with manifold at Ramchandrapur under Raghunathpur Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. |  |  | ORD/001175/2024-2025 | 2329/PD | 31/12/2024 | 01/03/2025 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 1.82 | 0 | 0 | 0
41 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying balance Distribution System of Parallel pipe line and changing existing CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-(Khantra, KhairaChak , Ruknibera, Gobindapur, Paranpur, Toldi) | Assistant Engineer | Junior Engineer-4 | ORD/001094/2024-2025 | 2183/PD | 13/12/2024 | 01/07/2025 | NANIGOPAL DEY | 96.2 | 0 | 0 | 0
42 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply of DI Specials & road crossing for Distribution line ZONE-IB of Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000337/2024-2025 | 1363/PD | 25/07/2024 | 10/02/2026 | MADHU SUDAN RAKSHIT | 7.01 | 0 | 0 | 0
43 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Continuation Work Order for"Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.10.2024 to 31.03.2025 | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000570/2024-2025 | 1375/PMD | 19/09/2024 | 20/03/2025 | PINTU DEY | 0.89 | 0 | 0 | 0
44 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Construction of Guard Room with toilet block at Zone-III under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001071/2024-2025 | 2102/PD | 05/12/2024 | 03/06/2025 | SUBHAJIT KUNDU | 6.41 | 0 | 0 | 0
45 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying Distribution System of Parallel pipeline and changing existing Cl main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. (SL-4) | Assistant Engineer | Junior Engineer-4 | ORD/000541/2024-2025 | 1756/PD | 13/09/2024 | 01/01/2026 | MS D.PALIT AND CO. | 190.01 | 0 | 0 | 60
46 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Uporkhajura of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000613/2024-2025 | 865/PMD | 04/06/2024 | 14/06/2024 | ANUP KUMAR SAHA | 0.79 | 0 | 0 | 90
47 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV - B under Purulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000589/2024-2025 | 1447/PMD | 01/10/2024 | 01/03/2025 | BISHWANATH NANDI | 13.34 | 0 | 0 | 65
48 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhujra-IIB (Tube Well-I), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000635/2024-2025 | 914/PMD | 11/06/2024 | 26/06/2024 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
49 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Special repairing works of HDPE pipe line from River side to Karandih Village , Kajuli Village ,Kajuli more to D.ED Collage road , Daldali Majhidih Village & Guard pilling Manifold to CWR Pipe line with all allied works of Retrofitting works in connection with Jal Jeevan Mission (JJM) at Maguria Lalpur under Raghunathpur W/S Scheme (Zone-IB) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001298/2024-2025 | 438/PD | 24/03/2025 | 22/07/2025 | ALOK KUMAR CHAKRABORTY | 31.69 | 0 | 0 | 75
50 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Maintenance work for Construction of Soak pit, Leach pit & Drain at Inspection Bunglow at Lakkhanpur WTP under Raghunathpur W/S Scheme(German Assisted) Zone-IB within Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  |  | ORD/000015/2025-2026 | 572/PD | 07/04/2025 | 06/06/2025 | CHANDAN CHATTERJEE | 5.63 | 0 | 0 | 0
51 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000005/2025-2026 | 568/PMD | 07/04/2025 | 05/08/2025 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0 | 0
52 | PURULIA |  | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Yard lighting arrangement at different OHR site and other works under Augmentation of Raghunathpur Pipe Water Supply Project under PMD, PHE. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000006/2025-2026 | 569/PMD | 07/04/2025 | 01/01/2026 | BISHWANATH NANDI | 24.28 | 0 | 0 | 80
53 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying Distribution System of Parallel pipeline and changing existing Cl main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-I-B) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001367/2024-2025 | 373/PD | 13/03/2025 | 11/07/2025 | DEBAKI RANJAN SARKAR | 128.19 | 0 | 0 | 0
54 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Balance work for Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -II OHR site to Bakdisha village , Velagora Village & Takhrapara village to Susunia village for increase pressure of Retrofitting works in connection with Jal Jeevan Mission (JJM) at Kolaboni under Raghunathpur W/S Scheme (German Assisted) Zone IB of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/001335/2024-2025 | 482/PD | 25/03/2025 | 23/07/2025 | BISWAJIT MAJI | 23.43 | 0 | 0 | 0
55 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Withdrawing of existing CI Distribution pipe line (Damage portion) and relaying of GI pipe (80 mm dia) and distribution parallel HDPE pipe line including other allied works from Adra More to Nilu Kali Mandir at Raghunathpur Water Supply Scheme (Zone-III) under Zone-IV of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001355/2024-2025 | 505/PD | 25/03/2025 | 23/07/2025 | M/S SAYAK BHATTACHARYA | 80.88 | 0 | 0 | 100
56 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Laying of 140 mm dia HDPE pipe line From OHR to Misson Para at Arrah under Raghunathpur Water Supply Scheme (German Assisted) (Zone-IB) of Raghunathpur Sub Division Under Purulia Division PHE Dte | Assistant Engineer | Junior Engineer-1 | ORD/000361/2025-2026 | 1520/PD | 19/08/2025 | 30/12/2025 | RABIN CHANDRA CHAIL | 21.16 | 0 | 0 | 0
57 | PURULIA |  | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | SM/18779 | Augmentation | Balance work for Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -II OHR site Doulatpur Public School to Saldiga village , Belabhal Village , Bahukata village &LadurkaPadarpara toSimlapara village for increase pressure of Retrofitting works in connection with Jal Jeevan Mission (JJM) at Kolaboni under Raghunathpur W/S Scheme (German Assisted) Zone IB of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000360/2025-2026 | 1519/PD | 19/08/2025 | 18/10/2025 | NANIGOPAL DEY | 26.09 | 0 | 0 | 0
Total | [13 empty] | 3889.22 | 0 | 0