## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-4 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000226/2023-2024 | 1256/PMD | 17/11/2023 | 15/02/2024 | RABINDRA NATH KHAN | 21.67 | 7.38 | 34.05 | 0
2 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-2 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000224/2023-2024 | 1254/PMD | 17/11/2023 | 15/02/2024 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 21.66 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-1 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000223/2023-2024 | 1253/PMD | 17/11/2023 | 15/02/2024 | TAPAN KUMAR DEY | 21.67 | 0 | 0 | 0
4 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-3 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000225/2023-2024 | 1255/PMD | 17/11/2023 | 15/02/2024 | SAIBAL SARKAR | 21.67 | 9.25 | 42.67 | 0
5 | PURULIA |  | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing and Renovation of Over Head Reservoir Capcaity 374cum at (ESR) at Lakhanpur W.T.P. under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001337/2023-2024 | 1720/PD | 04/12/2023 | 02/02/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.36 | 0 | 0 | 0
6 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Replacement of 14 Ring Current Collector at Lakshmanpur WTP Clariflocculator under Raghunathpur water supply project under Purulia Mechanical Division , P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) |  | ORD/000440/2023-2024 | 420/PMD | 11/03/2024 | 10/04/2024 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 1.48 | 0 | 0 | 0
7 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing and rectification of Gaseous Chlorination system at OHR no. 5,6 & 7 of Raghunathpur Water Supply Project under P.M.D., P.H.E. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000210/2023-2024 | 1182/PMD | 03/11/2023 | 18/11/2023 | EASTERN INDIA SALES AND SERVICE | 15.26 | 7.63 | 50 | 100
8 | PURULIA |  | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Laying pipe line across railway track area near mouza Shaldiha at Sutaboi under Keliathole Palashkola W/S Scheme within Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000882/2023-2024 | 1532/PD | 16/10/2023 | 15/11/2023 | SADHAN GORAIN | 52.43 | 25.27 | 48.19 | 100
9 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | WBSEDCL for Sohardi Mouza, Babugram, P.O-Sanka, Raghunathpur Water Supply Scheme |  |  | BILL/00146/2024-2025 | BP-24-25-28 | 11/06/2024 |  | WBSEDCL PURULIA | 2.32 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing of internal and External illuminations arrangements at existing Pump house-2 nos, PDB room Transformer room-2 nos , DG room, VCB room-2nos, AVR room, chlorine room, filter house(first floor and ground floor), chemical house (first floor and ground floor), Administrative building and Nine nos of OHR with supply luminaires and under Raghunathpur water supply project under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000039/2024-2025 | 952/PMD | 19/06/2024 | 17/09/2024 | SUBRATA DUTTA | 28.81 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Defixing the existing idle unit and supply delivery and installation of Electro-Magnetic Flow Meter with cable and remote display unit at different site of WTP. Intake OHR inlet and Outlet pipeline at Forest premises at Garpanchakot, WBSEDCL office premises under Raghunathpur water supply project under PMD. PHE. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000040/2024-2025 | 953/PMD | 19/06/2024 | 17/10/2024 | EASTERN INDIA SALES AND SERVICE | 83.58 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing and renovation of Boundary Wall with other allied work at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/003965/2023-2024 | 508/PD | 16/03/2024 | 15/05/2024 | BISWAJIT MAJI | 9.74 | 0 | 0 | 0
13 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Replacement of existing one number old VT pump with new one at intake of Lakshmanpur WTP of Raghunathpur W/S Project with allied works, under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000038/2024-2025 | 951/PMD | 19/06/2024 | 17/09/2024 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 20.75 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing of Chemical house panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000035/2024-2025 | 948/PMD | 19/06/2024 | 17/09/2024 | M/S UJJAL DIESEL SERVICE | 5.66 | 0 | 0 | 0
15 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing of Filter house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE DTE. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000036/2024-2025 | 949/PMD | 19/06/2024 | 17/09/2024 | MOUSUMI BENERJEE | 10.45 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Replacement of existing old Recirculation Sump Pump motor set at Lakshmanpur WTP of Raghunathpur W/S project with allied works, under PMD, PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000037/2024-2025 | 950/PMD | 19/06/2024 | 17/09/2024 | SAIBAL SARKAR | 22.94 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply, delivery & fitting of Fire Extinguisher with refilling of Fire Extinguisher at different sections of Raghunathpur Water Supply Project under Purulia Mechanical Division PHE, Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000454/2023-2024 | 434/PMD | 11/03/2024 | 10/04/2024 | M/S R.K. ENTERPRISE | 2.16 | 1.05 | 48.36 | 10
18 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing of Raw water Intke pump house panel at Lakshmanpur WTP under Raghunathpur water supply project under PMD PHE DTE . | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000077/2024-2025 | 998/PMD | 21/06/2024 | 19/09/2024 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 26.2 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing of Clear water pump house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000078/2024-2025 | 999/PMD | 21/06/2024 | 19/09/2024 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 57.19 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing and renovation of existing structure (i.e. Administrative building, Cholrine House, Filter House, Chemical House ) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/001335/2023-2024 | 1718/PD | 04/12/2023 | 18/01/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 33.25 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Repairing and renovation of existing structure (i.e. Clarifier Tank, CWR, Pump House, Switch Room etc.) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001336/2023-2024 | 1719/PD | 04/12/2023 | 18/01/2024 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 28.94 | 0 | 0 | 0
22 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Street light illumination arrangement at Lakshmanpur WTP East side of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000238/2024-2025 | 1227/PMD | 13/08/2024 | 02/09/2024 | M/S R.K. ENTERPRISE | 0.98 | 0 | 0 | 0
23 | PURULIA |  | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | SM/18915 | Augmentation | Supply of Safety items of Gaseous Chlorination system at Lakshmanpur WTP and OHR no 5 ,6 ,7 under Raghunathpur W/S project under PMD, PHE, Dte | ASSISTANT ENGINEER(H.Q) | JUNIOR ENGINEER | ORD/000042/2024-2025 | 955/PMD | 19/06/2024 | 17/09/2024 | TUSHAR GHOSH | 9.75 | 4.88 | 50 | 100
Total | [13 empty] | 511.94 | 55.44 | 10.83