## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.08 | Assistant Engineer |  | ORD/000445/2022-2023 | 303/PR | 23/06/2022 | 23/06/2023 | BOSE CONSTRUCTION | 4.76 | 1.47 | 30.83 | 100
2 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.02 | Assistant Engineer |  | ORD/000439/2022-2023 | 297/PR | 23/06/2022 | 23/06/2023 | BOSE CONSTRUCTION | 3.66 | 1.1 | 30.08 | 93
3 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Hura Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | Assistant Engineer | Junior Engineer | ORD/000758/2022-2023 | 1354/PD | 31/08/2022 | 30/06/2023 | SUPRIYA MAHANTI MISHRA | 4.81 | 0 | 0 | 100
4 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Dubra Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.04 | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 299/PR | 07/06/2022 | 07/06/2023 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 3.44 | 94.03 | 100
5 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Cheliyama Sub-District Laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.03 | Assistant Engineer | Junior Engineer | ORD/000440/2022-2023 | 298/PR | 23/06/2022 | 05/07/2022 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 3.52 | 96.17 | 100
6 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Raghunathpur Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.10.2023 to 31.08.2024). | Assistant Engineer | Junior Engineer | ORD/000656/2023-2024 | 1349/PD | 13/09/2023 | 14/08/2024 | MANATOSH SINGH | 6.59 | 5.52 | 83.82 | 85
7 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Continuation work order for Guarding arrangement through registered firm for District Laboratory all RWS Office Campus under RWS Purulia Sub-Division under Purulia Division, PHE Dte. (w.e.f.01/10/2023 to 31/03/2024) | Assistant Engineer | Junior Engineer | ORD/002166/2023-2024 | 1434/PD | 29/09/2023 | 30/03/2024 | BOSE CONSTRUCTION | 4.76 | 3.99 | 83.74 | 100
8 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Civil & Electrical Part related to NABL Recognition of Baghmundi Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | JUNIOR ENGINEER | ORD/001630/2023-2024 | 1837/PD | 12/12/2023 | 10/04/2024 | VIVEKANANDA CONSTRUCTION | 5.9 | 5.71 | 96.77 | 100
9 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Civil & Electrical Part related to NABL Recognition of Manbaazar-II Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/001638/2023-2024 | 1838/PD | 12/12/2023 | 10/02/2024 | SATWICK ENTERPRISE | 1.69 | 1.6 | 94.69 | 100
10 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. . (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 861/Pd | 30/06/2023 | 29/06/2024 | TUSHAR KANTI GORAI | 5.26 | 5.01 | 95.25 | 53
11 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Cheliyama Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 858/PD | 30/06/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 4.99 | 94.68 | 100
12 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Jhalda WTP Sub-Dist Laboratory under RWS purulia Sub-Division PHE Dte (w.e.f.01.02.2023 to 31.12.2023). | Assistant Engineer | Junior Engineer | ORD/001020/2022-2023 | 172/PD | 07/02/2023 | 07/01/2024 | ANUP KUMAR SAHA | 7 | 7 | 99.99 | 100
13 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Dubra Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. . (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 859/PD | 30/06/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 5 | 94.84 | 65
14 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 864/PD | 30/06/2023 | 29/06/2024 | ANUP KUMAR SAHA | 8.21 | 7.99 | 97.31 | 100
15 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 866/PD | 30/06/2023 | 29/06/2024 | SK ABBAS | 6.97 | 6.73 | 96.6 | 100
16 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-A) | Assistant Engineer | Junior Engineer | ORD/001079/2022-2023 | 100/PR | 28/02/2023 | 30/03/2023 | COMPUTER MEDIA | 0.92 | 0.91 | 99.81 | 100
17 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-B) | Assistant Engineer | Junior Engineer | ORD/001078/2022-2023 | 101/PR | 28/02/2023 | 30/03/2023 | COMPUTER MEDIA | 0.92 | 0.91 | 99.81 | 100
18 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Continuation order for the work of "Supply of Laboratory reagent/media/consumables required for routine water testing of different laboratories under Purulia Division, PHE Dte. ( For 2 months)" | Assistant Engineer | Junior Engineer | ORD/001267/2023-2024 | 1697/PD | 29/11/2023 | 14/12/2023 | ARUNALOY SCIENTIFIC HOUSE | 18.27 | 18.27 | 100 | 100
19 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub District Laboratory under under RWS Purulia Sub Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 862/PD | 30/06/2023 | 29/06/2024 | ANUDIP SAHA | 8.29 | 7.93 | 95.69 | 100
20 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000111/2023-2024 | 857/PD | 30/06/2023 | 29/06/2024 | BOSE CONSTRUCTION | 5.26 | 2.27 | 43.03 | 100
21 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Balarampur WTP Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.02.2023 to 31.12.2023). | Assistant Engineer | Junior Engineer | ORD/001019/2022-2023 | 171/PD | 07/02/2023 | 07/01/2024 | SADHAN GORAIN | 7 | 6.65 | 94.9 | 100
22 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 12 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-E) | Assistant Engineer | Junior Engineer | ORD/001077/2022-2023 | 99/PR | 28/02/2023 | 30/03/2023 | COMPUTER MEDIA | 0.77 | 0.77 | 99.26 | 100
23 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (2 nos Purulia District laboratory &Jhalda-II SDL,Manbazar -II SDL) SL NO.04 | Assistant Engineer | Junior Engineer | ORD/001072/2022-2023 | 94/PR | 28/02/2023 | 30/03/2023 | COMPUTER MEDIA | 0.66 | 0.66 | 99.75 | 100
24 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Jhalda-I Sub District Laboratory under under RWS Purulia Sub Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | JUNIOR ENGINEER | ORD/000098/2023-2024 | 860/PD | 30/06/2023 | 29/06/2024 | KOUSHIK CHATTERJEE | 8.28 | 7.93 | 95.69 | 80
25 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Santuri Sub-District Water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/000104/2023-2024 | 865/PD | 30/06/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 5.02 | 95.25 | 60
26 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.09.2023 to 31.12.2023) | Assistant Engineer | Junior Engineer | ORD/000924/2023-2024 | 476/A/23 | 31/08/2023 | 31/12/2023 | COMPUTER MEDIA | 0.87 | 0.5 | 57.14 | 100
27 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.02.2023 to 31.12.2023). | Assistant Engineer | Junior Engineer | ORD/001018/2022-2023 | 187/PD | 07/02/2023 | 07/01/2024 | ARUNALOY SCIENTIFIC HOUSE | 7 | 6.65 | 94.9 | 100
28 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus,Ranchi Road under Purulia Division, PHE Dte. [For 11 (Eleven) months]. | Assistant Engineer | Junior Engineer | ORD/001034/2022-2023 | 244/PD | 20/02/2023 | 20/01/2024 | ARUNALOY SCIENTIFIC HOUSE | 9.82 | 9.81 | 99.9 | 100
29 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Bundwan block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June ) | Assistant Engineer | Junior Engineer | ORD/004007/2023-2024 | 95/A/PR | 01/03/2024 | 01/06/2024 | GOPAL CHANDRA MAHATO | 0.97 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Puncha block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) |  | Junior Engineer | ORD/004009/2023-2024 | 97/A/PR | 01/03/2024 | 01/06/2024 | SRIBASH HAZRA | 0.97 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months April to June) | Assistant Engineer | Junior Engineer | ORD/004000/2023-2024 | 86/A/PR | 01/03/2024 | 01/06/2024 | DIPAK MANDAL | 0.96 | 0.15 | 15.27 | 30
32 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Joypur block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004020/2023-2024 | 107/A/PR | 01/03/2024 | 01/06/2024 | BIJAY GORAIN | 0.92 | 0.36 | 39.05 | 40
33 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004001/2023-2024 | 87/A/PR | 01/03/2024 | 01/06/2024 | CHANDAN MONDAL | 0.77 | 0.14 | 18.01 | 30
34 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | JUNIOR ENGINEER | ORD/004008/2023-2024 | 96/A/PR | 01/03/2024 | 01/06/2024 | UTTAM KUMAR MAHATO | 0.97 | 0.39 | 39.77 | 42
35 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004010/2023-2024 | 98/A/PR | 01/03/2024 | 01/06/2024 | TAPAN MAHATO | 0.97 | 0.17 | 17.4 | 30
36 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004011/2023-2024 | 99/A/PR | 01/03/2024 | 01/06/2024 | BABLU MAHATO | 0.97 | 0.32 | 32.88 | 30
37 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Jhalda-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to june) | Assistant Engineer | Junior Engineer | ORD/004002/2023-2024 | 88/A/PR | 01/03/2024 | 01/06/2024 | PRADIP MAHATO | 0.97 | 0.15 | 15.01 | 30
38 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Para block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) |  | Junior Engineer | ORD/004016/2023-2024 | 103/A/PR | 01/03/2024 | 01/06/2024 | ROHIT BANERJEE | 0.97 | 0.12 | 11.93 | 30
39 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Arsha block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004003/2023-2024 | 90/A/PR | 01/03/2024 | 01/06/2024 | SHAMBHU SEKHAR MAJHI | 0.97 | 0.23 | 23.33 | 30
40 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Raghunathpur-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June ) | Assistant Engineer | Junior Engineer | ORD/004015/2023-2024 | 101/A/PR | 01/03/2024 | 01/06/2024 | NISHAN KUMAR DAS | 0.89 | 0.28 | 31.46 | 30
41 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Raghunathpur-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004017/2023-2024 | 104/A/PR | 01/03/2024 | 01/06/2024 | SANGRAM MUKHERJEE | 0.87 | 0.15 | 16.89 | 30
42 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Kashipur block of Purulia District under Purulia Division P. H.E. Dte.( For 1month, April) | Assistant Engineer | Junior Engineer | ORD/004014/2023-2024 | 100/A/PR | 01/03/2024 | 01/04/2024 | PANKAJ MANDAL | 0.76 | 0 | 0 | 74
43 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Jhalda-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | JUNIOR ENGINEER | ORD/004022/2023-2024 | 89/A/PR | 01/03/2024 | 01/06/2024 | UMESH KUMAR MAHATO | 0.97 | 0.15 | 15.77 | 15
44 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Manbazar-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004006/2023-2024 | 92/A/PR | 01/01/2024 | 01/04/2024 | HEMANTA MAHATA | 0.97 | 0 | 0 | 0
45 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Baghmundi block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004004/2023-2024 | 91/A/PR | 01/03/2024 | 01/06/2024 | NIBARAN KUMAR | 0.97 | 0.13 | 13.05 | 30
46 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004019/2023-2024 | 106/A/PR | 01/03/2024 | 01/06/2024 | MILAN MAHATO | 0.97 | 0.44 | 45.55 | 52
47 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Purulia-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) |  | Junior Engineer | ORD/004018/2023-2024 | 105/A/PR | 01/03/2024 | 31/07/2024 | RUDRA PRASAD PATHAK | 0.96 | 0.05 | 5.31 | 100
48 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | Assistant Engineer | Junior Engineer | ORD/004021/2023-2024 | 108/A/PR | 01/03/2024 | 01/06/2024 | SUBAL MAHATO | 0.97 | 0.17 | 17.81 | 100
49 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Bonus bill paid for F.Y:2022-23 for 47 nos. staffs per head Rs.5300/-. |  |  | BILL/01180/2023-2024 | BP2024-25-38/39 | 04/05/2024 | 04/05/2024 | LABORATORY STAFFS | 2.49 | 0 | 0 | 0
50 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Honorarium payment for School & AWC Centre of water test, |  |  | BILL/00119/2024-2025 | BP-2024-25-124 | 30/05/2024 | 30/05/2024 | LABORATORY STAFFS | 0.3 | 0 | 0 | 0
51 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Ad-hoc Bonus 2023-24 bill payment for the Laboratory 52 nos. @ Rs.6000/- staffs. |  |  | BILL/00942/2024-2025 | BP-2024-25-522 | 29/10/2024 | 29/10/2024 | LABORATORY STAFFS | 3.12 | 0 | 0 | 0
52 | PURULIA |  | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19090 | Support-WQMSP | Monthly Remunaration bill paid for F.Y:2022-23 for 47 nos. staffs per head Rs.5300/-. |  |  | BILL/00043/2024-2025 |  | 25/04/2024 | 25/04/2024 | LABORATORY STAFFS | 2.49 | 0 | 0 | 0
Total | [13 empty] | 177.95 | 134.73 | 75.71