## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Rectification of internal & external lighting arrangement at conference hall & allied premises of awareness generation cum water sample collection centre at Mouza-ghat Block - Manbazar-2 under Purulia Mechanical Division under PHE Dte. |  | JUNIOR ENGINEER | ORD/000077/2023-2024 | 581/PMD | 19/05/2023 | 18/06/2023 | PREMNATH MITRA | 11.92 | 0 | 0 | 70
2 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Manbazar Water Supply scheme Block Manbazar-I under PMD PHE Dte. District Purulia. (2nd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000218/2023-2024 | 1203/PMD | 03/11/2023 | 01/02/2024 | PRINCE INDUSTRIES (INDIA) | 21.5 | 0 | 0 | 0
3 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Replacement of old centrifugal pump motor sets by the new pump motor set with supply and installation of Scada compatible MCC panel at clear water pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000066/2023-2024 | 553/PMD | 16/05/2023 | 15/07/2023 | RABINDRA NATH KHAN | 110.31 | 110.31 | 100 | 100
4 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2023-2024 | 555/PMD | 16/05/2023 | 15/07/2023 | TAPAN KUMAR DEY | 61.95 | 61.95 | 100 | 95
5 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-1) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2023-2024 | 556/PMD | 16/05/2023 | 15/07/2023 | SWAPAN ENTERPRISE | 21.65 | 21.15 | 97.7 | 10
6 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-2) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000070/2023-2024 | 557/PMD | 16/05/2023 | 15/07/2023 | NUPUR CHANDRA HALDER | 21.66 | 21.66 | 100 | 65
7 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-3) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000071/2023-2024 | 558/PMD | 16/05/2023 | 15/07/2023 | GOENKA ENTERPRISE | 21.65 | 20.67 | 95.46 | 100
8 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-4) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2023-2024 | 559/PMD | 16/05/2023 | 15/07/2023 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 21.65 | 21.65 | 100 | 100
9 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-5) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000074/2023-2024 | 560/PMD | 16/05/2023 | 15/07/2023 | H K DAS AND CO | 21.65 | 21.65 | 100 | 100
10 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Installation of One no submersible pumping machinery at intake pump house with supply and installation of Scada compatible MCC panel at Manbazar-II (part) w/s scheme under PMD, PHE, Dte. in the district of purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2023-2024 | 582/PMD | 19/05/2023 | 18/07/2023 | TAPAN KUMAR DEY | 26.38 | 26.26 | 99.52 | 60
11 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Augmentation of existing gaseous chlorination system at Manbazar-2(Part) w/s Scheme under Purulia mechanical Division, PHE, Dte. in the purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000073/2023-2024 | 561/PMD | 16/05/2023 | 15/07/2023 | ASHOKE ADHIKARY | 15.5 | 15.5 | 100 | 100
12 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Replacement of Rupture & multiple jointed LT Cable line from clear water pump house to Intake pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2023-2024 | 554/PMD | 16/05/2023 | 15/07/2023 | ANUP KR. SAHA | 42.18 | 42.05 | 99.68 | 100
13 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR DANGORDI FOR AUG OF MANBAZAR -II(PART) WATER SUPPLY SCHEME |  |  | BILL/00097/2023-2024 | BP-2023-2024-71 | 14/07/2023 | 14/07/2023 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
14 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR KUTNI UNDER AUG OF MANBAZAR-II(PART) WATER SUPPLY SCHEME |  |  | BILL/00098/2023-2024 | BP-2023-2024-74 | 14/07/2023 | 14/07/2023 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
15 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | New service connection for khariduara OHR campus for Aug of Manbazar (part-II) W/S scheme |  |  | BILL/00090/2023-2024 | BP-2023-2024-73 | 14/07/2023 | 14/07/2023 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
16 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR HENSLA UNDER AUGMENTATION OF MANBAZAR-II (PART) WATER SUPPLY SCHEME |  |  | BILL/00096/2023-2024 | BP-2023-2024-72 | 14/07/2023 | 14/07/2023 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
17 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | New service connection for Kutni OHR campus for Aug of Manbazar -II (part II) W/S scheme |  |  | BILL/00091/2023-2024 |  | 22/06/2023 | 22/06/2023 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
18 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Providing and Installation of Electro-Mechanical Equipment¿s at Intake, Clear water Pump House and 5 nos. OHRs in Manbazar-II (Part) water supply scheme under Purulia Mechanical Division, PHE, Dte., District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000637/2024-2025 | 1569/PMD | 14/11/2024 | 12/02/2025 | EASTERN INDIA SALES AND SERVICE | 80.69 | 0 | 0 | 0
19 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Installation of 3nos(10KW) on grid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at Manbazar-II(Part) water supply scheme PMD, PHE, Dte. District Purulia. (3rd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000548/2023-2024 | 483/PMD | 14/03/2024 | 05/09/2025 | WATER TECH | 15.33 | 0 | 0 | 100
20 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Arrangement for high pressure testing of Sub -Station equipment for 500 KVA Sub - Station at Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE,Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2024-2025 | 971/PMD | 20/06/2024 | 20/07/2024 | TAPAN KUMAR DEY | 1.19 | 1.19 | 100 | 100
21 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Making fencing boundry at Transformer Yard of Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000690/2024-2025 | 1702/PMD | 06/12/2024 | 01/12/2025 | TAPAN KUMAR DEY | 1.53 | 0 | 0 | 100
22 | PURULIA |  | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | SM/16414 | Augmentation | Payment of Consumption Meter , generation Metering installation for 30 KW Solar Plant at WTP under Manbazar - II Water Supply Scheme. |  |  | BILL/00657/2025-2026 |  | 10/11/2025 | 10/11/2025 | PURULIA REGIONAL OFFICE OF W.B.S.E.D.C.L | 0.23 | 0 | 0 | 0
Total | [13 empty] | 498.43 | 364.05 | 73.04