## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Purulia I Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000135/2023-2024 | 895/PMD | 01/08/2023 | 30/09/2023 | ANUP KR. SAHA | 6.42 | 5.32 | 82.92 | 83
2 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Hura Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000138/2023-2024 | 907/PMD | 07/08/2023 | 06/10/2023 | SEN BROTHERS | 6.42 | 5.32 | 82.95 | 90
3 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Purulia II Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000139/2023-2024 | 908/PMD | 07/08/2023 | 06/10/2023 | SAIBAL SARKAR | 6.42 | 5.32 | 82.92 | 50
4 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Balarampur Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000140/2023-2024 | 909/PMD | 07/08/2023 | 06/10/2023 | THE BUSINESS ENGINEERS INDIA | 3.21 | 2.66 | 82.88 | 90
5 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Bundwan Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000142/2023-2024 | 911/PMD | 07/08/2023 | 06/10/2023 | THE BUSINESS ENGINEERS INDIA | 3.21 | 2.66 | 82.88 | 50
6 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Bagmundi Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000137/2023-2024 | 906/PMD | 07/08/2023 | 06/10/2023 | COMBINE ENTERPRISES | 6.42 | 5.32 | 82.88 | 80
7 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Puncha Block under PMD, PHE, Dte. District Purulia. (2 nd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000214/2023-2024 | 1200/PMD | 03/11/2023 | 02/01/2024 | P. T. ENTERPRISE | 3.16 | 2.62 | 83.12 | 90
8 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Para Block under PMD, PHE, Dte. District Purulia. (2 nd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000187/2023-2024 | 1177/PMD | 03/11/2023 | 01/02/2024 | S. PATHAK & CO. | 6.3 | 5.23 | 83.05 | 85
9 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Manbazar I Block under PMD, PHE, Dte. District Purulia. (3rd Call) | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000549/2023-2024 | 484/PMD | 14/03/2024 | 13/05/2024 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.21 | 0 | 0 | 0
10 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Jhalda II Block under PMD, PHE, Dte. District Purulia.(2nd Call) | ASSISTANT ENGINEER,DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000612/2024-2025 | 1638/PMD | 29/11/2024 | 28/01/2025 | THE BUSINESS ENGINEERS INDIA | 6.41 | 0 | 0 | 0
11 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of display Board as per deptt. spec for all sanction solar scheme at different block (Manbazar- I, kashipur Bagmundi, Arsha etc) under Purulia Mechanical Division, PHE Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000318/2023-2024 | 189/PMSD(Drilling) | 15/12/2023 | 04/01/2024 | PINTU DEY | 0.97 | 0 | 0 | 100
12 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of display board as per deptt spec for all sanction solar scheme at different block (Hura,Jhalda II, Purulia I, & II etc) under Purulia Mechanical Division, PHE Dte | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000319/2023-2024 | 188/PMSD(Drilling) | 15/12/2023 | 04/01/2024 | PINTU DEY | 0.97 | 0.97 | 100 | 100
13 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Arsha Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000134/2023-2024 | 894/PMD | 01/08/2023 | 02/02/2025 | SHWET BARANI | 12.84 | 0 | 0 | 80
14 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Barabazar Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000141/2023-2024 | 910/PMD | 07/08/2023 | 06/10/2023 | NUPUR CHANDRA HALDER | 3.21 | 2.66 | 82.89 | 85
15 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Kashipur Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000144/2023-2024 | 913/PMD | 07/08/2023 | 06/10/2023 | A.K INDUSTRIES | 19.25 | 0 | 0 | 70
16 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Joypur Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000143/2023-2024 | 912/PMD | 07/08/2023 | 06/10/2023 | NUPUR CHANDRA HALDER | 3.21 | 2.66 | 82.89 | 85
17 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Neturia Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in | ORD/000145/2023-2024 | 914/PMD | 07/08/2023 | 06/10/2023 | A.K INDUSTRIES | 19.25 | 0 | 0 | 100
18 | PURULIA |  | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA | SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Santuri Block under PMD, PHE, Dte. District Purulia. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000171/2023-2024 | 919/PMD | 07/08/2023 | 06/10/2023 | MS ELECTRO ENTERPRISES | 9.63 | 0 | 0 | 85
Total | [13 empty] | 120.47 | 40.74 | 33.82