## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 4.44 | 92.4 | 0
2 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Work Order for Procurement of Chemicals required for smooth running of the laboratories under Howrah Division, PHE Dte. | AE HQ |  | ORD/000180/2022-2023 | 1414/HD | 08/07/2022 | 23/07/2022 | M/S LAXMI ENTERPRISE | 4.17 | 4.17 | 100 | 0
3 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supply of chemicals/consumables, Glasswares, Instruments & Miscellaneous related to NABL Accreditation for Chemical Testing of potable water of District level Water Quality Testing Laboratory for 11 nos mandatory parameters for Howrah District Water Testing Laboratory under Howrah Division, PHE Dte. |  |  | VCH/000962/2021-2022 | BP-2021-22-409 | 14/03/2022 | 14/03/2022 | NATURAL RESOURCES CONSORTIUM | 8.72 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of water purifer machine and LED Board at different District-Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000893/2022-2023 | 975/AE/USD | 24/03/2023 | 08/05/2023 | SUSHANTA MONDAL | 0.54 | 0.54 | 100 | 100
5 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Anandaniketan Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000899/2022-2023 | 976/AE/USD | 24/03/2023 | 08/05/2023 | C.S CONSTRUCTION | 0.97 | 0.97 | 100 | 100
6 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Howrah District water Testing Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000896/2022-2023 | 979/AE/USD | 24/03/2023 | 08/05/2023 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
7 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Silampur Sub- District water Testing Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000897/2022-2023 | 980/AE/USD | 24/03/2023 | 08/05/2023 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
8 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Gandalpara Nabin Pragati Seva Samity Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000895/2022-2023 | 978/AE/USD | 24/03/2023 | 08/05/2023 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
9 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Supplying, fitting and fixing of ACP LED Board for Ranapara Gramin Bikash Kendra Sub-District water Testing Laboratory under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000894/2022-2023 | 977/AE/USD | 24/03/2023 | 08/05/2023 | ABONTICA ENTERPRISE | 0.97 | 0.97 | 100 | 100
10 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | Procurement of Chemicals for water testing laboratories under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000073/2024-2025 | 3137/HD | 10/07/2024 | 25/07/2024 | LAB ANALYTICS | 7.38 | 7.38 | 100 | 100
11 | HOWRAH |  | Howrah Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratories. | SM/06614 | Support-WQMSP | PROCUREMENT OF CHEMICALS FOR WATER TESTING LABORATORIES UNDER HOWRAH DIVISION PHE DTE. | AE HQ | je_blk_ballyjag_how | ORD/000281/2025-2026 | 4415/HD | 25/11/2025 | 24/01/2026 | LAB ANALYTICS | 13.58 | 0 | 0 | 100
Total | [13 empty] | 44.04 | 21.38 | 48.54