## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Chaltakhali (Part) & Jotsadar Mouza) | AE/Ulu |  | ORD/000110/2020-2021 | 1505/HD | 04/11/2020 | 04/12/2020 | M/S ASHIRBAD (INDIA) | 29.03 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Chaltakhali Mouza (Part) | AE/Ulu |  | ORD/000111/2020-2021 | 1506/HD | 04/11/2020 | 04/12/2020 | M/S ASHIRBAD (INDIA) | 28.82 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000954/2020-2021 | 8443108 | 30/03/2021 | 30/03/2021 | PRADIP KUMAR JATI | 25.73 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting Khosalpur Water Supply Scheme |  |  | VCH/000869/2020-2021 | 84435 | 01/03/2021 | 01/03/2021 | PRADIP KUMAR JATI | 24.12 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000871/2020-2021 | 844327 | 17/03/2021 | 17/03/2021 | JAHANGIR ALAM | 26.44 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | SM/06713 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. |  |  | VCH/000952/2020-2021 | 8443106 | 30/03/2021 | 30/03/2021 | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0 | 0
Total | [13 empty] | 155.31 | 0 | 0