## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) |  |  | VCH/000246/2021-2022 | W/347 | 07/10/2021 | 07/10/2021 | USHA CONCERN | 3.52 | 0 | 0 | 0
2 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | PROVIDINMG STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMRAGORI PWSS, AMTA-II, BLOCK UNDER HOWAH DIVISION, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000051/2022-2023 | 297/CMSD-I (D) | 08/07/2022 | 23/07/2022 | DIPALI CONSTUCTION | 4.76 | 0 | 0 | 0
3 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCHEME, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000035/2022-2023 | 206/CMSD-I (D) | 20/06/2022 | 05/07/2022 | DIPALI CONSTUCTION | 2.09 | 0 | 0 | 0
4 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR SARDA W/S, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000036/2022-2023 | 205/CMSD-I (D) | 20/06/2022 | 05/07/2022 | DIPALI CONSTUCTION | 3.11 | 0 | 0 | 0
5 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000052/2022-2023 | 300/CMSD-I (D) | 08/07/2022 | 23/07/2022 | DIPALI CONSTUCTION | 3.44 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | Additional Retrofitting Sarda |  |  | VCH/000974/2021-2022 | BP-2021-22-423 | 21/03/2022 | 21/03/2022 | SUMANA ENTERPRISE | 2.17 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at SARDA W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) |  |  | VCH/000812/2021-2022 | BP-2021-22-362 | 28/02/2022 | 28/02/2022 | BISWAJIT BAG | 4.76 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme | SM/06721 | Retrofitting | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division, P.H.E. Dte. | AE HQ |  | ORD/000348/2024-2025 | 4832/HD | 20/11/2024 | 20/12/2024 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
Total | [13 empty] | 28.64 | 0 | 0