## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-C) | AE/SADAR | JE Sadar | ORD/000138/2020-2021 | 1550/HD | 05/11/2020 | 05/12/2020 | M/S ASHIRBAD (INDIA) | 18.96 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) | AE/SADAR | JE Sadar | ORD/000139/2020-2021 | 1551/HD | 05/11/2020 | 05/12/2020 | N. G ENGINEERING | 18.82 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-B) | AE/SADAR | JE Sadar | ORD/000142/2020-2021 | 1554/HD | 05/11/2020 | 05/12/2020 | M/S ASHIRBAD (INDIA) | 18.8 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Ground Water Based Piped Water Supply Scheme For Majhu Khetra |  |  | VCH/000995/2020-2021 | 844339 | 19/03/2021 | 19/03/2021 | DEV DAS SHAW | 5.64 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS |  |  | VCH/000727/2020-2021 | 84432 | 09/02/2021 | 09/02/2021 | N. G ENGINEERING | 16.5 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS |  |  | VCH/000730/2020-2021 | 84435 | 09/02/2021 | 09/02/2021 | M/S ASHIRBAD (INDIA) | 16.65 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS |  |  | VCH/000731/2020-2021 | 84436 | 09/02/2021 | 09/02/2021 | M/S ASHIRBAD (INDIA) | 16.38 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. and Laying of additional UPVC pipe line of 63 mm & 75 mm dia. Total 1500 mtr. Length within the Command area of Majukhtra PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-II) | AE/SADAR | JE Sadar | ORD/000429/2021-2022 | 343/HD | 17/02/2022 | 19/03/2022 | KRISH CONSTRUCTION | 4.53 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | SM/06774 | Retrofitting | Construction of Septic tank chamber with soak well at Head work site in Maju Khetra w/s scheme under Howrah Sadar Sub-Division, PHE Dte. |  |  | VCH/000690/2021-2022 | 844347 | 22/02/2022 | 22/02/2022 | ABONTICA ENTERPRISE | 0.59 | 0 | 0 | 0
Total | [13 empty] | 116.86 | 0 | 0