## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-B) | AE/SADAR |  | ORD/000012/2020-2021 | 840/HD | 25/08/2020 | 24/09/2020 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-C) | AE/SADAR |  | ORD/000013/2020-2021 | 841/HD | 25/08/2020 | 24/09/2020 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-D) | AE/SADAR |  | ORD/000014/2020-2021 | 842/HD | 25/08/2020 | 24/09/2020 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-G) | AE/SADAR |  | ORD/000017/2020-2021 | 845/HD | 25/08/2020 | 24/09/2020 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-K) | AE/SADAR |  | ORD/000021/2020-2021 | 849/HD | 25/08/2020 | 24/09/2020 | TIYASA ENTERPRISE | 4.56 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-R) | AE/SADAR |  | ORD/000028/2020-2021 | 856/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-T) | AE/SADAR |  | ORD/000030/2020-2021 | 858/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-U) | AE/SADAR |  | ORD/000031/2020-2021 | 859/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-V) | AE/SADAR |  | ORD/000032/2020-2021 | 860/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-N) | AE/SADAR |  | ORD/000024/2020-2021 | 852/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-X) | AE/SADAR |  | ORD/000034/2020-2021 | 862/HD | 25/08/2020 | 24/09/2020 | TIYASA ENTERPRISE | 4.56 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Y) | AE/SADAR |  | ORD/000035/2020-2021 | 863/HD | 25/08/2020 | 24/09/2020 | S.B. ENTERPRISE | 4.56 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Z) | AE/SADAR |  | ORD/000036/2020-2021 | 864/HD | 25/08/2020 | 24/09/2020 | S.B. ENTERPRISE | 4.56 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Q) | AE/SADAR |  | ORD/000027/2020-2021 | 855/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-E) | AE/SADAR |  | ORD/000015/2020-2021 | 843/HD | 25/08/2020 | 24/09/2020 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-W) | AE/SADAR |  | ORD/000033/2020-2021 | 861/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-H) | AE/SADAR |  | ORD/000018/2020-2021 | 846/HD | 25/08/2020 | 24/09/2020 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-I) | AE/SADAR |  | ORD/000019/2020-2021 | 847/HD | 25/08/2020 | 24/09/2020 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-O) | AE/SADAR |  | ORD/000025/2020-2021 | 853/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-P) | AE/SADAR |  | ORD/000026/2020-2021 | 854/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-S) | AE/SADAR |  | ORD/000029/2020-2021 | 857/HD | 25/08/2020 | 24/09/2020 | PRADIP KUMAR JATI | 4.56 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-A) | AE/SADAR |  | ORD/000011/2020-2021 | 839/HD | 25/08/2020 | 24/09/2020 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-J) | AE/SADAR |  | ORD/000020/2020-2021 | 848/HD | 25/08/2020 | 24/09/2020 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
24 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-L) | AE/SADAR |  | ORD/000022/2020-2021 | 850/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-M) | AE/SADAR |  | ORD/000023/2020-2021 | 851/HD | 25/08/2020 | 24/09/2020 | DEV DAS SHOW | 4.56 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-F) | AE/SADAR |  | ORD/000016/2020-2021 | 844/HD | 25/08/2020 | 24/09/2020 | N. G ENGINEERING | 4.56 | 0 | 0 | 0
27 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-Q |  |  | VCH/000419/2020-2021 | W/456 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.46 | 0 | 0 | 0
28 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-S |  |  | VCH/000424/2020-2021 |  | 02/12/2020 | 02/12/2020 | PRADIP KUMAR JATI | 4.49 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-O |  |  | VCH/000415/2020-2021 | W/455 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-L |  |  | VCH/000418/2020-2021 | W/452 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.43 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000427/2020-2021 | W/463 | 28/12/2020 | 28/12/2020 | TIYASA ENTERPRISE | 4.45 | 0 | 0 | 0
32 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-J) |  |  | VCH/000434/2020-2021 | W/465 | 29/12/2020 | 29/12/2020 | N. G ENGINEERING | 4.47 | 0 | 0 | 0
33 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/000641/2020-2021 | W/508 | 18/01/2021 | 18/01/2021 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
34 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-I) |  |  | VCH/000433/2020-2021 | W/464/4 | 30/12/2020 | 30/12/2020 | N. G ENGINEERING | 4.47 | 0 | 0 | 0
35 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F) |  |  | VCH/000430/2020-2021 | W/464 | 30/12/2020 | 30/12/2020 | N. G ENGINEERING | 4.45 | 0 | 0 | 0
36 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-H) |  |  | VCH/000432/2020-2021 | W/464/3 | 30/12/2020 | 30/12/2020 | N. G ENGINEERING | 4.49 | 0 | 0 | 0
37 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P |  |  | VCH/000414/2020-2021 | W/453 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
38 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-W |  |  | VCH/000420/2020-2021 | W/466 | 30/12/2020 | 30/12/2020 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
39 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-G) |  |  | VCH/000431/2020-2021 | W/464/2 | 30/12/2020 | 30/12/2020 | N. G ENGINEERING | 4.5 | 0 | 0 | 0
40 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Part-K |  |  | VCH/000426/2020-2021 | W/462 | 28/12/2020 | 28/12/2020 | TIYASA ENTERPRISE | 4.46 | 0 | 0 | 0
41 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-A) |  |  | VCH/000435/2020-2021 | W/457 | 28/12/2020 | 28/12/2020 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0 | 0
42 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-N |  |  | VCH/000416/2020-2021 | W/454 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.49 | 0 | 0 | 0
43 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-R |  |  | VCH/000425/2020-2021 | W/466 | 30/12/2020 | 30/12/2020 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
44 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-V |  |  | VCH/000421/2020-2021 | W/466/2 | 30/12/2020 | 30/12/2020 | PRADIP KUMAR JATI | 4.46 | 0 | 0 | 0
45 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) (Part-Z) |  |  | VCH/000428/2020-2021 | W/451 | 29/12/2020 | 29/12/2020 | S.B. ENTERPRISE | 4.46 | 0 | 0 | 0
46 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-Y) |  |  | VCH/000429/2020-2021 | W/451/1 | 29/12/2020 | 29/12/2020 | S.B. ENTERPRISE | 4.44 | 0 | 0 | 0
47 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-M |  |  | VCH/000417/2020-2021 | W/452/2 | 28/12/2020 | 28/12/2020 | DEV DAS SHOW | 4.47 | 0 | 0 | 0
48 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-T |  |  | VCH/000423/2020-2021 | W/466/4 | 30/12/2020 | 30/12/2020 | PRADIP KUMAR JATI | 4.47 | 0 | 0 | 0
49 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-U |  |  | VCH/000422/2020-2021 | W/466/3 | 30/12/2020 | 30/12/2020 | PRADIP KUMAR JATI | 4.48 | 0 | 0 | 0
50 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) | SM/06775 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | AE/SADAR |  | ORD/000427/2021-2022 | 341/HD | 17/02/2022 | 19/03/2022 | MONIRUL ISLAM | 4.47 | 0 | 0 | 0
Total | [13 empty] | 226.12 | 0 | 0