## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-A) | AE/SADAR |  | ORD/000208/2020-2021 | 1390/HD | 16/10/2020 | 15/11/2020 | DEV DAS SHOW | 4.57 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-D) | AE/SADAR |  | ORD/000211/2020-2021 | 1393/HD | 16/10/2020 | 15/11/2020 | PRADIP KUMAR JATI | 4.27 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-F) | AE/SADAR |  | ORD/000213/2020-2021 | 1395/HD | 16/10/2020 | 15/11/2020 | N. G ENGINEERING | 4.65 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-G) | AE/SADAR |  | ORD/000214/2020-2021 | 1396/HD | 16/10/2020 | 15/11/2020 | N. G ENGINEERING | 4.65 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-L) | AE/SADAR |  | ORD/000219/2020-2021 | 1401/HD | 16/10/2020 | 15/11/2020 | S.B. ENTERPRISE | 1.56 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-E) | AE/SADAR |  | ORD/000212/2020-2021 | 1394/HD | 16/10/2020 | 15/11/2020 | PRADIP KUMAR JATI | 2.81 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-B) | AE/SADAR |  | ORD/000209/2020-2021 | 1391/HD | 16/10/2020 | 15/11/2020 | DEV DAS SHOW | 4.5 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-I) | AE/SADAR |  | ORD/000216/2020-2021 | 1398/HD | 16/10/2020 | 15/11/2020 | M/S ASHIRBAD (INDIA) | 3.97 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-J) | AE/SADAR |  | ORD/000217/2020-2021 | 1399/HD | 16/10/2020 | 15/11/2020 | M/S ASHIRBAD (INDIA) | 3.78 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) | AE/SADAR |  | ORD/000218/2020-2021 | 1400/HD | 16/10/2020 | 15/11/2020 | S.B. ENTERPRISE | 2.3 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-C) | AE/SADAR |  | ORD/000210/2020-2021 | 1392/HD | 16/10/2020 | 15/11/2020 | PRADIP KUMAR JATI | 4.31 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-H) | AE/SADAR |  | ORD/000215/2020-2021 | 1397/HD | 16/10/2020 | 15/11/2020 | N. G ENGINEERING | 3.97 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000201/2021-2022 | W/178 | 14/08/2021 | 14/08/2021 | S.B. ENTERPRISE | 11.99 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000203/2021-2022 | W/179 | 14/08/2021 | 14/08/2021 | M/S ASHIRBAD (INDIA) | 21.8 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000200/2021-2022 | W/172 | 14/08/2021 | 14/08/2021 | DEV DAS SHAW | 16.14 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000202/2021-2022 | W/177 | 14/08/2021 | 14/08/2021 | PRADIP KUMAR JATI | 12.13 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Work Order for Laying of 90mm dia,Node point 53-55, 55-57, 57-101, Total 940 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Laskarpur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) Part ¿A | AE/SADAR |  | ORD/000433/2021-2022 | 347/HD | 17/02/2022 | 19/03/2022 | MONIRUL ISLAM | 4.07 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V) (Part-B) | AE/SADAR |  | ORD/000434/2021-2022 | 348/HD | 17/02/2022 | 19/03/2022 | KRISH CONSTRUCTION | 2.53 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000422/2021-2022 | 336/HD | 17/02/2022 | 19/03/2022 | MONIRUL ISLAM | 3.96 | 2.34 | 59.06 | 0
20 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000591/2021-2022 | W/592 | 21/12/2021 | 21/12/2021 | MONIRUL ISLAM | 3.32 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | VCH/000791/2022-2023 | 84438 | 22/09/2022 | 22/09/2022 | MONIRUL ISLAM | 8.49 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Development Internal pathway and allied work at H/W of Laskarpur PWSS. |  |  | VCH/000818/2022-2023 | 844318 | 27/09/2022 | 27/09/2022 | RAJLAKSHMI ENTERPRISE | 3.44 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-IV) | SM/06778 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) |  |  | VCH/000789/2022-2023 | 844323 | 29/09/2022 | 29/09/2022 | S.B. ENTERPRISE | 3.63 | 0 | 0 | 0
Total | [13 empty] | 136.83 | 2.34 | 1.71